As we move forward we have two huge tasks to complete at the same time, the integration with UBS Warburg and the re-start of our business.    The UBS corporate governance facilitates the creation of several committees which will meet on a regular basis to resolve issues and report on progress.  Within the UBS framework we will be creating a 'Transitional Steering Committee',  'Integration Committee' and 'Gas and Power Operating Committee'.

UBS has already created the Integration Committee which we will merge into.

Dave Forster will be attending all of these groups in the early weeks to ensure consistency and good communication.  Dave will also act as our point person for Mark Bridges from UBS, ensuring the simplest and most effective methods of communication are in place for both parties.

Please make a note of the meetings you are to attend, Tammie Schoppe will circulate dial-in numbers for the meetings in Sections 1 and 3 below.  The permanent dial in for the Integration committee has already been circulated to those attending.

This email outlines the governance structure that will be formalized with immediate effect:

Governance of UBS Warburg Energy LLC

- Transitional Steering Committee

This committee will be responsible for the overall management and co-ordination of the integration efforts for both the initial Launch Date and the later Disentanglement Date at the end of 2002.

Committee Members:

UBSW

Mike Hutchins (co-chair)

Pat O’Donnell

Mike Bolin

# UBSW Energy

Greg Whalley (co-chair)

Louise Kitchen

Proposed Logistics:

- This committee will meet on a weekly basis until shortly after the Launch Date, and then bi-monthly thereafter until December 31 2002.

- Minutes will be distributed to senior UBS and Enron management only.

- Proposed Time- Wednesday 8:30am CST  commencing February 6, 2002.

2. Integration Committee

This committee will be responsible for the day-to-day management and co-ordination of the integration efforts for both the initial Launch Date and the later Disentanglement Date at the end of  2002. Any issues, which this committee cannot resolve, will be escalated to the Transitional Steering Committee.

Proposed Committee Members:

Management:

UBSW			Pat O’Donnell (co-chair)

UBSW Energy		Louise Kitchen (co-chair)

Program Management:

UBSW			Mark Bridges

Beth Barrett d’Auria

UBSW Energy		David Forster

CFI:			Mike Hutchins

Collette Dow

Operations:

UBSW			Ernie Pittarelli

UBSW Energy		Sally Beck 
Legal:

UBSW			Louis Eber

UBSW Energy		Mark Haedicke

Mark Taylor

Financial Operations:

UBSW			Per Dyrvik

UBSW Energy		Wes Colwell

Credit:

UBSW 			Bill Glass

UBSW Energy		Bill Bradford 
        	Market Risk:

UBSW			Mike Stockman

UBSW Energy		David Port 
Technology:

UBSW			Matt Meinel

UBSW Energy		Jay Webb

Jenny Rub

Canada:		Peter Keohane

Security:		Steve Kinross 
Corp. Comm:		Claudia Robinson 
 			Sid Karpoff 
HR:

UBSW			Audrey Martin/Cheryl Roberts

UBSW Energy		David Oxley 
Corp. Services:

UBSW			Bruce Reilly

UBSW Energy		Wes Colwell

CRE:

UBSW			Markus Buergler

UBSW Energy		Jeff Golden

Proposed Logistics:

- This committee will meet on a weekly basis until reviewed at December 31 2002.

- Minutes will be distributed to the Transitional Steering Committee and team members as appropriate.

- Time - Thursday 9:00am CST

3.	Gas and Power Operating Committee:

This committee will be responsible for the operational running of the Gas and Power Trading business. The initial focus of this group will be the re-starting of the business. Following the relaunch the purpose of the Management Committees will be to push through its strategic plans 
and targets globally, to be able to react to market changes quickly, and provide a forum for communication across all locations. These committees should also maintain, and develop further, any synergies between the Gas and Power Business and other UBS businesses.

Proposed Committee Members:

UBSW Energy 
Louise Kitchen (co-chair) 
Greg Whalley (co-chair) 
Tim Belden 
Chris Calger 
John Lavorato 
Kevin Presto 
Hunter Shively 
Rob Milnthorp 
Plus ad hoc members of the Logistical support functions as and when required.

Proposed Logistics:

- This committee will meet on a weekly basis but not before March 2002.

- Prior to March 2002, this committee will be replaced by two sub-committees - the Operational Re-start Sub-Committee and the Commercial Re-start Sub-Committee.

3(i) Operational Restart Sub-Committee 
This subcommittee will be responsible for ensuring that the support functionality is full available at 
the restart date.

Proposed Sub-Committee Members:

Management				Pat O’Donnell (co-chair)

Louise Kitchen (co-chair)

Operations				Sally Beck

Legal					Mark Haedicke 
Financial Operations			Wes Colwell 
Credit					Bill Bradford 
Market Risk 				David Port 
IT					Jay Webb 
Infrastructure				Jenny Rub 
Canada					Peter Keohane 
Program Management			David Forster

Proposed Logistics: 
 This sub-committee will meet weekly until disbanded. 
 Time Tuesday 8:00am CST  (starting Feb 5, 2002)

3(ii) Commercial Re-start Sub-Committee

This subcommittee will be responsible for ensuring that the UBS Warburg Energy Counterparties are capable of transacting with our new company in the shortest time possible and in the most efficient way for both the counterparty and UBS Warburg Energy.

Proposed Sub-Committee Members:

Management:			Louise Kitchen 
Legal                           		Bryan Murtaugh (UBSW)

Mark Taylor

Elizabeth Sager/Leslie Hansen

Mary Cook/Jeff Hodge

Credit                          		Bill Glass (UBSW)

Bill Bradford

Canada				Peter Keohane 
Commercial			Barry Tycholiz

Frank Vickers 
Laura Luce 
Rob Milnthorp 
Chris Calger

Program Management		David Forster 
Other members to be announced

Proposed Logistics:

- This sub-committee will meet weekly until disbanded.

- Time Tuesday 10:00am CST commencing February 5th 2002