UPDATE - OASIS/BEEP SPLIT/SC SPECIFIC PMI

INFORMATION& TIME-LINE OF EVENTS

##### REVISED INSTALLATION DATE: 05/23/01	 TIME:  19:00PST to 22:00PST

Conference Bridge Number**:	1-888-837-2407	Passcode: 362256

**The conference bridge will be activated for all SCs to utilize during the Installation

UNSTRUCTURED TESTING (round 2)  DATE: 05/22/01  TIME: 10:00PST to 15:00PST

Please be advised that we will hold unstructured testing on the following system:  https://alhidev33/iso in response to requests made by several SCs.  We will use the same passwords as round 1 of unstructured testing.  Please contact Jim Blatchford at (916) 608-7051 if you did not participate in round 1 for passwords to the test system.   You will use the same Logon Ids as production SI.

TIMELINE OF EVENTS PRIOR TO AND DURING IMPLEMENTATION

| DATE | Time | Task |
| --- | --- | --- |
| 5/17/01 DONE | By the End of the Day | Issue notice to SCs about implementation. |
| 5/18/01 DONE | 10:00 | Conference call - Review Implementation Plan - Address questions/concerns regarding the Plan - Review Contact information - Review Information regarding unstructured testing - Review Screen Prints |
| 5/22/01 | 11:00-14:00 | Unstructured Testing held on https://alhidev33/iso Submit Day Ahead and Hour Ahead schedules in Unstructured environment – will not be running markets and producing final information and PMI unless otherwise agreed to. |
| 5/23/01 | 09:00 | HA Operator - Issue Reminder notice to Market Status e-mail list and through SI Messaging system about early submission of Hour Ahead and Supplemental Energy Schedules to account for system down time . |
|  | 14:00 | Publish DA Finals in current format. Implementation team to convert DA Default Hour Ahead schedules to beep-split format for use beginning Operating Hour Ending (HE) 1:00 Trade day 5/24/01. |
|  | Prior to 19:00 | - SCs to submit their Hour Ahead schedules for HE 23&24 for trade date 05/23/01 before 19:00PST - SCs to submit their Supplemental Energy schedules for hours 21-24 trade date 05/23/01 before 19:00PST - Download All SC Specific History (Workspace, Schedules, and Usages) as all history will be removed as a result of the new implementation. |
| 5/23/01 | 19:00- 19:45 | - Run HE 22 Normal and Pre-run HA markets for HE hours 23&24 (05/21/01) transfer data to SI database and Publish. - Notify SCs on the conference bridge as each hour’s hour-ahead finals and PMI are available to download (HE22-HE24). |
|  | 19:45-20:00 | Allow for all SCs on bridge to verify downloads complete (with a maximum wait time of 15 minutes) Remember Public PMI is still accessible from www.caiso.com OASIS site |
|  | 20:00 | SI Down - All DA and HA Ancillary Spin and Non-Spin schedules for trade date 5/24/01 will be converted by ISO to the new format with the Contingency Flag set to default status, "No". New Software Installed to systems and configured (excluding contingency only units). |
|  | 22:15-22:30 | SI Up- SCs to submit any changes for HE 1 within 15mins. Close HE1 with new software and publish as normal. |