Stage 2 - March 1, 2001 Filing

Key Dates and Milestones

12/14 (F)	   Distribute initial drafts of

Congestion Management

Pricing and Losses

Planning

Market Monitoring

Facilities Inclusion

12/19 (W)	   Initial Stakeholder Meeting to clarify the drafts distributed on 12/14

1/8 (T)		   Written comments due on drafts distributed on 12/14

1/10 (Th)

1/15 (T)	   Distribute initial drafts of

Paying Agent Agreement

Credit Appendix

Scheduling Coordinator Agreement

1/21 (M)	   Distribute initial drafts of

Filing letter

Ancillary Services

TOA

Bylaws

Interregional Coordination (Canadian Participation)

GIA, LIA, and/or Billing and Settlements Section as appropriate

1/24  (Th)	    Second Stakeholder Meeting to clarify the drafts distributed on 1/15 & 21

1/29 (T)	Written comments due on drafts distributed on 1/15 and 1/21; modifications     to 1/8 comments on 12/14 materials also welcomed

2/4 (M)	     Full Filing Draft distributed

2/6&7 (W&Th)    RTO RRG Days

2/15 (F)	     Final written comments due on full filing package

3/1 (F)		     File with FERC