April _____, 2000

Mr. Robert M. Kinert

Corporate Account Manager

Account Services

Pacific Gas and Electric Company

123 Mission Street, Room 2657

San Francisco, CA 94177

Re: Interconnection Costs for CSU Fresno Substation Project

Dear Bob:

The purpose of this letter is to inform you of our dissatisfaction with the conduct of Pacific Gas and Electric Company (PG&E) regarding the proposed project at the Herndon/Bullard substation near the California State University, Fresno (Fresno State) campus.  It is the opinion of both ourselves as well as Fresno State that PG&E has not supported this project in good faith and has intentionally failed to cooperate with Enron and Fresno State in order to prevent this project from being successfully completed.  The chronology outlined in this letter demonstrates that PG&E’s failure to cooperate and its skyrocketing cost estimates appear intended to deny Fresno State an opportunity to position itself better in the deregulated energy market, to gain an asset, and to reduce its operating costs.

To begin with, on August 6, 1998, Fresno State received an unsolicited proposal from PG&E to install certain electrical equipment and make modifications to the Herndon/Bullard Substation in Fresno as well as the distribution system serving

the Fresno State main switchboard.  PG&E proposed that after the completion of this project, PG&E would be able to upgrade Fresno State’s main account from PG&E’s E-20P rate to the E-20T rate, which is a lower-cost rate.  PG&E proposed to perform the modifications and installations under its Electric Rule 2, Special Facilities.  PG&E’s proposal included a charge of $1,105,000 +/-20% for substation modifications and other transmission components, and $585,000 +/-50% for a dedicated “express” distribution line from the substation to the Fresno State campus, for a total potential high-side cost of approximately $2.2MM [prior to ITCC or cost of ownership charges].  PG&E’s proposal was based on the premise that Fresno State would not incur any up-front costs, but rather would be charged monthly in perpetuity in an amount of approximately $22,500 ($8.1MM over thirty years).

In the meantime, Enron Energy Services (Enron) had in February 1998 signed a comprehensive energy services agreement with both the California State University system as well as the University of California.  As the contracted energy service provider, Enron offered and was invited by Fresno State to analyze the financial implications of PG&E’s original proposal.  During this analysis phase, Enron offered to submit a parallel proposal to design, finance, and build similar facilities to enable Fresno State to qualify for the E-20T rate.  Fresno State indicated a strong interest in receiving an alternative proposal.  Enron confirmed its intent to proceed with a proposal in a letter to Fresno State dated November 19, 1998. The letter included a financial analysis of PG&E’s August 6, 1998 proposal.

As such, on January 6, 1999, Fresno State issued RFP ZS99-012889, inviting bidders to design and build the pertinent facilities to qualify for PG&E’s E-20T rate.  PG&E was also invited to formally bid on the project.  Enron realized early on that significant interconnection issues would need to be addressed and resolved with PG&E in order to

provide a meaningful response to the RFP.  This turn of events resulted in PG&E being in the unique position of competing with Enron for the RFP while at the same time Enron was entirely dependent on PG&E in order to submit a meaningful RFP

response.  Nevertheless, on January 14, 1999, Enron requested that PG&E submit cost estimates for the following facility enhancements:

(a)	Cost of potentially available surplus PG&E property adjacent to the Herndon/Bullard Substation for the purposes of constructing a Fresno State-owned transmission substation.

(b)	Interconnection with PG&E’s transmission grid .

(c)	Cost of building a dedicated distribution “Express” line from the proposed Fresno State-owned substation to the existing main service point, similar to the PG&E’s original August 6, 1998 proposal.

On January 25, 1999, PG&E notified Enron that it could not complete Enron’s request for the cost information.

On January 27, 1999, Enron informed Fresno State of PG&E’s conduct and requested that the RFP due date be postponed to allow Fresno State an opportunity to meet with all prospective bidders.  That meeting did not happen, but Fresno State issued Amendment No. 2 with a new RFP response date of February 16, 1999.  PG&E continued to stonewall Enron by refusing to provide cost information to Enron, and Enron had no option but to request another postponement, which Fresno State issued as Amendment No. 3 on February 11, 1999, with a revised due date of March 8, 1999.

During the intervening six weeks, PG&E informed Enron that it would not allow Enron to bid into the RFP and construct the same project that PG&E itself had proposed in August 6, 2000.  PG&E’s stated reason was that it “is not willing to, nor required to, own, operate and maintain facilities islanded between two customer-owned facilities” ; that is, while PG&E’s August 6, 1998 proposal involved PG&E-owned facilities connected to Fresno State via a PG&E-owned “express” distribution line, PG&E would not allow Fresno State-owned facilities (constructed by Enron) to be connected to Fresno State via the same PG&E-owned “express” line.  To this date PG&E has not provided either Enron or Fresno State with a technical justification for this distinction other than a reference in PG&E’s January 25, 1999 letter to a conversation between PG&E and Fresno State.

Again, Enron had no option but to request Fresno State to consider an alternative interconnection option that would not “island” Fresno State, and Fresno State

agreed as it also recognized that PG&E had effectively stifled any chance for a true “apples-to-apples” RFP.  However, Enron’s alternative design would still require active PG&E participation in developing interconnection cost estimates, as would every other conceivable interconnection scheme.  Therefore, on February 17, 1999 Enron submitted a request addressed to DeAnn Hapner, PG&E’s Vice President of Regulatory Relations in an effort to place proper emphasis on the importance of a timely and substantive response.  Ms. Hapner subsequently delegated the responsibility to respond for PG&E to you.  Finally, on February 24, 1999 Enron received PG&E’s formal response to

the original January 14th information request in the form of a “rough cost” Informational Review.

In the Informational Review, PG&E offered (a) two interconnection options, a line tap for approximately $178,000, a bus tap for approximately $500,000, (b) a cost for constructing the overhead 115kV transmission line of approximately $150,000, and (c) an undergrounding option for its pertinent distribution facilities (approximately $500,000).  In addition, PG&E quoted an ITCC and cost of ownership markup of approximately 75%.

Enron relied heavily on PG&E’s Informational Review in order to arrive at interconnection costs for Enron’s response to Fresno State’s RFP as there were no alternatives to using PG&E for the interconnection scope of work.  In order to minimize costs to Fresno State for this project, Enron proposed to build a new transmission substation on Fresno State property, and build an overhead distribution line from that substation to Fresno State’s main service point.  PG&E would construct and own the substation interconnection and transmission line between the Herndon/Bullard Substation to PG&E.  The proposal included a firm Enron cost for the design/build portion.

Enron’s interconnection cost proposal included $178,000 for the bus tap and $150,000 for the overhead 115kV transmission line.  Because PG&E’s Informational Review numbers were a “rough cost”, Enron added an extremely generous contingency factor of almost 90%, then added PG&E’s markup of 75%, for a total interconnection price of approximately $1.07MM.

Enron was notified in June 1999 that Fresno State had awarded the project to Enron, and Enron and Fresno State executed a definitive agreement for Enron’s proposed project on October 6, 1999.  On November 15, 1999, Enron met with PG&E at Fresno State to further refine the interconnection requirements and to set scope and budget.  At this meeting, at Enron’s and Fresno State’s urging, PG&E promised to provide a detailed cost estimate by December 15, 1999.  On December 20, 1999 [did we contact PG&E between 12/15 and 12/20?] PG&E inexplicably informed Enron that more time was needed to prepare the cost estimate due to “personnel vacations and holidays”.  Reluctantly, Enron agreed to a new date promised by PG&E, January 6, 2000, by which PG&E would submit a formal Detailed Study.  However, it was not until January 12, 2000 that both CSU Fresno and Enron received the Detailed Transmission Interconnection Study.

Enron  and PG&E met on about January 17, 2000 at the PG&E Learning Center to review the PG&E’s Detailed Transmission Interconnection Study.   Enron  was stunned at PG&E’s “revised” cost estimates.  Instead of the $178,000 originally estimated for

the line tap, PG&E informed Enron and Fresno State for the very first time  that a line tap was “no longer an option” due to “other transmission activities” being planned by PG&E.  PG&E would only install a bus tap at a cost of $832,803, a 467% cost increase.  The original $150,000 cost estimate for the 115kV transmission line scope of work had skyrocketed to $539,803, a 359% cost increase.  Furthermore, PG&E for the first time informed Enron and Fresno State that it was also including an additional $227,525 for “Engineering, Project Management, and Others, $40,395 for “Removal/Relocation”, and $60,454 for “Land Projects”.  And to top everything off, PG&E informed Enron and Fresno State that it had “misquoted” the original markup rate of 75%, and that the new rate was actually 95.6%.  As such, the original project cost had ballooned from $1.07MM (including Enron’s 90% contingency factor) to more than $3.26MM.

Enron attempted to ascertain from PG&E why the interconnection costs had escalated so dramatically, but PG&E could not provide a firm answer.  For example, Enron specifically asked PG&E how the $40,395 “Removal/Relocation” amount had been determined, and PG&E said [Rob?].  Enron asked about the other line items and received similar answers.  Enron asked if any of the estimated amounts would be refunded if PG&E did not in fact incur such costs, and was told that PG&E would retain any unearned amounts.  Enron pointed out that the increased interconnection cost would render the Fresno State project infeasible from an economic standpoint, and Enron requested that PG&E review the submitted costs and provide a more detailed breakdown.  PG&E provided the breakdown on January 24, 2000, and reiterated that the submitted cost figures were their best and lowest cost estimate.

Enron then proceeded with obtaining project cost quotations from several third-party contractors who have experience working with PG&E on similar construction projects.  Enron compared the contractor cost quotations on a line-by-line basis with PG&E’s figures and found significant cost differences.  On March 7, 2000, PG&E. Fresno State, and Enron met in San Ramon to discuss the cost difference issues.  Despite the firm third-party cost quotations, PG&E reiterated that their cost estimates were driven down as far as possible and that no further review on their part was warranted.  After much debate, PG&E agreed to have the individuals responsible for providing the cost quotations meet with Enron.  This meeting was held on March 29, 2000.

As you can see from the above chronology, PG&E has repeatedly engaged in a pattern of conduct to delay the Fresno substation project and to derail the project by providing unrealistic and cost-prohibitive pricing.  This conduct has severely jeopardized the project’s viability.  As such, we hereby request that PG&E allow us to review its cost estimating practices and explain the rationale behind its most recent cost quotations.

We are looking forward to discussing the interconnection cost with the proper authority within the PG&E organization. Please call me at your earliest convenience to schedule a meeting at your head office in San Francisco.

I may be reached at (925) 543-3879.

Sincerely,

Enron Energy Services, North America

Dirk A. van Ulden

Director, Account and Facility Management

San Ramon District

cc:	Dick Smith/Fresno State

Bob Boyd/Fresno State

Douglas Huth/Enron

Richard Crevelt/Enron

Jeff Dasovich/Enron Corp

Thomas Riley/Enron

Andrew Wu/Enron