Napoleonville Land Sale Closing Timeline

Monday, November 5

- initial feedback from TB legal team on draft sale document

Friday, November 9

- second draft of land sale document submitted to TB

- this draft will address easements that were unresolved from March ’01 sale as well as new easements from Tract 4a to Tract 5a via 50-foot strip

- TB obtains current land survey to their satisfaction (last survey completed 4/00)

Wednesday, November 14

- phase 1 environmental assessment completed

- (IF NECESSARY) Enron to provide TB with requested:

  - Licenses, leases, tax bills, records, title documents, certificates

  - Similar contracts, warranties, guaranties

  - All other agreements, documents, letters or notices in Enron’s possession concerning the property

Friday, November 16

- Title search completed by TB

- Final document drafted, approved by all parties

Monday, November 19

- Account, wire transfer information conveyed, ENA accounting and bookkeeping (?) groups notified

Wednesday, November 21

- Final land sale document signed, transfer of cash by end of business day