EPE-Empresa Produtora de Energia Ltda.

Rodovia Dos Imigrantes, No. 3770

Distrito Industrial

Cuiaba MT	CEP: 78098-840

January [___], 2001

Siemens Aktiengesellschaft

Power Generation (KWU)

P.O. Box 3220

Department F2K

D-91050 Erlangen, Germany

Siemens Ltda.

Av. Mutinga No. 3.800

Sao Paulo – SP

05110-901

Brazil

Re:	Technology Assurance Agreement, dated effective September 5, 1997 (the “TAA”), among EPE-Empresa Produtora de Energia, Ltda. (“Owner”) and Siemens Aktiengesellschaft (“Contractor”).  Capitalized terms used herein but not otherwise defined herein shall have the respective meanings assigned to such terms in the TAA.

Gentlemen:

The following sets forth the agreement of Owner and Contractor solely with respect to certain amendments to the TAA.

To carry out the intent of the parties and in consideration of the mutual promises set forth herein and in the TAA and for other good and valuable consideration, Owner and Contractor hereby agree, to the extent set forth herein, to amend, modify, and supplement the TAA as follows:

- Commencement/End of Initial Guarantee Period.

Contractor and Owner agree that (i) the Initial Guarantee Period shall commence on the date that is twelve (12) months prior to the date on which Phase III of the Facility achieves Provisional Completion, and (ii) subject to Section 2 hereof, the Initial Guarantee Period shall end on the first anniversary of the date on which Phase III of the Facility achieves Provisional Completion.

- Tolling of Initial Guarantee Period/Extended Guarantee Period.

Contractor and Owner agree that the Initial Guarantee Period or the Extended Guarantee Period, as the case may be, shall be tolled during the period commencing on the date that Contractor commences commissioning the Facility using natural gas and ending on the date that Phase III of the Facility achieves Substantial Completion.

- Liquidated Damages.

On or before [____________, 2001], Contractor shall pay to Owner the sum of [Five Million Three Hundred Fifty-seven Five Hundred Dollars ($5,357,500)] in satisfaction of its obligation to pay liquidate damages under Section 2.02 of the TAA for the period commencing on the date that is twelve (12) months prior to the date on which Phase III of the Facility achieves Provisional Completion and ending on the date of this Agreement.

# General.

- Any disputes arising under or in connection with this letter agreement shall be resolved in accordance with the provisions of Section 6.08 of the TAA.

- This letter agreement shall be governed by, and construed in accordance with, the laws of the State of New York.

- This letter agreement may be executed in one or more counterparts each of which shall be deemed an original and all of which shall be deemed one and the same agreement.

- This letter agreement, the TAA, and each other agreement delivered pursuant thereto or in connection therewith that is executed by each party contain the entire understanding of the parties with respect to the subject matter hereof and reflect the prior agreements and commitments of the parties with respect thereto.

- Section headings used in this letter agreement are for reference purposes only.

- The agreements, waivers, amendments, and representations set forth in this letter agreement are expressly limited to their terms and do not purport to amend, supplement, or otherwise modify the TAA (except to the extent set forth herein).

If the foregoing represents your understanding of the agreement between Owner and Contractor, please sign and date the enclosed copy in the spaces provided below, and return to the undersigned.

Very truly yours,

EPE-EMPRESA PRODUTOR DE ENERGIA LTDA.

By:______________________________

Title:_____________________________

ACKNOWLEDGED AND AGREED:

SIEMENS AKTIENGESELLSCHAFT

By:______________________________

Name:____________________________

Title:_____________________________

Date:_____________________________