April 15, 2001

GREENFIELD SHIPPING COMPANY LIMITED
c/o Mitsui O.S.K. Lines, Ltd.
2-1-1 Toranomon, Minatu-ko

Tokyo, Japan 105-8688

Attention: Managing Director, Liquefied Gas Carrier Division

By Telefax: +81 3 3587 7748

Dear Iwata San,

TIME CHARTER PARTY DATED JANUARY 18, 1999 BETWEEN DABHOL POWER COMPANY (DPC) AND GREENFIELD SHIPPING COMPANY LIMITED

In accordance with our obligations under the above Time Charter Party, we notify you of the following:

- Delivery of Ship

Per Clause 6(a)(iii) of the Time Charter Party, DPC has chosen to reduce the existing 1-month Delivery Window and fix the Scheduled Delivery Date as November 15, 2001.

2)	Potential Force Majeure Event

We refer to the telephone conversation our Mr. Wayne Perry had with you earlier in the week in which we informed you of the incident that took place at the LNG Facility being constructed at Dabhol on the morning of April 9, 2001.

The purpose of this communication is to give you notice of the incident as is required under Clause 27(b)(ii) of the Time Charter Party. We have already communicated the incident to you promptly and using the quickest possible means and now confirm the information in writing. We believe that the incident is a Project Force Majeure event and is likely to affect DPC’s ability to perform under the Time Charter Party.

The incident occurred during the pneumatic testing of the two 32-inch LNG lines from the LNG Jetty to the storage tanks. There was a failure during the pneumatic test on the morning of April 9, 2001 in which there was extensive impact on the lines, and the pipework supports and plinths have been damaged for a length of approximately 240 metres.  Internal inspection of the pipelines from the point of failure to the shore is underway. We expect some impact on the schedule, which could be in the order of 3-months. A full Root Cause Analysis of the failure is underway and the Contractor is taking steps to mitigate the impact on schedule.

We shall promptly from time to time furnish to you such relevant information as is available to us appertaining to the above incident and shall furnish you with updated estimates of the impact on schedule of the LNG Facility.

3)	Sub-charter

As a risk mitigation measure we also acknowledge that we are looking at a sub-charter proposal with Enron, which if formalised would bring up an earlier delivery of the ship. We look forward to discussing this proposal in the near future with both Greenfield and the parties concerned.

If you have any questions or comments concerning this notification, please do not hesitate to contact us.

Yours faithfully,

For Dabhol Power Company

Neil McGregor

President & CEO