August 1, 2000

Richard Williams

Barclays Bank

# Re:  Lost Creek Financing – Conversion

[Summary Update on the construction of the project – Audrey to write up]

## 1.  Extension of Date Certain

Under Section 3.05 of the Construction and Term Credit Agreement (Credit Agreement), we are allowed to extend the Date Certain to December 31, 2001.  We are required to notify the Banks of the extension prior to August 31, 2000.  The formal extension letter is attached.

Although the extension allows us to have the Conversion Date occur as late as December 31, 2001 – we are targeting a Conversion Date of September 10, 2000.

2.  Amendment to the Gas Gathering Agreement (1)

Under the previously amended Firm Gathering Agreements, the Shippers were to begin paying the Fixed Gathering Fee on July 1, 2000.  Since the construction of the pipeline has been delayed, Lost Creek Gathering Company, L.L.C. and the Shippers have agreed to delay the start of these Fixed Gathering Fees to October 1, 2000.  The Firm Gathering Agreements have been amended to reflect the October 1, 2000 start date.  Accordingly, the end date of the Firm Gathering Agreements has been simultaneously moved back one quarter and now ends on September 30, 2010.  The Members of Lost Creek have agreed to bear any Operation and Maintenance costs incurred prior to October 1, 2000 in accordance with their respective membership interest.

3.  Amendment to the Administration Services Agreement (2)

Initially, the compression on the pipeline was scheduled to be gas compressors.  Fuel for the gas compression would be retained at a minimum rate of 1% in-kind from the Shippers.

Since then it has been found that electric compression is more efficient and economic.  Therefore, Lost Creek has installed electric compressors and has made arrangements for the operation of the electric compressors.  The Shippers will continue to pay for the compression services by retainage of 1% of the gas being transported under the Firm Gathering Agreements.  The revenues from the sale of the retained fuel gas more than covers the cost of the electric power for the electric compressors.

## 4.  Revision to the Amortization Schedule

The amortization schedule attached to the Credit Agreement was for 40 quarterly payments with the first payment starting Sept 30, 2000.  Since (1) the Conversion Date is going to be delayed and (2) the Gas Gathering Agreement has been pushed back one-quarter (i.e. starting Oct 1, 2000 through Sept 30, 2010), we request that we keep the same 40 quarterly installments as listed in the Credit Agreement but have the first principal payment start in December 31, 2000 and the last principal payment be on September 30, 2010 contemporaneous with the term of the Gas Gathering Agreements.  The revised Amortization Schedule is attached as Attachment A as required under Section 3.05 of the Credit Agreement.

## 5.  Updated Base Case Cash Flows

The Base Case Model has been updated for the new start dates and revised amortization schedule.  We meet the debt service coverage test required for Conversion.  We are also required to hedge 75% of the term loan.  In the base case, we have assumed that the company has swapped the required loan amount for a 7.20% rate.  The swap will be entered into closer to the Conversion Date.  The Base Case Cash Flows is attached as Attachment B.

## 6.  Legal Documents associated with Conversion

Our lawyers have prepared the documents required for the conversion.  We shall be sending them over to you for your approval.  We would like to have the documents finalized by  August 31, 2000.

If you have any questions, please call me at 713-853-5274 or Dean Henry at 713-624-9836.

Sincerely,

[ ]

Lost Creek Gathering Company

cc:  [ ], Stone and Webster