# MARKETING AND COMMUNICATIONS PLAN FOR OLER

# GOAL:	To make employees aware of services and to be seen as a neutral third party resource available to resolve

# employee conflicts and or disputes.

## Suggested Course of Action:

- Decide upon and develop key messaging points for audience

- Decide on name of group

- Decide what employee services you want to highlight, and catalog those services

- Develop look and feel that is unique to OLER, yet still falls within the Enron  branding guidelines

- Establish presence on Enron Intranet

- Review current literature and make certain that it is appropriate for audience, if not develop literature for target audience

- Push service through internal marketing channels

- Because Enron is such a large company and things change so quickly, some type of re-marketing needs to be done every three months.

| ACTION ITEM | PERSON RESPONISBLE | DUE DATE | STATUS |
| --- | --- | --- | --- |
| Decide on messaging points | Michelle Cash, Valeria Hope—I will work with you on this. We need 3 key thoughts that will create one overall message. From this we can come up with a tag line. | By end of July 2001 |  |
| Decide on Name of Group | Valeria to meet with Karen Denne to discuss and should be determined by next week | August 2, 2001 |  |
| With messaging and name decided upon, work with Mark Wilson to develop several looks and feels that will be a unique identifier for the OLER group | Karen Moore, Mark Wilson | August 9, 2001 |  |
| Present four possible looks to Michelle and Valeria for their final decision and approval | Moore and Wilson | August 9, 2001 |  |
| Create content for Intranet; work with web designers to create site; decide where it should be housed | Valeria Hope, Karen Moore and Johnny Hoang | August 16, 2001 |  |
| Create new written materials (if needed) | Content to be provided by OLER; Moore and Wilson on layout and look and feel | August 16, 2001 |  |
| Work with Courtney Votaw to create a series of 3 ETV ads to run during the week of August 19, 2001 | Moore, Votaw, and Bowne | August 16, 2001 |  |
| Schedule an eSpeak with Michelle Cash | Moore to schedule with Palmer | TBD |  |
| Have banner created for infozone kiosk (with new look and feel). Also have a monitor with new website up so that you can show it off to employees and demonstrate navigation if employees are interested | OLER to staff Infozone one day during week of August 19, 2001 | Date TBD will check with Sally Alvarez |  |
| Decide on giveaway that can be handed out at the kiosk that feeds into the overall marketing theme | Moore to work with Valeria | ASAP |  |
| Once theme is decided upon and messaging is clear, speak to Karen Denne about having a short write up in Enron Business | Moore to work with Mary Clark and Karen Denne | TBD |  |
| Make certain that New Hire information is updated if employee literature changes | Valeria | TBD |  |
| Possible phone message from Jeff Skilling encouraging employees to stop by the kiosk | Moore to write script (Cash and Hope approve) and schedule recording date with Joannie | TBD |  |
| Sending out a well-crafted email to employees telling them about the services and encouraging them to visit the kiosk | Moore to write and coordinate (Cash and Hope give final approval) | TBD |  |

Possible ideas for future marketing would include:

--having a booth at a Big E Café.

--every three months running eTV ads.

--possible brown bag lunches where you can explore a specific topic

--possibly working with the Culture Committee on a joint venture