#### Docket No.:  CP99-522-000

Project Name:  Gallup Expansion/Coolers

| Environmental Conditions Order Issuing Certificate dated January 13, 2000 | NNG Response Required (Yes/No) | Director Letter Required (Yes/No) | Date Director Letter/NNG Response |
| --- | --- | --- | --- |
| - Transwestern shall follow the construction procedures and mitigation measures described in its application and supplements and as identified in the environmental assessment, unless modified by this order. Transwestern must: - request modification to these procedures, measures, or conditions in a filing with the Secretary of the commission (Secretary); - justify each modification relative to site-specific conditions; - explain how that modification provides an equal or greater level of environmental protection than the original measure; and - receive approval in writing from the Director of the Office of Pipeline Regulation (OPR) before using that modification. (Responsibility: Earl Chanley, James Moore, Arnold Eisenstein, Mike McCracken) | Yes, where applicable | Yes, where applicable |  |
| - The director of OPR has delegated authority to take whatever steps are necessary to insure the protection of all environmental resources during construction and operation of the project. This authority shall allow: - the modification of conditions of this order; and - the design and implementation of any additional measures deemed necessary (including stop-work authority) to assure continued compliance with the intent of the environmental conditions as well as the avoidance or mitigation of adverse environmental impact resulting from project construction and operation. (Responsibility: Earl Chanley,James Moore, Arnold Eisenstein, Mike McCracken) | No | No | NA |
| - Transwestern shall file a noise survey with the Secretary no later than 60 days after placing the Gallup compressor station in service. If the noise attributable to the operation of this station at full load exceeds an Ldn of 55 dBA at any nearby noise sensitive areas, Transwestern shall install additional noise controls to meet that level within one year of the in-service date. Transwestern shall confirm compliance with the Ldn of 55 dBA requirment by filing a second noise survey with the Secretary no later than 60 days after it installs the additional noise controls. NOTE: Transwestern reported to FERC that it would install the noise mitigation measures recommended by Hoover & Keith in their Noise Survey dated 11/10/99. (Responsibility: Larry Campbell, Earl Chanley) | # Yes –Gallup noise survey due no later than 6/30/00. Extension granted til 8/1/2000 | No | Gallup noise survey filed 7/21/2000 indicating noise level below 55 Ldn at nearest NSAs. |
| ### ORDERING PARAGRAPHS |  |  |  |
| A. A certificate of public convenience and necessity is issued authorizing Transwestern to construct and operate the Gallup compressor station and to install and operate cooling equipment at the LaPlata ”A” and Bloomfield compressor stations, as more fully described in the application and this order. | No | No | NA |
| - Transwestern must comply with Part 157 of the regulations, especially paragraphs (a) The certificate shall be void and without force or effect unless accepted in writing by applicant within 30 days from the issue date of the order issuing such certificate: Provided, however, That when an application for rehearing of such order is filed in accordance with section 19 of the Natural Gas Act, such acceptance shall be filed within 30 days from the issue date of the order of the Commission upon the application for rehearing or within 30 days from the date on which such application may be deemed to have been denied when the Commission has not acted on such application within 30 days after it has been filed: Provided further, That when a petition for review is filed in accordance with the provisions of section 19 of the Natural Gas Act, such acceptance shall be filed within 30 days after final disposition of the judicial review proceedings thus initiated. (RESPONSIBILITY: Susan Scott, Donna Martens) | # Yes | No | Filed 1/14/00 |
| - Applicant must file with the Commission, in writing and under oath, until October 31, 1989, an original and four conformed copies, and thereafter as prescribed in Sec. 385.2011 of this chapter and, upon request must furnish an intervener with a single copy, of the following: (1) Within ten days after the bona fide beginning of construction, notice of the date of such beginning; (RESPONSIBILITY: Earl Chanley, James Moore, Arnold Eisenstein, Mike McCracken) | # Yes | No | Gallup: 1/17/00 beg of const filed on 1/21/00 Bloomfield: 2/22/00 beg of const filed on 2/24/00 LaPlata: 2/28/2000 beg of const filed on 2/29/2000 |

| (2) Within ten days after authorized facilities have been constructed and within 10 days after such facilities have been placed in service or any authorized operation, sale, or service, has commenced, notice of the date of such completion, placement and commencement, and (RESPONSIBILITY: Earl Chanley,James Moore, Arnold Eisenstein, Mike McCracken) |  | # Yes | No |  |  | Bloomfield 4/6/2000 in-service filed on 4/10/2000. Completion of construction effective 5/1/2000 filed on 5/5/00. ---------- LaPlata 4/20/2000 in-service filed 4/24/2000. Completion of construction effective 5/8/2000 filed on 5/10/2000. ----------- Gallup 5/1/2000 in-service and completion of construction filed on 5/5/2000. |
| --- | --- | --- | --- | --- | --- | --- |
| (3) Within six months after authorized facilities have been constructed, a statement showing, on the basis of all costs incurred to that date and estimated to be incurred for final completion of the project, the cost of constructing authorized facilities, such total costs to be classified according to the estimates submitted in the certificate proceeding and compared therewith and any significant differences explained. (RESPONSIBILITY: Earl Chanley, James Moore, Arnold Eisenstein, Mike McCracken) |  | ## Yes Bloomfield due 10/6/2000 LaPlata due 10/20/2000 Gallup due 11/1/2000 11/29/2000 filed request for waiver of 6 month requirement and extension of time. | No |  |  | NA |
| e. The certificated issued to applicant is not transferable in any manner and shall be effective only so long as applicant continues the operations authorized by the order issuing such certificate and in accordance with the provisions of the Natural Gas Act, as well as applicable rules, regulations, and orders of the Commission (RESPONSIBILITY: All) |  | No |  | No | NA |  |
| (f) In the interest of safety and reliability of service, facilities authorized by the certificate shall not be operated at pressures exceeding the maximum operating pressure set forth in Exhibit G-II to the application as it may be amended prior to issuance of the certificate. In the event the applicant thereafter wishes to change such maximum operating pressure it shall file an appropriate petition for amendment of the certificate. Such petition shall include the reasons for the proposed change. Nothing contained herein authorizes a natural gas company to operate any facility at a pressure above the maximum prescribed by state law, if such law requires a lower pressure than authorized hereby. (RESPONSIBILITY: Earl Chanley, Arnold Eisenstein) |  | No |  | No | NA |  |
| - The facilities must be constructed and made available for service within one year from the date this order is issued, pursuant to paragraph (b) of section 157.20 of the regulations. (RESPONSIBILITY: Earl Chanley, James Moore, Arnold Eisenstein, Mike McCracken) | No |  |  | No | NA |  |
| (D) Transwestern shall be permitted to charge its proposed discounted Part 284 Rate Schedule FTS-1 transportation rates as initial rates, subject to Transwestern’s filing these rates with the Commission with 15 days of the date of this order as required by section 157.14(a)(11)(v) of the regulations. (RESPONSIBILITY: Lorraine Lindberg, Susan Scott, Donna Martens) | ## Yes |  |  | No | 1/18/00 –filed Motion for Extension of Time 2/14/00 –filed request for rehearing Order granting rehearing issued 3/8/2000 |  |

| (E) Transwestern shall restructure its relationship with Enron Company so that Transwestern will have sufficient operation control over the motor at the Gallup compressor station to assume regulatory responsibility for the motor’s operation. Within 30 days from the date of this order, Transwestern shall file a report with the Commission stating how it complied with this condition. (RESPONSIBILITY: Susan Scott) | Yes | No | Filed 2/14/00 |
| --- | --- | --- | --- |
| (F) Transwestern shall notify the Commission’s environmental staff by telephone and/or facsimile of any environmental noncompliance identified by other Federal, state, or local agencies on the same day that such agency notifies Transwestern. Transwestern shall file written confirmation of such notification with the Secretary of the Commission within 24 hours. (RESPONSIBILITY: Larry Campbell, Butch Russell, Earl Chanley, James Moore) | Yes, when applicable | No | NA |