Midwest ISO Commercial Operations Plan

Proposed November 19, 2001 Draft

Assumptions

- MISO will produce AFC Calculations starting on Nov 27th

- All Customer registrations completed no later than December 10, 2001

- Creation of more detailed implementation steps based on the below items by a task force (yet to be formulated)

November 27, 2001

- Operation of OASIS and Scheduling

  - Complete demonstration prior to Dec 7

  - Run OASIS and scheduling in parallel with TO systems

  - Complete OASIS data  needed for January 1 service.

  - Required use of the schedule system starting Dec 1st (required participation of all TO’s in Testing)

December 15, 2001

- Security Coordination

  - Implement pending Dec 4 test results reviewed by TOCG (Transmission Owners Certification Group)

  - Continuation of redispatch congestion management and load curtailment practices that exist today

  - TLR authority as of December 15 rests with MISO

  - Coordinate with

  - all existing Security Coordinators and/or ARTO.

- Maintenance Coordination

  - Phase-in of MISO processing of maintenance requests.

  - MISO will not  pay anyone for movement of a maintenance request in December.

  - MISO will submit process documentation and demonstrate system for TOCG on December 4.

- Long Term Planning

  - Conduct impact studies for requests more than 1 month out

  - Run studies in conjunction with applicable TO’s

  - Start gathering of information and committee startup

  - MISO coordinates with TO long term planning activities

- Market Monitor

  - Market Monitor begins monitoring activities

- Dispute Resolution

  - Completion of documentation for real time dispute resolutions by Dec 4th

- Operations Planning

- Generation Interconnection Agreement

  - Phase-in of GI process as filed and FERC approved

- Scheduling

  - Continuation of current parallel operations (electronic coordination)

  - MISO to announce a date of when they will take a live schedule starting after Jan 1st

  - MISO and all TO’s will post all schedules in parallel until January 1.

  - MISO will schedule a demonstration date

January 1, 2002

- Tariff Administration (Point-to-Point Service only)(MISO suggestion:  Could include existing NITS)

  - Pending acceptable AFC calculations, waive the ‘no later than’ language for granting monthly firm load service

- Settlements and Billing

  - Begin point-to-point services billing excluding schedule 4 on January 1, 2002

  - MISO collects the FERC approved cost adder (schedule 10) beginning January 1, 2002

- Congestion Management

  - Need to know the outcome of FERC decision on December 19th.

  - MISO suggestion:  Use existing practices and phase-in MISO CM.

- Ancillary Services (MISO provide all but Schedule 4)

  - New Schedule 4 Policy definition completed by January 30, 2002

  - New Schedule 4 Implementation of policy by March 30, 2002

  - Use existing TO Schedule 4s until implementation of new Schedule 4

# February 1, 2002

- Network Service begins under MISO tariff

- Full implementation of Settlements (all schedules, except schedule 4)

- MISO suggestion: Full Implementation of MISO Congestion Management process.