| ACTION | RESPONSIBILITY | DUE DATE | STATUS | ISSUES |
| --- | --- | --- | --- | --- |
| # Press Release | Palmer, Team | Aug. 8 | Draft | Needs IR input; buy side review |
| # Q & A Documents - Deal/external - Employee/internal - Customer/partner | Denne, Ambler Ambler, Gilchrist Buyer Commercial | Aug. 8 Aug. 8 Aug. 8 | Not drafted Draft Not drafted | 8-K, Board presentation will help; P & S Agreement needs more answers; ID more questions |
| # Contact Lists/Protocol/Timing - Media - Gov’t Officials/Partners - U.S./Europe - CALME - ESA - EI - APACHI | Corp./In-country Shapiro Shapiro/Schroeder McClelland/Haug Bestard/Bannatine Wilson/Cline Merrill/McDonald | Announce date Aug. 4 Aug. 4 Aug. 4 Aug. 4 Aug. 4 | Done Open Open Open Open Open Open | Need to coordinate timing Separate Government Regulator from Commercial |
| # Employee Communication - Email - Voice mail - Video script/production - e-Speak | Gilchrist/Clark/Vegas Mary Mary Mary Sarah/Erin Rice | Day prior Day prior Day prior Announce date | Open Open Open Open |  |
| # Key Messages | Denne/Kean/Palmer | Aug. 4 | Draft |  |
| # Asset Information/MAPS | Hal Means | Aug. 4 | Done | Re-format |
| # Online Newsroom | Brandon Rigney | Announce date | Open |  |
| Analyst’s Materials | IR | Announce date | Open |  |
| ACTION | RESPONSIBILITY | DUE DATE | STATUS | ISSUES |
| # Message Conference Call | Dick Leibert | Day prior to ann. |  |  |
| # Buyer Identity | Dick Leibert | ASAP | Unknown | Could be major part of story, spokesperson? |
| # Ratings Agencies | Fastow | Immed. prior | Open |  |
| # Translation | Ambler/Vegas | Day prior | Open |  |
| # NGO Notification | Kimberly/Goldblatt | Announce date | Open |  |