| ACTION | RESPONSIBILITY | DUE DATE | STATUS | PROGRESS/ISSUES |
| --- | --- | --- | --- | --- |
| # Press Release | Palmer, Denne* Miceli (buy side edits) | Aug. 16 | Approvals | To Office of Chairman, 1st pass |
| # Q & A Documents - Deal/external - Employee/internal - Customer/partner | Denne/Ambler Ambler/Vegas/Bonnard Buyer Commercial/Miceli | Aug. 16 Aug. 16 Aug. 16 | Approvals Approvals Not drafted | Extensive updates/revisions, to office of chairman for 1st pass |
| # Contact Lists/Protocol/Timing - Media - Gov’t Officials/Partners - U.S./Europe - CALME - ESA - EI - APACHI - In-country media conference call | Corp./In-country # Shapiro Shapiro/Schroeder McClelland/Haug Bestard/Bannatine Wilson/Cline Dahlke&Merrill/McDonald Zaayman/Regional PR | Announce date Aug. 4 Aug. 4 Aug. 4 Aug. 4 Aug. 4 Aug. 14 | Done Open Open Open Open Open Open Underway | Need to coordinate timing Separate Government Regulator from Commercial 90% complete |
| # Key Messages | Denne/Kean/Palmer (Vegas draft) | Aug. 16 | Peer Review | Review & comments underway |

| ACTION | RESPONSIBILITY | DUE DATE | STATUS | ISSUES |
| --- | --- | --- | --- | --- |
| # Employee Communication - Email - Voice mail - Video script/production - Lay – Employee Meeting - Sutton EI Meeting - Enron TV - e-Speak - Corp. Intranet Updates - E Biz & Enron Business - EI bi-weekly e-mail newsletter - EI employee hotline | Bonnard/Clark/Vegas/Ambler Clark/Ambler Clark/Vegas Clark/Vegas Clark/Denne Ambler/Haux/Talan Clark/Vegas Sarah/Rice/Ambler/Talan Clark/Rigney/Talan/Haux Clark/Vegas Ambler/Vegas/Feener Bonnard/Vegas | Day prior Day prior Day prior Announce date Day after Day after + Two days after Ongoing Ongoing Ongoing Day after | Draft Draft Draft Open Open Open Open Open Open Open Open | Ambler to supply 1st draft by 8/10 Vegas to supply 1st draft by 8/10 Vegas to supply 1st draft by 8/14 |
| # Asset Information/MAPS | # Means/Haux | Aug. 10 | Done | Re-format |
| # Online Newsroom | Brandon Rigney/Means | Announce date | Open |  |
| Analyst’s Materials | IR | Announce date | Open |  |
| # Message Conference Call | Dick Leibert | Day prior to ann. |  |  |
| # Media Policy/Brief | Johan Zaayman/Monica Talan | August 14 | Draft | Distributed for PR management review |
|  | RESPONSIBILITY | DUE DATE | STATUS | ISSUES |
| # Ratings Agencies | Fastow | Immed. prior | Open |  |
| # Translation | Ambler/Vegas | Day prior | Open | Spanish, Portuguese, Japanese, Korean and German |
| # NGO Notification | Kimberly/Goldblatt/Miceli | Announce date | Draft | Preparing contact list of NGOs |
| # Stakeholder Letter | # Miceli | August 11 | Draft | Under review, needed for country manager packet |
| # Business Unit Communication Plans | Ambler/Vegas/Miceli/ Zaayman/Means/Haux | August 4 | Done | APACHI, CALME, EGE&P, ESA, India and Wind needed. Updates underway |
| # Media/Stakeholder Tracking | Means/Zaayman | Announce Date | Open |  |
| # Broadcast Addresses (How does it work) | Zaayman/Means | August 8 | Open | Secure contact info. and input lists |
| # Develop V & V Draft for EI | Miceli/Ambler | Week after | Open |  |
| # Buyer Info. Q&As | Leibert/Ambler/Vegas | August 10 | Shift | Incorporate into full Q&As |
| # Multilateral Contacts | John Hardy/Miceli | August 14 | Open | Lists and draft letter |

* Lead contact for communication team in bold