TURNKEY AGREEMENT

for

GENERATION BARGE

MOORING FACILITIES

Rockaway, New York

Between

ENRON ENGINEERING & CONSTRUCTION COMPANY

(Contractor)

And

ENRON NORTH AMERICA CORP.

(Company)

EFFECTIVE DATE: JANUARY 22, 1999

TABLE OF CONTENTS

TURNKEY AGREEMENT

Part I		Turnkey Agreement

Page

1.	Scope of Work	1

2.	Materials	1

3.	In-Service Date	1

4.	Term 	2

5.	Contract Price	2

6.	Notices	2

7.	Tax Identification Number	2

8.	Parts and Exhibits	2

Part II		Turnkey Agreement – General Terms and Conditions

1.	Definitions	1

2.	Time Requirements	3

3.	Schedule, In-Service Date and Final Acceptance	3

4.	Review and Contractor Reporting Requirements	4

5.	Inspection and Responsibilities for the Work	5

6.	Representations and Warranties	6

7.	Governmental Authorization and Contractor Assistance	9

8.	Guarantees	10

9.	Rights Reserved to and Material Furnished by Company	11

10.	Risk of Loss, Passage of Title	11

11.	Correction of Work	11

12.	Extra Work - Changes	12

13.	Use of Completed Portions of the Work	12

14.	Default, Termination, and Suspension	12

15.	Force Majeure	16

16.	Records and Audit	17

17.	General Payment Conditions	18

18.	Taxes and Other Payments	19

19.	Liquidated Damages	20

20.	General Indemnity	20

21.	Patent Indemnity	22

22.	Traffic and Special Loads	23

23.	Insurance	23

24.	Safety Precautions	23

25.	Compliance with Laws and Regulations	24

26.	Environmental Waste	24

27.	Company Policy Regarding Drugs/Alcohol/Weapons	25

28.	Ingress and Egress	25

29.	Public Relations	25

30.	Independent Contractor	25

31.	Protection of Materials, Equipment, and Work	26

32.	Confidentiality	26

33.	Governing Law	27

34.	Controlling Provisions in Case of Conflict	27

35.	Assignment and Subcontracting	27

36.	Proprietary Rights	28

37.	Contractual Rights	28

38.	General	28

39.	Dispute Resolution	29

40.	Limitation of Liability	30

#### Part III	-	Instructions and Information to Bidders

##### Part IV	-	Proposal of Bidder

Exhibit A	-	Scope of Work

Exhibit B	-	Intentionally Omitted

Exhibit C	-	Intentionally Omitted

Exhibit D	-	Contractor's Extra Work Rate Schedule

Exhibit E	-	Minimum Insurance Requirements

Exhibit F	-	Governmental Authorizations

Exhibit G  -	Contractor's Completion Affidavit, General Contractor’s/Engineer’s Partial Lien Waiver and Affidavit of Payment, and General Contractor’s/Engineer’s Final Lien Waiver and Affidavit of Payment

Exhibit H	-	Intentionally Omitted

Exhibit I	-	Intentionally Omitted

Exhibit J	-	Intentionally Omitted

Exhibit K	-	Progress Payment Schedule

PART I

TURNKEY

### CONSTRUCTION AGREEMENT

GENERAL UNDERSTANDINGS AND OBLIGATIONS OF THE PARTIES

This agreement ("Agreement") is made and entered into as of the ____ day of _______, 2000, by and between ENRON NORTH AMERICA CORP., a corporation organized and existing under the Laws of the State of Delaware, with general offices at 1400 Smith Street, Houston, Texas 77002, hereinafter referred to as "Company", and ENRON ENGINEERING & CONSTRUCTION COMPANY, a Texas corporation, with general offices at 1400 Smith Street, Houston, Texas 77002, hereinafter referred to as "Contractor:"

WITNESSETH THAT:

WHEREAS, Company desires the performance by an independent contractor pertaining to the turnkey engineering/design, procurement, construction, installation and commissioning of certain docking facilities for barge mounted electric generation facilities to be located at end of Bay 24th Street, N/O Mott Avenue, Far Rockaway, New York at the southern southwestern corner of Long Island  (the “Work”); and

WHEREAS, Contractor has reviewed and is familiar with the specifications and the site and scope of such Work and has submitted a Proposal to Company to perform such Work in accordance with Company's request.

NOW, THEREFORE, in consideration of the amount(s) of money to be paid by Company to Contractor, and the mutual covenants, agreements and obligations of the parties hereinafter set forth, the parties do hereby agree as follows:

1.	Scope of Work	.  Contractor shall furnish and pay for all labor, supervision, tools, engineering, technical capability, transportation, material(s) and supplies and all other items or accessories necessary for Contractor to perform and accomplish the Scope of Work in the manner defined and described in Exhibit "A" of this Agreement.

2.	Materials	.  Company has an option to furnish those materials shown in Exhibit "C".

3.	In-Service Date	.  Contractor shall commence Work on ____________, 2000, and shall perform the Work at such a rate of progress as necessary to meet the "In-Service Date" of ______________, 2000.

4.	Term	.  This Agreement shall commence on the date of execution ("Effective Date") and shall continue until Final Acceptance of the Work by Company, unless otherwise terminated as provided in Section _____.

5.	Contract Price	  As total consideration for the Work to be performed hereunder, Company shall pay Contractor the Contract Price set forth in Part IV.  However, should Company authorize Contractor to perform Extra Work, which is not within the Scope of Work, such Extra Work shall be reimbursed in accordance with Part II, Section 12 of this Agreement.

6.	Notices	.  All notices, consents, requests, invoices or statements provided for or permitted to be given under this Agreement must be in writing and are effective on actual receipt by the intended recipient or by delivery to the address, or facsimile number during working hours (8:00 a.m. to 5:00 p.m. CST) for the recipient listed below:

TO COMPANY:

NOTICES		INVOICES

Enron North America Corp.

1400 Smith Street

Houston, Texas 77002

Attn:

TO CONTRACTOR:

NOTICES

Enron Engineering & Construction Company

All notices, invoices, and other communications ("Notices") shall be sent to the parties at their respective addresses in writing and as set forth above.  Notices sent through the mail shall be deemed to have been received on the third (3rd) day after mailing.  Notices delivered via hand delivery or facsimile shall be deemed to have been received on the day of delivery.

7.	Tax Identification Number	.  Contractor hereby designates No. ______________ as its tax identification number for all purposes which may require Company to report to taxing authorities moneys paid to Contractor for Work provided hereunder.

8.	Parts and Exhibits.  This Agreement consists of the following Parts and Exhibits, all of which are attached hereto and by this reference made a part hereof:

Part I		-	General Understandings and Obligations of the Parties

Part II	-	General Terms and Conditions

Part III	-	Instructions and Information to Bidders

Part IV	-	Proposal of Bidder

Exhibit A	-	Scope of Work

Exhibit B	-	Intentionally Omitted

Exhibit C	-	Intentionally Omitted

Exhibit D	-	Contractor's Extra Work Rate Schedule

Exhibit E	-	Minimum Insurance Requirements

Exhibit F	-	Governmental Authorizations

Exhibit G	-		Contractor's Completion Affidavit, General Contractor’s/Engineer’s Partial Lien Waiver and Affidavit of Payment, and General Contractor’s/Engineer’s Final Lien Waiver and Affidavit of Payment

Exhibit H	-	Intentionally Omitted

Exhibit I	-	Intentionally Omitted

Exhibit J	-	Intentionally Omitted

Exhibit K	-	Progress Payment Schedule

IN WITNESS WHEREOF, this Agreement is executed on the Day and year first above written, but is effective on the Effective Date.

"COMPANY"					   "CONTRACTOR"

Enron North America Corp.	Enron Engineering &

Construction Company

By:								By:

Name: ___________________________			Name:

Title : ____________________________		Title :

TURNKEY CONSTRUCTION AGREEMENT

PART II

GENERAL TERMS AND CONDITIONS

- Definitions.  All definitions contained in this Paragraph and any other part of this Agreement shall apply throughout this Agreement.

"Actual Cost" shall mean the total actual expenses incurred by Contractor for all items including, but not limited to, materials, labor, transportation, profit, and office expenses which are directly related to performance of the Work.

"Affiliate" as used herein shall mean any of Company's parent or affiliated companies.

"Business Day" shall mean every calendar Day other than a Saturday, Sunday, or a Day which is a federal bank holiday in Houston, Texas.

"Central Clock Time" or "CCT" shall mean Central Standard Time (CST) except for that period when daylight savings is in effect.  During this period, CCT shall mean Central Daylight Time (CDT).  Unless otherwise stated, all times in this agreement are Central Clock Time.

"Claim" shall have the meaning set forth in Paragraph 20 of this Part II.

"Company's Premises" includes all work places, land, right-of-way easements, surface easements, property, buildings, temporary and permanent structures or installations, vehicles, helicopters, airplanes and other conveyances owned by, leased to, operated by and under the control of Company, its parent and/or affiliated companies or otherwise used for Company's, its parent's and/or affiliated companies' business (including all land and offshore facilities).

"Company's Representative" as used herein shall mean the individual designated in writing by Company to Contractor as the person having general authority to decide questions and resolve problems raised by Contractor or occurring in relation to the Work.  The Company's Representative shall also have authority to delegate to inspectors or other Company's instructed personnel, designated duties in connection with the quality, inspection and progress of the Work; provided, however, that the Company's Representative shall not have authority to delegate its duties under Paragraphs 11 and 16 herein.  Company may change Company’s Representative at any time and from time to time by written notice to Contractor.

"Construction Schedule" shall mean a detailed construction schedule in graph or CPM form as required from Contractor pursuant to Part III of this Agreement.

"Contract Price" shall have the meaning given to such term in Part IV of this Agreement.

"Contractor’s Representative" as used herein shall mean the individual designated by Contractor as the person having general authority to represent Contractor.  Except as specified in Paragraph 5(b) of this Part II, Contractor’s Representative shall have complete written authority to act on behalf of, and to bind, Contractor in all matters pertaining to the Work and this Agreement.

"Day" shall mean a period beginning and ending at nine o'clock a.m., Central Clock Time.

"EPA" shall mean the Environmental Protection Agency.

"Extra Work" shall have the meaning set forth in Paragraph 12 of this Part II.

"Extra Work Order" shall have the meaning set forth in Paragraph 12 of this Part II.

"Facilities" shall mean the mooring facilities for the multiple barge mounted electric generation units to be constructed and installed near Far Rockaway, New York at the southern southwestern corner of Long Island, together with all it facilities, properties, equipment, easements, rights of way, permits, components and all rights with respect thereto, all of which are more specifically defined in the Scope of Work.

"Final Acceptance" shall have the meaning set forth in Paragraph 17(d) of this Part II.

"Governmental Authorizations" shall mean all permits, licenses, authorizations, consents, decrees, waivers, privileges, approvals, authorizations or exemptions from, and all filings with, and notices to, any governmental authority or any court or judicial authority in each case required in order for the Work to be acquired, constructed and operated in compliance with applicable Laws.

"Hazardous Materials" means hazardous wastes, hazardous substances, hazardous constituents, toxic substances or related materials, whether solids, liquids or gases, including but not limited to substances defined as "Hazardous Wastes", "Hazardous Substances", "Toxic Substances", "Pollutants", "Contaminants", "Chemicals Known To Cause Cancer Or Reproductive Toxicity", "Radioactive Materials", or other similar designations subject to regulation under any federal, state or local laws, or any rules, regulations, plans or ordinances adopted, or other criteria and guidelines promulgated pursuant thereto, governing or regulating the use of such substances or materials, or damage to or the use of natural resources, soil, surface water, groundwater, subsurface strata or the ambient air, now or hereafter in effect.

"In-Service" shall mean that the Work is capable of being placed in service as a electric power generation facility though not completed and accepted.

"In-Service Date" shall have the meaning set forth in Paragraph 3(b) of this Part II.

"Interest Rate" shall mean a per annum rate of interest equal to the lesser of (a) the prime rate published in the Wall Street Journal under "Money Rates" and (b) the maximum rate permitted by applicable Laws.

"Judgment" Whenever the judgment, consent, approval, discretion, determination, satisfaction, request, or like acts or the refrain from acting is to be given, exercised or made, the Company shall do so reasonably in accordance with standard industry practice and procedures.

"Law" shall mean any constitution, charter, act, statute, law, ordinance, code, rule, regulation, order, treaty, decree, announcement or published practice or any interpretation thereof (including those related to labor, taxes and the environment), or specified standards or objective criteria contained in any applicable Governmental Authorization, or other legislative or administrative action of any governmental authority, or a final decree, judgment or order of a court or any applicable engineering, construction, safety or electrical generation code.

"Punchlist" shall have the meaning set forth in Paragraph 3(b) of Part II.

"Scope of Work" shall mean the scope of work attached hereto as Exhibit "A" including all other work reasonably necessary and inferable from such Exhibit “A”.

"Site" shall mean any physical location or locations near the mooring location, as specified in Exhibit "A", where the Work is to be performed, including any off-Site work or storage facilities.

"Subcontractor" shall mean any subcontractor, vendor or supplier of equipment, materials or services to Contractor or any subcontractor or any person engaged or employed by any such subcontractor, vendor or supplier in connection with the performance of any portion of the Work.

"Utility" shall mean Long Island Power__________________.

"Waste" as used herein shall include, but not be limited to, any garbage, refuse, sludge and other spent or discarded material, including solid, liquid, semisolid, or contained gaseous materials resulting from industrial, commercial, mining and agricultural activities or from community or individual activities, excluding, however, all Hazardous Materials.

"Work" as used herein shall mean the doing of all things described in the Scope of Work defined in Part I all in accordance with the terms, conditions, and standards of this Agreement.

2.	Time Requirements.  Time being of the essence in the performance of this Agreement, the Contractor agrees to prosecute the Work regularly, diligently and uninterruptedly at such rate of progress as will be sufficient to meet the In-Service Date specified in Part I.  Contractor acknowledges that the time requirements herein provided are both reasonable and realistic.

- Schedule, In-Service Date, and Final Acceptance.

(a)	Construction Schedule.  At the time of execution of this Agreement, Contractor shall submit to Company a Construction Schedule and progress chart showing its projected rate of progress toward completion of the Work.  The Construction Schedule shall be in accordance with Part III, Instruction to Bidders, where applicable, or as otherwise specified by Company herein.

- In-Service Date.  Upon completion of that portion of the Work required to place the Facilities in electric power generation service, Contractor shall so notify the Company in accordance the provisions of Paragraph 6 of Part I.  Company and Contractor shall inspect the Facilities, and if in Company’s sole judgment the Work is capable of being placed in electric power generation service, the Company shall establish the “In-Service Date”.  Within fifteen (15) Days of such In-Service Date, the Contractor and Company shall perform an on-Site inspection of the Facilities and establish a punchlist of items remaining to be completed per the Scope of Work (the “Punchlist”).

- Final Acceptance.  Upon Contractor’s completion of all items specified in the Punchlist to Company’s satisfaction, delivery of all items required in this Agreement, execution and delivery in the form specified by Company of any and all documents necessary to convey ownership of the Facilities to the Company and the completion of those requirements more specifically set forth in Paragraph 17(d) of Part II, Company shall make final payment to Contractor.

- Review and Contractor Reporting Requirements.  Contractor shall submit, in a timely manner, its engineering and detailed design drawings, calculations, specifications, data, and all other pertinent information required herein, to Company's Representative for review and comment in sufficient time to enable Company to review, raise comments or queries on such drawings and documents and to permit resolution of such comments or queries prior to the commencement of the Work described in such drawing or document and without impeding the performance of Contractor's other obligations under this Agreement.  Company's review of such drawings and documents will cover only general conformity of the data to the Scope of Work in Exhibit "A".  Company's review does not indicate a thorough review of all dimensions, quantities, and details; nor shall review by Company be construed as relieving the Contractor from any responsibility for errors or deviations from the requirements of this Agreement.  All engineering data submitted, after final processing by Company shall become part of this Agreement and the Work indicated or described thereby shall be performed in conformity therewith, unless otherwise required by Company.

During the performance of the Work, Contractor shall submit to Company biweekly (or more frequently if requested by Company)  progress reports on the actual progress and updated schedules containing information and documentation as may be required by this Agreement or requested by Company.  In the event Contractor's performance of the Work is not in compliance with the schedule established for such performance or Construction Schedule, Company may, in writing, require Contractor to submit its plan for schedule recovery, or specify in writing the steps to be taken to achieve compliance with such schedule, and/or exercise any other remedies under this Agreement.  Contractor shall thereupon take such steps as may be necessary to improve its progress without additional cost to Company.

- Inspection and Responsibilities for the Work.

- Company's Representative

The Company's Representative will visit the Work Site at intervals appropriate to keep familiar generally with the progress and quality of the Work and to determine in general if the Work is proceeding in accordance with this Agreement.  However, the Company's Representative will not be required to make exhaustive or continuous on-Site inspections to check the quality or quantity of the Work.

Except as required by Law, the Company's Representative will not be responsible for, and will not have control or charge of, the means, methods, techniques, sequences or procedures or for safety precautions and programs in connection with the Work, and the Company's Representative will not be responsible for Contractor's failures to carry out the Work in accordance with this Agreement.  The Company's Representative will not be responsible for or have control or charge over the acts or omissions of the Contractor, its Subcontractors, or any of their agents or employees, or any other persons performing the Work.   Contractor shall carry out its obligations hereunder to ensure that the Work is designed, specified, and constructed in a manner which complies with the requirements and standards as set forth herein.  Contractor shall bring to the attention of Company any discrepancies between the Work and such requirements and standards of which the Contractor should be aware.

The Company's Representative shall at all times have access to the Work wherever it is in preparation or progress, and to any other location where equipment or material for the Work, if any, is being fabricated or stored by the Contractor or its Subcontractors.  All Work shall be performed in a good and workmanlike manner and shall meet with the approval of Company's Representative; provided, however, that no inspection or suggestion by Company Representative or Company employees or agents shall operate to control the method of performance of the Work hereunder, the manner and method of performing the same being under the sole control and direction of Contractor, Company having interest only in the results obtained, and Contractor shall perform all Work hereunder as an independent contractor.

- Contractor's Representative

On or before commencement of the Work, Contractor shall designate the Contractor's Representative, who shall be authorized to act on behalf of Contractor, with whom Company may consult at all reasonable times, and whose instructions, approvals, requests and decisions shall be binding upon Contractor as to all matters pertaining to this Agreement and the performance of Contractor hereunder; provided however, that the Contractor’s Representative shall not have authority to amend or to modify any of the provisions of this Agreement.  Contractor may change the Contractor's Representative at any time and from time to time by written notice to Company.

- Representations and Warranties.

(a)  Contractor covenants, warrants and represents to Company that:

(i)		It is a corporation duly organized, validly existing and in good standing under the laws of its jurisdiction of incorporation, qualified to do business in all jurisdictions in which the nature of the business conducted by it makes such qualification necessary and where failure so to qualify would have a material adverse effect on its financial condition, operations, prospects or business. Contractor has authority to do business in the state in which the Work is to be performed

(ii)		It is not in violation of any applicable Law which violations, individually or in the aggregate, would affect its performance of any obligation under this Agreement.  There are no legal or arbitration proceedings or any proceeding by or before any court or governmental authority now pending or (to its best knowledge) threatened against it which, if adversely determined, could reasonably be expected to have a material adverse effect on its financial condition, operations, prospects or business as a whole, or ability to perform all its obligations under this Agreement.

(iii)		None of the execution and delivery of this Agreement, the consummation of the transactions herein contemplated or compliance with the terms and provisions hereof and thereof will conflict with or result in a breach of, or require any consent under, its charter or bylaws or any applicable Law, or any agreement or instrument to which it is a party or by which it is bound or to which it or any of its respective assets are subject, or constitute a default under any such agreement or instrument.

(iv)		It has all necessary power and authority to execute and deliver and it has all necessary power and authority to perform its respective obligations under this Agreement; and its execution, delivery and performance of this Agreement has been duly authorized by all necessary action on its part; and this Agreement has been duly and validly executed and delivered by it and constitutes its legal, valid and binding obligation, enforceable in accordance with its terms, except as the enforceability thereof may be limited by bankruptcy, insolvency, reorganization or moratorium or other similar Laws relating to the enforcement of creditors' rights generally and by general equitable principles.

(v)		The Work will be accomplished in a good and workmanlike manner in accordance with Company's approved practices and standards, including but not limited to the Engineering Standards, with approved practices and standards of the industry, and with all plans and specifications made a part of this Agreement.  Contractor assumes sole responsibility to assure that the Work is accomplished in accordance with any and all prudent and applicable safety standards.

(vi)		Contractor is engaged in the business of, and has developed the requisite expertise for performing the Work.  Contractor and its agents, employees and Subcontractors have the capability, experience, expertise and means required to perform the Work and the Work will be performed using personnel, equipment and materials qualified and/or suitable to do Work requested.  Contractor acknowledges that Company is relying on Contractor's expertise and knowledge in its performance of the Work.

(vii)	Contractor shall comply with all valid applicable federal, state and local Laws, ordinances and regulations thereunder, issued or promulgated by units of government and regulatory bodies with jurisdiction over any aspect of the Work.  Contractor shall secure, at its expense, all necessary permits and licenses for the performance and completion of the Work, including but not limited to, the operation, hauling and transportation of all materials and/or equipment needed, used or supplied in and for the Work, and Contractor shall pay in connection therewith, without reimbursement from Company, all valid and applicable fees, assessments or taxes levied by units of government with jurisdiction.

(viii)	Upon completion of the Work, the Site as it relates to the Work performed by Contractor will comply with the requirements of all permits and all valid and applicable statutes, ordinances, orders, rules and regulations of the federal, state, and local governments having jurisdiction thereof.

(ix)		It shall be the responsibility of the Contractor to examine, and Contractor specifically represents that it has carefully examined this Agreement, including all drawings, specifications, and special conditions, if any; that it has inspected the sites and routes of the Work, and is acquainted thoroughly with all conditions likely to be encountered in performing the Work.  In relation to the project Site, Contractor has taken into account all facets of the job including, but not limited to, the items listed below as they relate to the specifications and the conditions which may be encountered in performing the Work, and Contractor's price reflects consideration of all of them.

1.	Abnormal weather conditions.

2.	Completion of project in order to meet the specified In-Service Date.

3.	Labor conditions and availability.

4.	Rail locations.

5.	Material type, size and availability.

6.	Road load limit.

7.	Special taxes, assessments, or use fees.

8.	Equal Opportunity/Affirmative Action/Drug Testing responsibility.

9.	Applicable federal, state and local Laws, ordinances, statutes, rules and regulations.

10.	Applicable federal, state and local environmental safety standards.

11.	Means of communications with and transportation and access to the Site

12.	Equipment availability and cost

(x)		As of the Effective Date, Contractor shall be deemed to have inspected the Site and its surroundings and has satisfied itself as to the condition of all circumstances affecting the Site and the Work, including the nature of the ground and subsoil, the form and nature of the Site, the extent and nature of the work and materials necessary for the carrying out and completion of the Work, the means of communications with and transportation and access to the Site, the accommodations Contractor may require and in general all risks and contingencies influencing or affecting the Work.  Contractor shall not, except as expressly provided in this Agreement, be entitled to any extensions of the In Service Date or to any adjustment of the Contract Price on grounds of misinterpretation or misunderstanding of any such matter, nor shall it, except as provided, be released from any of the risks accepted or obligations undertaken by it under this Agreement or on the grounds that it did not or could not reasonably have foreseen any matter which affects the execution of the Work.

(xi)		Contractor shall make timely payments to all materialmen, Subcontractors and suppliers for materials and services furnished by them for the Work, and failure of Contractor to so perform shall be deemed a breach hereof.

(xii)	Contractor warrants good title to all Work, including easements and rights of way, and warrants and guarantees that title, when it passes to and vests in company, will be free and clear of any and all liens, claims, charges, security interests, encumbrances and rights of others of any type or kind.

- Company covenants, warrants and represents to Contractor that:

(i)		It is a limited liability company duly organized, validly existing and in good standing under the laws of its jurisdiction of incorporation, qualified to do business in all jurisdictions in which the nature of the business conducted by it makes such qualification necessary and where failure so to qualify would have a material adverse effect on its financial condition, operations, prospects or business.

(ii)		It is not in violation of any applicable Law which violations, individually or in the aggregate, would affect its performance of any obligation under this Agreement.  There are no legal or arbitration proceedings or any proceeding by or before any court or governmental authority now pending or (to its best knowledge) threatened against it which, if adversely determined, could reasonably be expected to have a material adverse effect on its financial condition, operations, prospects or business as a whole, or ability to perform all its obligations under this Agreement.

(iii)		None of the execution and delivery of this Agreement, the consummation of the transactions herein contemplated or compliance with the terms and provisions hereof and thereof will conflict with or result in a breach of, or require any consent under, its charter or bylaws or any applicable Law, or any agreement or instrument to which it is a party or by which it is bound or to which it or any of its respective assets are subject, or constitute a default under any such agreement or instrument.

(iv)		It has all necessary power and authority to execute and deliver and it has all necessary power and authority to perform its respective obligations under this Agreement; and its execution, delivery and performance of this Agreement has been duly authorized by all necessary action on its part; and this Agreement has been duly and validly executed and delivered by it and constitutes its legal, valid and binding obligation, enforceable in accordance with its terms, except as the enforceability thereof may be limited by bankruptcy, insolvency, reorganization or moratorium or other similar Laws relating to the enforcement of creditors' rights generally and by general equitable principles.

7.	Governmental Authorization and Contractor Assistance.

(a)	Contractor shall obtain in a timely manner the Governmental Authorizations listed in Exhibit F for which it is designated as responsible for submitting and obtaining and all other Governmental Authorizations required in order for the Facilities to be located and operated at the Site or which applicable Law requires. Contractor shall give all notices and pay all fees required to be given or paid in relation to any such Governmental Authorizations which are the responsibility of Contractor, and such fees are specifically included in the Contract Price herein.  Contractor shall use reasonable efforts (including, but not limited to, providing documents and information requested by Company) to assist Company in its efforts to obtain the Governmental Authorizations which Company is required to obtain pursuant to Section 7(b) and as indicated in Exhibit F.  Contractor will use reasonable efforts to support Company in Company’s coordination and communications with Utility.

(b)	Company shall be responsible for obtaining or causing to be obtained, the Governmental Authorizations listed in Exhibit F which shall include, for which it is designated as responsible for submitting and obtaining and all other Governmental Authorizations Company shall use reasonable efforts (including, but not limited to, providing documents and information requested by Contractor) to assist Contractor in its efforts to obtain the Governmental Authorizations which it is required to submit and obtain pursuant to Section 7(a).  Company shall be responsible at all times for coordinating and communicating with Utility with respect to all matters, including submission of notices and other documents and the handling and processing of comments and directions given by Utility.

8.	Guarantees.  Contractor shall be responsible for any and all materials or Work until acceptance thereof by Company, and shall be required to repair, to the satisfaction of Company, or pay for, any loss, injury or damage which said materials or Work may sustain from any source or cause whatever before acceptance of the Work. Contractor guarantees and warrants to Company that the Work shall comply strictly with the provisions of this Agreement and that the Work shall be first-class in every particular and free from defects in workmanship and any errors and omissions in the design or engineering furnished by Contractor or Contractor’s Subcontractors, at any tier.  Without limitation of any other rights or remedies of Company, if any defect in the Work in violation of the foregoing guarantees and warranties arises for a period of twenty-four (24) months after In-Service, Contractor shall upon receipt of written notice of such defect promptly furnish, at no cost to Company, design and engineering, labor, equipment and materials necessary to correct such defect and to cause the Work to comply fully with the foregoing guarantees.

Contractor further warrants to Company that all materials, equipment and supplies furnished by Contractor for the Work shall be new, unrepaired, unmodified, merchantable, of the most suitable grade and fit for their intended purposes.  Additionally, Contractor shall request guarantees with respect to machinery, equipment, materials, and work from all vendors, Subcontractors and construction contractors from which Contractor procures machinery, equipment, materials or work in connection with Work performed hereunder, and will make such guarantees available to Company, and its assignees, to the full extent of the term thereof.  Such guarantees will extend for at least twenty-four (24) months from Company's Final Acceptance of the Work, and such guarantees will guarantee the material and equipment to be free of faulty design (where materials or equipment are designed by vendor or Subcontractor), workmanship and materials, and that the materials and equipment comply with Company's specifications.  Such guarantees shall run directly to Company, and Contractor shall render all reasonable assistance to Company in enforcing such guarantees, including cooperation with Company in litigation brought to enforce such guarantees.  If a vendor or Subcontractor is unable or unwilling to guarantee the material and equipment to be free of faulty design, workmanship and materials by reason of the vendor or Subcontractor relying upon Contractor's process or mechanical calculations, in the design and manufacture of the materials and equipment, the Contractor shall guarantee to Company and its successors and assigns that such materials and equipment will be free of faulty design, materials and workmanship for a period of twenty-four (24) months from Company's Final Acceptance of the Work.

9.	Rights Reserved to and Material Furnished by Company	.  As an option, Company may elect to furnish to Contractor those major items of material and/or equipment set forth in Exhibit C, that are within the Contractor’s Scope of Work and Contract Price. In the event Company elects such option, the parties agree that:  (i) Company shall furnish said material and/or equipment to Contractor in accordance with the project schedule delivery dates; and (ii) that a corresponding reduction shall be made to the Contract Price for the actual purchased cost of each item of material or equipment furnished by Company; provided, however, that in no event shall the price reduction for any item exceed Contractor’s budgeted cost for such item.

All risks of damage or loss to said stocks of materials by pilferage, vandalism or casualty of any nature shall be Contractor's risk after delivery and unloading of such materials at the delivery points noted in the specifications.

10.	Risk of Loss, Passage of Title.

- Contractor, at its sole cost, shall be responsible for and obligated to replace, repair, or reconstruct the Work and any material, equipment, or supplies furnished for the Work which is lost, damaged or destroyed prior to In-Service Date however such loss shall occur.  Contractor shall be responsible for repair and replacement of any of Company's other property, other than the Work covered by this Agreement, which is lost, damaged, or destroyed by the act or omission of Contractor.

- Title to the Work or any part thereof shall pass to Company when payment for the Work or any part thereof is made.  The provisions of Paragraph 9(a) shall govern the risk of loss under this Agreement, notwithstanding the provisions of this Paragraph 9(b) respecting the passage of title.

11.	Correction of Work.  When it appears to Company during the course of the Work that any of the Work does not reasonably conform to the provisions of this Agreement and any and all drawings and specifications), Company shall notify Contractor of such non-conformity and Contractor shall, at its sole expense and without reimbursement from Company, promptly make the necessary corrections so that such Work will so conform.  In addition, Contractor shall, at its sole expense, promptly correct, repair, or replace any defects, deficiencies, errors or omissions in workmanship in the Work performed by Contractor or any Subcontractor of Contractor, or any failure in any part of the Work.  Contractor will repair or commence repairs within fifteen (15) Days of notification.  Upon Contractor's failure to promptly correct said Work hereunder, Company may make the necessary corrections and may invoice Contractor for the reasonable cost thereof.  In the event the Work performed by Contractor for Company is incorrect or otherwise in error, the Contractor shall indemnify and hold Company, its parent and affiliated companies, harmless from and against all damages, losses, costs, and expenses (including attorneys' fees) which Company may incur by reason of Contractor's error.

12.	Extra Work - Changes  Company may require Contractor to perform work or furnish materials or equipment, or the use thereof, in connection with the Work which are not included in this Agreement (hereinafter referred to as "Extra Work"). Extra Work may be occasioned by major changes in specifications requiring additional work or materials of different nature, kind and cost from that contemplated at the time of execution of this Agreement, or the performance of other or additional work incident to the completion of the facilities here involved, but not in contemplation of the parties at the time of execution of this Agreement.

Contractor shall not perform any Extra Work without first having secured written authorization from Company which shall be signed by Company's Representative (“Extra Work Order”).  Such authorization shall describe the work to be done and specify the price to be paid therefor, or the basis on which such price shall be calculated in accordance with the applicable unit prices, set forth in Exhibit "D".  Company and Contractor shall agree in the Extra Work Order what modification, if any, should be made to the Contract Price or In-Service Date as a result of the Extra Work Order.  Should Contractor perform any Extra Work without advance written authorization from Company Representative such Extra Work shall be at Contractor's expense.

Modifications or changes in the specifications which are within the general scope of this Agreement may be made at any time by Company's Representative's written order to Contractor.  Company shall decide as to the meaning and intent of any portion of the specifications where the same may be thought to be obscure or where the same are in dispute, and company shall have the right to correct any errors or omissions therein when corrections are necessary to the proper fulfillment of its intent.  Such modification or changes shall not be considered Extra Work.

IN NO EVENT SHALL COMPANY BE LIABLE TO CONTRACTOR, ITS SUBCONTRACTORS, VENDORS OR AFFILIATES, FOR ANY LOSSES SUFFERED BY CONTRACTOR, WHETHER DIRECT OR INDIRECT, CONSEQUENTIAL, OR SPECIAL LOSS OR DAMAGE, ARISING FROM COMPANY'S REQUIREMENT FOR EXTRA WORK.

13.	Use of Completed Portions of the Work.  Company shall have the right to take possession of and use any completed or partially completed portions of the Work, notwithstanding that the time for completing the entire Work or such portions thereof may not have expired, but such taking possession and use shall not be deemed an acceptance of any Work not completed as specified.

14.	Default, Termination, and Suspension.

- Termination - Contractor's Default.

(i)	Termination for Contractor's Inability to Perform.  If any proceeding is instituted against Contractor seeking to adjudicate Contractor as a bankrupt or insolvent, or if Contractor makes a general assignment for the benefit of its creditors, or if a receiver is appointed on account of the insolvency of Contractor, or if Contractor files a petition seeking to take advantage of any other Law relating to bankruptcy, insolvency, reorganization, winding up or composition or readjustment of debts and, in the case of any such proceeding instituted against Contractor (but not by Contractor) such proceeding is not dismissed within sixty (60) Days of such filing, or should Company conclude, on evidence deemed by it to be sufficient, that Contractor’s financial position is insecure, Company may, without prejudice to any other right or remedy Company may have, terminate this Agreement effective one (1) Business Day after giving written notice of such termination to Contractor.

(ii)	Termination for Contractor's Failure to Perform.  If Contractor refuses or fails, except in cases for which an extension of time is provided, to supply sufficient properly skilled workmen or proper materials, or it fails to meet the Construction Schedule, or if it fails to make prompt payment of undisputed invoices due to Contractor's Subcontractors or for materials or labor, or otherwise repudiates or is in default with respect to any of its obligations to any Contractor's Subcontractor, or otherwise is guilty of a material violation of a provision of this Agreement or fails to correct or commence correction of any defective Work during performance of the Work of which it is advised by Company or any Company’s Representative within five (5) Days of receipt of notice, or if Contractor is cited for failure or failures to observe the Occupational Safety and Health Act of 1970, as amended, and the regulations issued thereunder, which citations and failure in the judgement of Company will adversely affect the proper and timely completion of the Work or the necessary operations and work of Company or for the breach of paragraphs 22 or 25 of Part II of this Agreement, Company may, without prejudice to any right or remedy and after giving Contractor one (1) Business Day's notice thereof, terminate this Agreement.

(b)	Company's Rights. 	 In the event that Company elects to terminate this Agreement pursuant to Paragraph 14(a) if this Part II, Contractor shall provide Company, any Replacement Contractors, as defined below, and Subcontractors, or lender, at Contractor's expense, the right to continue to use any and all patented and/or proprietary information (subject to reasonable proprietary restrictions) of Contractor, Contractor's Subcontractors, or other third party providing Work under this Agreement, which Company deems necessary to complete the Work.  Furthermore, Company shall have the right to take possession of all Contractor's materials wherever located on the date of such termination for the purpose of completing the Work and may employ any other person, firm or corporation (sometimes hereinafter referred to as "Replacement Contractor") to finish the Work in accordance with the terms of this Agreement as may be assigned to such Replacement Contractor pursuant to Paragraph 14(c) of this Part II, by whatever method that Company may deem expedient.  Company shall be required to mitigate reasonably the cost for completion of such Work but may make such expenditures as in Company's sole judgement will best accomplish the timely completion of the Work, provided Company shall not be required or expected to mitigate any such costs by terminating, repudiating or renegotiating any agreement entered into between Contractor and any Contractor's Subcontractor.

(c)	General Obligations. 	 If Company elects to terminate this Agreement or Contractor's employment pursuant to Paragraph 14(a) of this Part II, Contractor shall, at Company's request and at Contractor's expense, perform the following relative to the Work so affected:

(i)		immediately discontinue the Work on the date and to the extent specified in such notice;

(ii)		assist Company in preparing an inventory of all Contractor's Materials, Contractor's Construction Equipment and Company's Equipment and supplies in use or in storage at or off the Site;

(iii)		assign to Company, or to any Replacement Contractor designated by Company all subcontracts and other contractual agreements (including warranties) as may be designated by Company, all of which subcontracts and contractual agreements shall be so assignable, and make available all issued permits, licenses, authorizations, approvals, patents and other proprietary rights then held by Contractor pertaining to the Work and use reasonable efforts to procure cancellation upon terms satisfactory to Company of all other orders, Subcontracts, and rental agreements; remove from the Site all such Contractor's materials, Contractor's construction equipment and rubbish as Company may request;

(iv)		thereafter execute only that portion of the Work directed by the Company as may be necessary to preserve and protect Work already in progress and to protect equipment and materials at the Site or in transit thereto;

(vi)		deliver to Company all design and other information as may be reasonably requested by Company for the completion and/or operation of the Work.

(d)	Payment Obligations. 	 If Company terminates this Agreement pursuant to Paragraph 14(a) of this Part II Contractor shall not be entitled to receive any further payments under this Agreement until the Work is finished.  As soon as practicable after completion of the Work, Company shall determine the total reasonable and necessary expense incurred and accrued in connection with the termination of this Agreement including all legal fees and expenses and the completion of the Work including, without limitation, all amounts charged by any Replacement Contractor to finish the Work based on the obligations such Replacement Contractor assumes under this Agreement and under any of Contractor's subcontract(s) or other contractual agreement(s) that Company elects to have assigned to such Replacement Contractor pursuant to Paragraph 14(c)(ii) of this Part II, and additional reasonable and necessary overhead incurred and accrued by Company to effect such takeover and to complete the Work.  If the total expenses incurred by Company in completing the Work exceed the balance of the Contract Price unpaid at the time of Contractor's default, then Contractor shall be liable for and shall pay to Company the amount of such excess, within ten (10) Days following receipt of Company's demand for such payment.  To the extent that total expenses incurred by Company in completing the Work are less than the Contract Price, then Company shall pay Contractor for the Actual Value of Work performed by Contractor in accordance with the terms of this Agreement prior to termination.

(e)	Optional Termination by Company	.

(i)		Rights.  Company may terminate this Agreement in whole or in part at any time by written notice thereof to Contractor.  Upon receipt of any such notice, Contractor shall, unless the notice directs otherwise:  (i) immediately discontinue the Work on the date and to the extent specified in such notice; (ii) place no further orders or subcontracts for materials or services except as may be necessary for completion of such portion of the Work as is not discontinued; (iii) promptly make every reasonable effort to procure cancellation upon terms satisfactory to Company of all orders, subcontracts and rental agreements to the extent they relate to the performance of the Work that is discontinued; and (iv) thereafter execute only that portion of the Work continued and as may be necessary to preserve and protect Work already in progress and to protect equipment and materials at the Site or in transit thereto.

- Remedies.  CONTRACTOR WAIVES ANY CLAIMS FOR CONSEQUENTIAL DAMAGES, INCLUDING LOSS OF ANTICIPATED PROFITS FOR UNCOMPLETED WORK, on account of a termination by Company pursuant to this Paragraph 14(e) and shall accept as its sole remedy the following:  Contractor shall be entitled to reimbursement for its actual costs and incurred liabilities not paid to date plus all reasonable out-of-pocket costs of termination, for all aspects of the Work properly performed by Contractor, and Contractor's Subcontractors.  Contractor shall use reasonable efforts to minimize any such costs of termination.  If, at the date of such termination, Contractor has properly performed services or purchased, prepared, or fabricated off the Site any materials, or assembled off the Site any equipment for subsequent incorporation at the Site, Company shall have the option of having such equipment and materials or that portion of equipment and materials prepared or fabricated delivered to the Site or to such other place as Company shall reasonably direct.  Payments for termination under this Paragraph 14(e) shall be due to Contractor within thirty (30) Days of Company's receipt of (i) a substantiated invoice approved by Company and (ii) of any such materials or off the Site fabrication of materials.

- Suspension of Work.

(i)		Company may at any time, from time to time, by written notice to Contractor suspend further performance of all or any portion of the Work by Contractor.  Said notice of suspension shall specify the date of suspension and the estimated duration of the suspension.  Upon receiving any such notice of suspension, Contractor shall promptly suspend further performance of the Work to the extent specified, and during the period of such suspension shall properly care for and protect all Work in progress and materials, supplies, and equipment Contractor has on hand for performance of the Work.  Upon the request of Company, Contractor shall promptly deliver to Company copies of outstanding purchase orders and subcontracts of Contractor for materials, equipment and service for the Work, and shall take such action relative to such purchase orders and subcontracts as may be directed by the Company.  Contractor shall use its best efforts to utilize its material, labor and equipment in such a manner as to mitigate costs associated with suspension.  Company may at any time withdraw the suspension of performance of the Work as to all or part of the suspended Work by written notice to Contractor specifying the effective date and scope of withdrawal, and Contractor shall resume diligent performance of the Work for which the suspension is withdrawn on the specified effective date of withdrawal.

(ii)		Contractor shall give Company written notice within five (5) Business Days after the point in time during a suspension which Contractor believes the suspension gives rise to a claim by Contractor for an increase in the Contract Price or in the In-Service Date. Notwithstanding the foregoing, in no event shall such notice be given by Contractor later than five (5) days after the withdrawal of suspension.  Within ten (10) Business Days after the happening of such event, Contractor shall supply Company with a statement supporting Contractor's claim, which statement shall include Contractor's detailed estimate of the change in Contract Price and In-Service Date.  Contractor shall substantiate its claim with payroll documents, paid invoices, receipts, records of performance and other documents satisfactory to Company and subject to Company's verification.  Company shall not be liable for, and Contractor hereby waives, any claim or potential claim of Contractor which was not reported by Contractor in accordance with the provisions of this Article.  The parties shall negotiate in good faith to reach an agreement, but in no case, except with Company's prior written consent, shall any work be halted pending such agreement, whether or not the claim can be resolved to Contractor's satisfaction, and Contractor shall be bound by the terms and conditions of this Agreement to prosecute the Work without delay to its successful completion.   No claim hereunder by Contractor shall be allowed if asserted after final payment under this Agreement.  Contractor's remedies are limited to those expressly set forth in this Agreement and in no event shall Contractor be entitled to any prospective profits or any damages because of such suspension or withdrawals of suspension.

15.	Force Majeure. Notwithstanding any other provision in the Agreement to the contrary, including any provision with the same or similar qualifying language, no delays in or failure or omission in the performance of any obligation under this Agreement by Contractor or Company, other than payment of money, shall constitute default under this Agreement if and to the extent such delay or failure of performance is caused by Force Majeure.  “Force Majeure” shall mean any act that (a) renders it impossible for Contractor to perform its obligations under this Agreement, (b) is not reasonably anticipated by Contractor, (c) is beyond its reasonable control, (d) is not due to its fault or negligence and (e) cannot be avoided by the exercise of due diligence, including the expenditure of any reasonable sum of money.  Subject to the satisfaction of the conditions set forth in (a) through (e) above, Force Majeure shall consist of the following types of events: act of government, acts of God, strike, insurrection, embargo, fire, flood, earthquake, explosion, riot, war, rebellion, sabotage, epidemic, or any other cause beyond reasonable control of a party to this Agreement.  In no event shall Force Majeure include economic hardship or changes in market conditions.  In the event of a force majeure occurrence, the party whose performance is prevented by such occurrence shall notify the other party, in writing, as soon as reasonably possible, but in no event later than five (5) days after the occurrence of the force majeure event, and give full particulars thereof and shall reasonably endeavor to remedy the situation as soon as possible.  Appropriate price and schedule changes shall thereafter be made to this Agreement.  Failure to give notice as provided herein shall be deemed waiver of any claim for such force majeure event.

16.	Records and Audit.  Company, or its designated representative shall have the right for a period of four (4) years following completion of the Work under this Agreement during reasonable business hours, upon ten (10) days prior notice at Contractor's office location and at Company's expense, to audit all books and records of Contractor, and any Subcontractor of Contractor, relating to the Work performed by Contractor or such Subcontractor pursuant to this Agreement. Contractor shall keep, maintain, and make available to Company complete, accurate, and up-to-date written records, including but not limited to: records of the productive time of Contractor's employees involved in performing the Work, salary information of employees who worked under this Agreement, receipts and notes and records which are pertinent to the Work, expenses and costs incurred under this Agreement, and payment thereof.  Such records shall be provided by Contractor to Company within ten (10) days of Company's request for such records from Contractor.

Where Contractor's invoice includes compensation for Work performed at a unit price basis, Contractor shall submit its determination of the number of units of Work performed, determined in accordance with the provisions of this Agreement, and substantiated by documents satisfactory in form and content to Company.  Upon verification by Company of such documents, Company will advise Contractor in writing of either acceptance of Contractor's determination of the number of units or of Company's determination of the number of units.

Contractor's invoice shall include and be substantiated and supported by equipment time slips, paid invoices, time sheets, receipts and other documents satisfactory to and verified by Company.

Contractor shall maintain for a period of four (4) years after final payment under this Agreement, all records and accounts pertaining to Work performed by Contractor under this Agreement for a unit price, a reimbursable price, or otherwise authorized in writing by Company for performance on a reimbursable basis.  Company shall have the right to audit, copy and inspect said records and accounts at all reasonable times during the course of such Work and for the above four (4) year period for the purpose of verifying units furnished and/or costs incurred, as applicable.

17.	General Payment Conditions.

- Once each month following commencement of the Work, Contractor shall prepare an invoice for the actual amounts paid by Contractor for Work satisfactorily completed during the billing period based upon the Progress Payment Schedule, Exhibit "K" of this Agreement as may be modified by any Extra Work Order.  All invoices, with supporting data, shall be sent as set forth in Part I.  Upon approval of such invoice, and subject to the further provisions hereof, Company shall pay Contractor the amount paid by Contractor as shown by the invoice within thirty (30) Days of receipt of such invoice, less any amounts reflecting payment made on previous invoices.  Company shall withhold ten percent (10%) of the amount of such payments. Payments not made when due shall bear interest at the Interest Rate.

- Timely payment by the Company to Contractor is a material part of this Agreement.  Subject to the provisions of Paragraph 17(c), if payment is withheld, Contractor may suspend services or terminate this Agreement without incurring liability to the Company, or others for damages including consequential or indirect damages.

(c)	In the event Company disputes the amount or content of any invoice, Company shall not be responsible for payment of such invoice or portion of such invoice that is in dispute, until such time as the dispute is resolved.

(d)	Subject to the provisions of Paragraph 3(c) of Part II, final payment to Contractor (including the remaining ten percent (10%)) shall be made by Company only after presentation of Contractor's final adjusted invoice (initialed and dated by Company's representative), accompanied by an executed Contractor's Completion Affidavit, and General Contractor’s/Engineer’s Final Lien Waiver and Affidavit of Payment (samples of which are marked Exhibit "G" and attached hereto), and properly supported by evidence including, releases or waivers of all liens, or claims for property damage or personal injury and proof of payment of all taxes and other obligations assumed hereunder, arising out of or in connection with the Work by all persons, firms, corporations, or agencies of government on whose behalf such liens or claims could be or have been filed, satisfactory to Company, that all charges for labor and material incorporated in the Work and all other damages or indebtedness connected with the Work for which such liens or claims could be filed have been paid and that the Work is free of all liens, claims and encumbrances.  Such payment shall be made by Company pursuant to Contractor's final adjusted invoice following Company's receipt of evidence of payment of obligations and receipt of such invoice and final inspection report from Company's representative advising that the Work has been satisfactorily completed.  Company's payment of this invoice shall constitute its “Final Acceptance” of the Work.  Acceptance by Contractor of such final payment shall constitute a waiver by it of all claims against Company related to or arising out of this Agreement.  Such Final Acceptance and payment by either party hereto shall not, however, release Contractor and its surety from any unperformed obligations hereunder.

(e)	It is understood and the parties hereto agree that the sums to be paid, as set forth above, shall be the entire consideration to be received by Contractor from Company for the Work performed hereunder, and that said sums shall include any and all taxes and contributions as set forth in Paragraph 18 hereinbelow.  Contractor shall, where applicable, separately list on its invoices all valid sales taxes on services provided hereunder.

(f)	Company, without waiver or limitation of any rights or remedies of Company, shall be entitled from time to time to deduct from any amounts due or owing by Company to Contractor in connection with this Agreement (or any other agreement with Company) any and all amounts owed by Contractor to Company in connection with this Agreement.

18.	Taxes and Other Payments.

(a)	Sales and Use Taxes

Contractor agrees that the Contract Price to be paid for Work performed under this Agreement includes any such sales, use, gross receipts or like taxes on materials, supplies, equipment or services furnished by Contractor or Subcontractor and on services performed by Contractor or Subcontractor.  Contractor shall separately list on its invoice(s) all such taxes, including the tax rate and the taxing authority to whom such taxes are due and directly payable.  Contractor shall obtain the necessary permits and licenses to remit sales, use, gross receipts and like taxes to the applicable taxing authority.  Contractor agrees to indemnify Company for all taxes, penalties and interest resulting from Contractor's failure to properly remit itemized taxes to the applicable taxing authority.  Upon written notice to Contractor, Company may elect to directly remit sales, use, gross receipts or like taxes to the taxing authority to whom such taxes are due and directly payable.  If Company exercises such election, Company shall provide Contractor with written evidence, as required by applicable taxing authority, prior to Contractor's procurement or payment of taxable purchases.

(b)	Other

Contractor assumes full responsibility for and agrees to pay for, and agrees that the Contract Price to be paid by Company as set herein shall be fully inclusive of, all labor, including overtime as legally required, all overhead, and all contributions and taxes payable under federal and state social security acts, old age pension, worker's compensation laws, unemployment compensation laws and income tax laws and any other applicable laws as to all of its employees and agents engaged in the performance of the Work hereunder; and Contractor hereby agrees to indemnify and save Company harmless against the consequences of any failure by Contractor or any of its Subcontractors to pay or withhold taxes, charges or compensation due on behalf of its employees or agents involved in the Work.

19.	Liquidated Damages.

If the Work is not capable of being placed In-Service by the In-Service Date, Contractor shall pay as liquidated damages $_____________ to the Company, except when Contractor’s delay in causing the Work to be placed In-Service may be due in whole or in part to Force Majeure or any Company caused delay.  The liquidated damages shall be paid on or within five (5) Business Days of the In-Service Date.  Contractor shall further pay as liquidated damages, $___________ on or within five (5) Business Days of the first (1st) day of every subsequent month for as long as the Work is incapable of being placed In-Service, again, except when Contractor’s delay in causing the Work to be place In-Service may be due in whole or in part to Force Majeure or any Company delay.

Company and Contractor acknowledge and agree that because of the unique nature of the Facility and the unavailability of a substitute Facility, it is difficult or impossible to determine with precision the amount of damages that would or might be incurred by the Company as a result of Contractor's failure to achieve In-Service by the In-Service Date.  It is understood and agreed by the parties that (i) Company shall be damaged by failure of Contractor to meet such obligations, (ii) it would be impracticable or extremely difficult to fix the actual damages resulting therefrom, (iii) any sums which would be payable under this Agreement are in the nature of liquidated  damages, and not a penalty, and are fair and reasonable, and (iv) such payment represents  a reasonable estimate of fair compensation for the losses that may reasonably be anticipated from such failure.

20.	General Indemnity.  To the maximum extent permitted by law, Company and Contractor agree to the following:

(a)	CONTRACTOR SHALL INDEMNIFY, DEFEND AND HOLD HARMLESS COMPANY, ITS PARENT AND AFFILIATED COMPANIES, AND ITS DIRECTORS, OFFICERS, EMPLOYEES, AND AGENTS (THE “INDEMNIFIED PARTIES”) FROM AND AGAINST ANY AND ALL CLAIMS, DEMANDS, LOSSES, DAMAGES, CAUSES OF ACTION, SUITS AND LIABILITIES OF EVERY KIND, INCLUDING ALL EXPENSES OF LITIGATION, COURT COSTS, AND ATTORNEY'S FEES, FOR INJURY TO OR DEATH OF ANY PERSON, OR FOR LOSS OR DAMAGE TO ANY PROPERTY CAUSED BY THE NEGLIGENT ACT OR OMISSION OF ANY EMPLOYEE, AGENT OR SUBCONTRACTOR OF CONTRACTOR and INJURY TO OR DEATH OF ANY PERSON, or property damage (including property of Contractor or Company) caused by any spill or release of Hazardous Materials DUE TO THE ACTIONS OR INACTIONS OF Contractor, its Subcontractors or any of their respective agents.  IN THE EVENT ANY PROPERTY DAMAGE OR PERSONAL INJURY IS CAUSED BY THE CONCURRENT NEGLIGENCE OF CONTRACTOR AND ONE OR MORE OF THE INDEMNIFIED PARTIES OR A THIRD PARTY, CONTRACTOR SHALL INDEMNIFY THE INDEMNIFIED PARTIES TO THE EXTENT CONTRACTOR’S NEGLIGENCE CONTRIBUTED TO SUCH DAMAGE OR INJURY.  CONTRACTOR SHALL HAVE NO LIABILITY FOR ANY CLAIM, DAMAGE OR CAUSE OF ACTION RESULTING FROM THE SOLE NEGLIGENT ACTS OR OMISSIONS OF THE INDEMNIFIED PARTIES.

CONTRACTOR FURTHER AGREES, EXCEPT AS MAY BE OTHERWISE SPECIFICALLY PROVIDED HEREIN, THAT THE OBLIGATION OF INDEMNIFICATION HEREUNDER SHALL INCLUDE, BUT NOT BE LIMITED TO, THE FOLLOWING:

(I)		LIENS BY THIRD PERSONS AGAINST THE COMPANY, ITS PARENT AND AFFILIATED COMPANIES, AND THEIR PROPERTY, BECAUSE OF LABOR, SERVICES, MATERIALS, OR ANY OTHER TYPE OF LIEN, FURNISHED TO CONTRACTOR, ITS ASSIGNEES OR SUBCONTRACTORS, IN CONNECTION WITH THE WORK PERFORMED BY CONTRACTOR HEREUNDER.

(II)		EXPENSES, CLAIMS, FINES, AND PENALTIES OR OTHER ENFORCEMENT CHARGES, RESULTING FROM THE FAILURE OF CONTRACTOR TO ABIDE BY ANY AND ALL VALID AND APPLICABLE LAWS, RULES OR REGULATIONS OF ANY GOVERNMENTAL OR REGULATORY AUTHORITY WITH JURISDICTION.

CONTRACTOR SHALL WAIVE AND RELEASE, AND DOES HEREBY WAIVE AND RELEASE, ANY AND EVERY MECHANIC'S LIEN OR RIGHT OF LIEN WHICH ACCRUES TO IT AT ANY TIME UPON ANY REAL ESTATE, BUILDING OR STRUCTURE OF THE COMPANY, ITS PARENT OR AFFILIATED COMPANIES, OR IF WORK IS TO BE PERFORMED ON PROPERTY OF THIRD PARTIES, EVERY MECHANIC'S LIEN OR RIGHT OF LIEN WHICH ACCRUES TO IT UPON ANY REAL ESTATE, BUILDING OR STRUCTURE OF SUCH THIRD PARTIES, AS A RESULT OF THE PERFORMANCE OF THE WORK.

For purposes of this Section 20, "Claims" shall include, without limitation, claims for personal injury or damages to or with respect to property; claims for the recovery of response costs, or actions required or orders issued under environmental laws; claims for restitution, contribution or equitable indemnity from third parties or any governmental entity; claims for injunctive relief; and other orders or notices of violation from federal, state or local agencies or courts.

IT IS THE EXPRESS INTENT OF THE PARTIES HERETO THAT THE INDEMNITY SET FORTH IN THIS SUBSECTION (b) SHALL BE APPORTIONED TO CONTRACTOR BASED SOLELY ON CONTRACTOR'S FAULT.

COMPANY DOES NOT GIVE CONTRACTOR ANY INDEMNITY OF ANY KIND IN CONNECTION WITH THIS CONTRACT OR THE WORK, AND NO SUCH INDEMNITY SHALL BE IMPLIED BY THE TERMS OF THIS AGREEMENT, THE CONDUCT OF THE PARTIES, THE RELATIONSHIP OF THE PARTIES, OR OTHERWISE.

If any one or more of the provisions contained in this Contract shall for any reason be held to be invalid, illegal, or unenforceable in any respect, such invalidity, illegality, or unenforceability shall not affect any other provision, and this Contract shall be construed as if such invalid, illegal, or unenforceable provision had never been contained in this Contract.  Further, it is agreed that with respect to any statutory limitations now or hereinafter in effect and affecting the validity or enforceability of the specific indemnification provisions hereof, such statutory limitations are made a part of the indemnification provisions hereof and shall operate to amend the indemnification provisions above to the minimum extent necessary to bring the indemnification provisions into conformity with the requirements of such statute and, as so modified, the indemnity provisions shall continue in full force and effect.

(b)	Company shall notify Contractor of any Claim that has given or could give rise to a right of indemnification hereunder or that may be presented to it by any party.  Contractor shall, at its sole cost and expense, investigate, handle, respond to, and provide defense for any Claim for which it gives indemnity herein; provided that Company shall have the right and opportunity to participate in any such investigation or defense.  At Company's sole discretion and option, exercisable at any time, Company may itself undertake the defense, litigation, settlement or satisfaction of any such Claim, reserving its right to seek indemnification against Contractor until after the Claim is resolved, or Company may direct Contractor to contest, defend, litigate, settle or satisfy any Claim made against Company, provided that Contractor shall not settle any Claim without Company's prior written consent.  In the event the Contractor, after receipt of notice of a Claim, fails to furnish a defense and indemnity as provided for under this provision, the Company shall be entitled to receive from the Contractor its attorneys' fees, costs, expenses and any amounts paid in the enforcement of this Contract.

(c)	For all indemnities contained in this Agreement, references to Company shall mean Company, its members, affiliated companies, partners, co-owners, joint venturers, and each of its and their respective directors, officers, employees, agents, servants, representatives, affiliates, including Company's joint interest owners and the surface fee owner(s) of the real property on which the Work is being performed or to which Contractor may have access hereunder.

(d)	In the event that this Paragraph 20 is found to be in conflict with any applicable law or governmental regulation, then to the extent necessary to resolve such conflict and only to such extent, such provision is to be deemed amended so as to be in compliance with any such law or governmental regulation.

(e)	In the event that Contractor engages a Subcontractor to perform any portion of the Work, Contractor agrees that it will obtain from each such Subcontractor indemnity provisions for the benefit of Company that are at least as extensive as those provided by Contractor to Company.  If Contractor fails to obtain an indemnity provision from any of its Subcontractors, Contractor agrees to protect, defend, indemnify and hold harmless Company to the same extent as provided above, as if Contractor were its Subcontractors and shall carry contractual indemnity insurance therefor.  Contractor's Subcontractors shall carry insurance policies substantially similar to, and in the same amount as, Contractor's policies of insurance carried hereunder.

(f)	Without limiting the scope of the foregoing obligations, Contractor agrees to procure insurance including contractual indemnity insurance to cover the indemnity obligations assumed by it hereunder.

21.	Patent Indemnity.  Contractor shall indemnify and hold Company, its parent and affiliated companies, its members, its members parent and affiliated companies, harmless from any and all claims arising out of infringement of patent, copyright or proprietary rights because of use of any method, process, equipment or apparatus employed by Contractor, its assignees or Subcontractors in the performance of the Work.

22.	Traffic and Special Loads.

(a)  Contractor shall carry out the Work so as not to interfere unnecessarily or improperly with access to and use of public roads.  Contractor shall liaise with, and ascertain the requirements of, all Governmental Authorities in relation to vehicular access to and use of public roads and shall comply with those requirements.  Contractor shall use  reasonable means to prevent damage to any highway or bridge by any traffic of Contractor or any Subcontractor and in particular, but without limitation, shall select routes, choose and use vehicles, and restrict and distribute loads so that such traffic as will inevitably arise from the moving of equipment to and from the Site shall be limited as far as reasonably possible and so that no damage will be caused to public highways and bridges.  Contractor shall be responsible for the routing for delivery of heavy or large loads to the Site.

(b)	Where the nature of the Work is such as to require the use by Contractor of waterborne transport, the provisions of Section 22(a) shall apply and be construed as though the terms “road”, “bridge” and “highway” include each lock, dock, terminal, sea wall or other structure related to a waterway and the term “vehicle” includes watercraft and shall have effect accordingly.

23.	Insurance.  Contractor shall procure and maintain in effect until acceptance of the Work by Company, at Contractor's sole expense, the minimum insurance coverages set forth in Exhibit "E", which shall be subject to Company's approval as to form, amount and issuing company.  Contractor shall comply with all "Additional Requirements" provisions of Exhibit "E" and said provisions are hereby incorporated in this Paragraph 23 as if fully set forth herein.  Contractor shall submit to Company at the time Contractor executes this Agreement, a Certificate of Insurance, in form satisfactory to Company, evidencing that satisfactory coverage of the type and limits set forth hereinabove are in effect.

Should Contractor fail to comply with any of the foregoing insurance requirements, Company, in its sole discretion, may immediately terminate this Agreement.  Contractor further agrees that nothing contained in Exhibit "E" shall relieve Contractor of any of Contractor's obligations and responsibilities contained in any Paragraph of this Agreement.

24.	Safety Precautions.  Contractor shall be responsible for and take all necessary and proper safety precautions to protect from accident or injury, all persons, including its employees and its Subcontractors' employees, who may be at or on the premises where the Work is being performed.  Contractor shall establish and enforce adequate, reasonable, prudent and proper safety rules and procedures and emergency procedures necessary for safe completion of the Work.  In the event of any emergency endangering life or property, Contractor shall take such action as may be necessary to prevent, avoid or mitigate injury, damage or loss and shall promptly notify Company of any such emergency and the actions taken by Contractor.

25.	Compliance With Laws and Regulations.  Contractor certifies all products, commodities or services furnished under this Agreement have been furnished in compliance with all applicable Laws and regulations, including, but not limited to, as amended, Title VI and Title VII of the Civil Rights Act of 1967, the Equal Pay Act of 1963, and Rehabilitation Act of 1974, the Immigration Reform Control Act of 1986, and Executive Orders of the President of the United States.  Contractor shall assure that each of its permitted Subcontractors complies with said requirements as well.  Contractor agrees to protect, defend, indemnify and save harmless Company, members, its parent and affiliated companies, and their directors, officers, employees, and agents, from all claims, suits, liabilities and costs, including attorney fees and costs of court, arising out of Contractor's or its permitted Subcontractors' violation of or non-compliance with such Laws, regulations, orders and guidelines.

Any breach by Contractor of any provisions contained in this Paragraph (including, without limitation, any citation of Contractor for failure to comply with any valid Law, ordinance, regulation or rule, including the Occupational Safety and Health Act of 1970 and the rules and regulations issued thereunder) which adversely affects the proper and timely completion or the performance of the Work by Contractor or affects Company's operations, shall afford Company the right, in addition to all other remedies, to invoke the Provisions of Paragraph 14 hereof.

26.   Environmental Waste.  Contractor will remove all Waste from Company's Premises which may be generated in the course of or in connection with the Work, and shall lawfully dispose of same.

(a)	Existing Hazardous Materials	.  Upon the discovery of any Hazardous Materials existing on the Site at the date of this Agreement, for which Contractor does not have liability under this Agreement, Contractor shall (i) promptly cease work in the affected area and direct its workers and Subcontractors not to remove or further disturb the material or item; (ii) promptly notify Company of such discovery; (iii) use all reasonable efforts to mitigate the effects of any such discovery on the Site, any property or person, and the performance of the Work and (iv) follow any and all directions of Company’s Representative with respect to such discoveries.  Contractor shall at Company's expense remediate such existing Hazardous Materials but only at the direction of Company to do so.

(b)	Conditions Caused by Contractor	.  Contractor shall be liable for, and shall indemnify, defend and hold harmless Company and Company’s employees, officers, and agents with respect to, any Hazardous Materials created, brought on, generated or disposed from the Site by Contractor, or any Subcontractor or disturbed by Contractor or any Subcontractor causing its release following Contractor’s or any Subcontractor’s knowledge of the existence of such Hazardous Materials.  At its own expense, Contractor shall perform all necessary clean-up, removal and disposition with respect to any such Hazardous Materials, for which it is responsible, in compliance with all applicable Law.

27.	Company Policy Regarding Drugs/Alcohol/Weapons.  Contractor agrees to advise its employees and the employees of its Subcontractors and agents that it is the policy of Company that:

(a)	The use, possession and/or distribution of illegal or unauthorized drugs, drug-related paraphernalia or weapons on Company's premises is prohibited and the use or possession of alcoholic beverages, except where authorized by Company's management, is also prohibited;

(b)	Entry onto or presence on Company's premises by any person, including Contractor, Contractor's employees, Subcontractors, Subcontractors' employees, contract personnel, temporary employees and visitors, constitutes consent to Company to conduct searches, whether announced or unannounced, on Company's premises of the person and his or her personal effects for such prohibited items; and

(c)	Any person who is found in violation of the policy or who refuses to permit a search may be removed and barred from Company's premises, at the direction of Company.

28.	Ingress and Egress.  As specified in the Scope of Work, Contractor shall secure all rights-of-way and rights of ingress and egress necessary for the prosecution of the Work.  Contractor shall not enter upon private property until all rights-of-way and rights of ingress and egress have been secured.  Contractor shall comply fully with any and all terms and conditions contained in such rights-of-way and rights of ingress and egress and shall fully indemnify Company, its parent and affiliated companies, in the same manner as set forth in Paragraph 20 above, for any costs and expenses incurred by Company, its parent and affiliated companies, as a result of any non-compliance therewith by Contractor.

29.	Public Relations.  Contractor shall exert all reasonable efforts to maintain good will for the benefit of Company with the landowners, tenants, and lessees along the right-of-way, and with the general public.  Nothing contained herein shall permit or be deemed to permit use by Contractor of Company's name, directly or indirectly, in the form of advertising or in a press release without the prior receipt of Company's written approval. Contractor shall not make news releases, publicize or issue advertising pertaining to the Work or this Agreement without first obtaining the written approval of Company.

30.	Independent Contractor.  The parties hereto agree that the Work rendered by Contractor in the fulfillment of the terms and obligations of this Agreement shall be as an independent contractor, and this Agreement does not create an employer/employee relationship between Company and Contractor.  Contractor is not entitled to the benefits provided by Company or its parent, subsidiaries or affiliates to their employees, and Contractor is not an agent, partner, or joint venturer of Company, its parent or any subsidiary or affiliate.  Contractor shall act at its own risk and expense in its fulfillment of the terms and obligations of this Agreement and agrees to employ and direct any persons performing any work hereunder.  Contractor shall not represent itself to third persons to be other than an independent contractor of Company, nor shall Contractor offer to agree to incur or assume any obligations or commitments in the name of Company, subject to the powers expressly granted in the Agency Agreement entered into between the Company and Contractor of even date herewith.

31.	Protection of Materials, Equipment, and Work.  	Contractor shall at all times, in accordance with the best practices and at no additional cost to Company, preserve and protect Contractor's material, Company’s material, Contractor's construction equipment and Company's equipment used by Contractor in the execution of the Work from damage or loss due to weather, fire, theft, unexplained disappearance or other similar casualty.

Contractor shall at all times in accordance with the best practices and at no additional cost to Company, protect the Work from damage due to Contractor's operations, equipment and materials (whether stored or installed), paving, structures and any and all other items on jobsite belonging to Company, or others.

Company shall not be responsible for any loss suffered by Contractor, or damage to the Work, or to materials, tools and equipment of Contractor or of any other contractor, and Contractor assumes responsibility for any such loss or damage and for any cost of repairing, making good, or replacing any such loss or damage that may be directed by Company.

Contractor shall take necessary actions to preclude damage to all structures, equipment, and vegetation, (such as trees, shrubs, and grass) on or adjacent to the Site, which are not to be removed and which do not unreasonably interfere with the work required under this Agreement.

Contractor shall protect from damage all existing improvements and utilities (1) at or near the Site and (2) on adjacent property of a third party, the locations of which are made known to or should be known by Contractor.  Contractor shall repair any damage to those facilities, including those that are the property of a third party, resulting from the failure to comply with the requirements of this Agreement or failure to exercise reasonable care in performing the Work.  If Contractor fails or refuses to repair the damage promptly, Company may have the necessary work performed and charge the cost against Contractor's account.

32.	Confidentiality.  It is understood that Contractor may have access, as determined by Company in its sole discretion, to confidential materials and information ("Confidential Information") of Company, its parent, subsidiaries, or affiliates in order to provide the Work hereunder.  It is further understood that Contractor will utilize the Confidential Information received by it only for the purpose of providing the Work contemplated hereunder and for no other purposes whatsoever.  In no event shall Contractor divulge any such Confidential Information to any third party without the express prior written consent of Company's Representative.  Upon termination of this Agreement, Contractor agrees not to disclose or use any Confidential Information that it may have concerning the affairs of Company, except for information that is required by Law to be disclosed; provided, however, that nothing in this Paragraph 32 shall be construed to prohibit Contractor from operating its business in competition with Company.  Contractor shall advise all recipients of Confidential Information as to the provisions of this Paragraph and their commitment to be bound by its conditions, and it is agreed that the provisions of this Paragraph shall survive the termination of this Agreement.

33.	Governing Law.  This Agreement and the rights and duties of the parties arising out of this Agreement shall be governed by and construed in accordance with the laws of the State of Texas, except provisions of that law referring to governance or construction of the laws of another jurisdiction.

34.	Controlling Provisions in Case of Conflict. In the event of any conflict or inconsistency within the various provisions of this Agreement, the Exhibits and other incorporated or associated documentation, the provisions of Part II, General Terms and Conditions of this Agreement shall control, with the exception of Exhibit A, Scope of Work, which shall be the controlling document in case of conflicts between the provisions contained in the Scope of Work and the other Exhibits to and provisions of this Agreement.

35. 	Assignment and Subcontracting. Company may assign this Agreement, in whole or in part, to an affiliate, a member, or member’s affiliate without the consent of Contractor.  Company shall notify Contractor of such assignment seven (7) calendar days prior to executing such assignment.  Contractor shall not assign this Agreement nor assign or hypothecate any payment or part of the payment which may accrue hereunder, nor subcontract the Work or any part thereof, without first having obtained written approval from Company.  In the event Company grants such approval, Contractor shall nonetheless be obligated to Company to complete the Work in the time and manner herein agreed, all in accordance with the terms and conditions hereof.  Any transfer or assignment in violation of this Paragraph 35 shall be void.

Contractor shall further cause each Subcontractor to assume and satisfy all obligations of Contractor hereunder to the full extent same may be applicable to the portions of the Work subcontracted. Contractor guarantees that its Subcontractors will comply fully with the terms of this Agreement applicable to the portion of the Work performed by them.   Contractor shall be liable for all acts and omissions of any assignee, Subcontractor, or any of their employees or agents, as if performed or omitted by Contractor. If any portion of the Work which has been subcontracted by Contractor is not prosecuted in accordance with this Agreement, on request of Company the Subcontractor shall be replaced at no additional cost to Company and shall not be employed again on the Work.

Any assignee or Subcontractor shall be subject to the confidentiality obligations of this Agreement and it shall be a condition to the granting of any assignment or subcontract that such Subcontractor shall execute a confidentiality agreement in a form acceptable to Company.

36.	Proprietary Rights.  All materials which Contractor is required to furnish, prepare or develop in the performance and completion of Work hereunder (whether delivered to Company or not), including, but not limited to, reports, plans, drawings and specifications, calculations, maps, sketches, notes, data and samples, are the sole and exclusive property of Company without limitation (except Contractor may retain a copy thereof), subject to Contractor's right to use the same to perform the Work under this Agreement.  Such materials (including all copies thereof) shall, together with any materials furnished by Company hereunder, be delivered to Company upon request and in any event upon completion or termination of this Agreement.  All such materials shall be considered to be confidential and Contractor may not disclose such materials or information provided to Contractor by Company to any third parties without Company's express consent.

37.	Contractual Rights.  The terms and provisions of this Agreement shall inure to the benefit of and be binding upon the permitted successor, assigns and representatives of the parties hereto.  Contractor agrees that the exercise of any and all rights or remedies at law or in equity against any member, member’s parent or affiliate, parent, subsidiary or affiliate of Company by Contractor, its successors, assigns and representatives, arising out of or in connection with the Work or any obligation under this Agreement, is expressly waived.  The provisions of this Agreement shall not impart rights enforceable by any person, firm or organization not a party or not bound as a party, or not a permitted successor or assignee of a party bound to this Agreement.

38.	General.

- Entire Agreement. The terms and provisions of this Agreement are intended to supersede any conflicting terms or conditions in any other agreement between the parties.  This Agreement contains the entire agreement between the parties and shall not be modified or supplemented except by written instrument duly executed by both parties.

- Severance. If any provision of this Agreement shall, for any reason, be held violative of any applicable Law, and so much of said Agreement is held to be unenforceable, then the invalidity of such a specific provision herein shall not be held to invalidate any other provisions herein, which other provisions shall remain in full force and effect.

- Survival of Provisions.  The terms and provisions of Paragraphs 6, 8, 11, 15, 18, 20, 21, 25, 26, 29, 30, 32, 33, 36 and 37 of this Part II shall survive the termination of this Agreement.

- Waiver. No waiver of any of the provisions of this Agreement shall be deemed or shall constitute a waiver of any other provisions hereof (regardless of whether similar), nor shall any such waiver constitute a continuing waiver unless otherwise expressly provided.

- Relationship of the Parties.  Nothing contained in this Contract shall be construed as constituting a joint venture or partnership between Contractor and Company.

- Further Assurances. Contractor and Company agree to provide such information, execute and deliver any instruments and documents and to take such other actions as may be necessary or reasonably requested by the other party which are not inconsistent with the provisions of this Contract and which do not involve the assumption of obligations other than those provided for in this Contract, in order to give full effect to this Contract and to carry out the intent of this Contract.

- Counterpart Execution.  This Contract may be signed in any number of counterparts and each counterpart shall represent a fully executed original as if signed by both parties.

39.  Dispute Resolution	.

39.1   Negotiation of Disputes and Disagreements.   In the event of any dispute or disagreement arising out of or relating to the implementation or performance of this Agreement, which dispute the parties hereto have been unable to settle or agree upon within a period of ten (10) days after the dispute or disagreement arises, each party shall nominate a senior officer of its management to meet at an agreed time and place not later than ten (10) days after the dispute or disagreement has arisen to attempt to resolve such dispute or disagreement.  Should a resolution of such dispute or disagreement not be obtained within fifteen (15) days after the meeting of senior officers for such purpose, either party may then by notice to the other submit the dispute to arbitration in accordance with the provisions of Paragraph 39.2.

39.2	Arbitration Resolution.  Excepting Company’s right to terminate this Agreement pursuant to Paragraph 14, any claim, dispute or controversy arising out of or relating to this Agreement, shall be submitted to binding arbitration by the Arbitration Committee of the American Arbitration Association, in accordance with the construction industry rules then in effect.  The arbitration hearing shall be held in Houston, Harris County, Texas, on at least twenty (20) business days prior written notice to the parties.   There shall be three arbitrators, with each party selecting one; the third arbitrator, who shall be the chairman of the panel, shall be selected by the two party-appointed arbitrators.  The claimant shall name its arbitrator in the demand for arbitration and the responding party shall name its arbitrator within thirty (30) days after receipt of the demand for arbitration.  The third arbitrator shall be named within thirty (30) days after the appointment of the second arbitrator.  The Arbitration Committee of the American Arbitration Association shall be empowered to appoint any arbitrator not named in accordance with the procedure set forth herein.  Each arbitrator will be qualified by at least ten (10) years experience in the natural gas and/or electric construction and engineering industry.  The decision of the arbitrators shall be final and binding upon the parties without the right of appeal to the courts.  In deciding the substance of any such claim, dispute or disagreement, the arbitrators shall apply the substantive Laws of the State of Texas; provided, however, except as is otherwise provided in this Agreement, that the arbitrators shall have no authority to award consequential damages or punitive damages under any circumstances (whether it be exemplary damages, treble damages, or any other penalty or punitive type of damages) regardless of whether such damages may be available under Texas Law, the parties hereby waiving their right, if any, to recover consequential damages or punitive damages in connection with any such claims, disputes or disagreements.  The award rendered by the arbitrators shall be final and judgment thereon may be entered by any court having jurisdiction thereof.  The costs and expenses of the arbitration (including reasonable attorneys’ fees) will be borne by the losing party, unless the arbitrators determine that it would be manifestly unfair to honor this agreement of the parties and determine a different allocation of costs.  Arbitration proceedings shall be conducted in English.

39.3	Continuation of Work.   Pending final resolution of any dispute, whether or not submitted to arbitration hereunder, Company and Contractor shall continue to fulfill their respective obligations hereunder.

40. 		Limitation of Liability.

IN NO EVENT SHALL COMPANY BE LIABLE TO CONTRACTOR, ITS SUBCONTRACTORS, VENDORS OR AFFILIATES, FOR ANY LOSSES SUFFERED BY CONTRACTOR, WHETHER DIRECT OR INDIRECT,  CONSEQUENTIAL, OR SPECIAL LOSS OR DAMAGE ARISING HEREUNDER.  CONTRACTOR SHALL NOT BE LIABLE TO COMPANY UNDER ANY CIRCUMSTANCES FOR INCIDENTAL OR CONSEQUENTIAL DAMAGES NOR FOR ANY COST OR EXPENSE THAT PROVIDES BETTERMENT, UPGRADE, OR ENHANCEMENT TO COMPANY.

PART III

INSTRUCTIONS AND INFORMATION TO BIDDERS

Bidder (Contractor) shall comply with this Part III of this Agreement in the preparation and submittal of its bid proposal.  Bidder shall complete all areas requesting information and rates, properly execute both sets of documents under Part I, General Undertakings and Obligations of the Parties hereto, and return both complete sets of documents to Company.  The requirements, which each such executed Proposal shall meet, are:

A.	IDENTITY OF BIDDER

Proposals by corporations shall be signed with the legal name of the corporation, followed by the name of the state of incorporation and by the signature and designation of the president, secretary or other person authorized to bind the corporation in the matter.  The corporate seal should also be affixed and the name of each person signing typed or printed below his signature.  When requested by Company, satisfactory evidence of the authority of the persons signing on behalf of the Bidder shall be furnished.  The full name and business address of the Bidder must be included and the Proposal must be signed with Bidder's usual signature.  Proposals by partnerships shall include the full names of all partners and shall be signed with the partnership name by one of the members of the partnership (identified as a "general partner") or by an authorized representative.

B.	CHANGES AND CORRECTIONS

Erasures or other changes in the Agreement are not allowed.

C.	ENTIRE WORK

Proposals must cover the entire Work as specified, including any addenda thereto.

D.	NOMINATION OF SUBCONTRACTOR WORK AND SUBCONTRACTORS

The Bidder must accompany the Proposal with a description of any part of the Work which the Bidder desires to subcontract and the names of proposed Subcontractors.  Acceptance of this information shall not prejudice Company's expressed right elsewhere in this Agreement to reject any such subcontracting or Subcontractors.

E.	CONSTRUCTION SCHEDULE

Bidder shall accompany the Proposal with a detailed Construction Schedule in graph or CPM form.  The Construction Schedule shall include a staffing curve and list of equipment Bidder proposes to use on the Work.

F.	SURETY

Contractor shall provide the bonds as specified in Part II of this Agreement. Contractor will submit with its proposal a commitment from a bonding agency for such bonding requirements.

G.	FINANCIAL STATEMENT

Bidder shall furnish a current financial statement to Company with its proposal.

H.	WITHDRAWAL OF PROPOSAL

A proposal may be withdrawn only by written or telegraphed request received by Company prior to the time for opening of bids announced in Company's letter of transmittal.

I.	EXCEPTIONS TO SPECIFICATIONS

Exceptions, if any, from the requirements of the specifications forming a part of this Agreement shall be specifically noted in Bidder's Proposal.

J.	INSURANCE REQUIREMENTS

Contractor shall deliver to Company at the time Contractor executes this Agreement the Insurance Certificate (or certificates) required in this Agreement, plus certified copies of permits to do business in the states in which the Work will be performed.  Such insurance certificate shall name Enron North America Corp., its respective parent and affiliated companies, and their directors, officers, employees, and agents, as additionally insured along with a waiver of subrogation clause on the certificate.  If the Contractors current insurance coverages are less than those stated minimum requirements in Part II of this Agreement, Contractor shall include in a separate cover letter the cost for the additional insurance.  Company will determine if this additional coverage is required for the project.

- PROGRESS PAYMENT SCHEDULE

A Progress Payment Schedule as specified in Exhibit "K" shall be included in Bidder's Proposal.  The Progress Payment Schedule shall outline the Company’s payments to Contractor based upon the Contractor’s expected Work progress and completion.  Exhibit K Progress Payment for Pipeline Work is intended to be Contractor's projection of the payment schedule.  Actual payments shall be made based upon the payment provisions of Part II of this Agreement.

- EXCEPTIONS TO CONTRACT PROVISIONS

Exceptions, if any, from the provisions of Part I and Part II of this Agreement shall be specifically noted in Contractor’s Proposal or deemed waived.

Company will not execute this Agreement until all of the documents required in this Part III are received by it, and shall have the right to revoke its notification of award if Bidder fails to deliver the above described documents, although Company may, in its discretion, allow a longer period of time for delivery of the indicated documents.

PART IV

PROPOSAL OF BIDDER

Contractor hereby proposes and agrees to undertake the Work as defined and specified in this Agreement for the Contract Price set forth below, as such Contract Price may be adjusted by one or more Change Orders. The Contract Price shall be Contractor’s complete bid for all costs to complete the Work and shall include provisions for all construction conditions at the location of the Work:

Docking Facilities:

Contract Price:	[Five hundred thousand Dollars]     [ $500,000]

Any Extra Work performed under the provisions of Section 8 will be performed on a cost reimbursable basis.

Contractor agrees that the above-listed Contract Price includes all sales and use taxes and other applicable taxes on materials, supplies, equipment or services involved in performing the Work. Contractor shall, where applicable, for information purposes only, separately list on its invoice(s) to Company any and all such valid sales taxes on materials, supplies, equipment or services to be provided hereunder.

The Contract Price covers and includes all of Contractor's charges to Company's account for the construction and installation of the Work under the terms of this Agreement, and shall cover and include all overhead, supervision, labor, use of equipment furnished, and all other cost and expense incurred by the Contractor in the performance of said Work.  Unless the Work performed varies materially from the Scope of Work in Exhibit A, described in the Drawings and the Specifications, there shall be no adjustment to the Contract Price.

Payment Schedule

To be furnished by Contractor as set forth in Exhibit “K”.

Subcontractors

The Contractor shall furnish with his bid a list of the names, addresses and telephone numbers of all Subcontractors Contractor intends to utilize in the performance of the Work; and the name of a principal contact for each Subcontractor.

EXHIBIT A

SCOPE OF WORK

EXHIBIT D

###### CONTRACTOR'S EXTRA WORK RATE SCHEDULE

1.  EQUIPMENT.  With respect to Extra Work - Changes as Noted in Paragraph 11 of Part II of this Agreement wherein the Contract Price shall be adjusted for applicable equipment, the individual classifications and rates for all equipment to be used for which Contractor will be compensated shall be limited to the classifications and rates listed on the Equipment Rate Schedule set forth herein by Contractor.

Such rates cover and include all charges for the use of equipment on a fully maintained basis, excluding only operating labor, but expressly including all gasoline, oil, grease and other fuel, supplies, repair parts, repair labor, taxes, license fees, rentals, supervision, overhead and profit and all other costs incident to the use of equipment to be furnished by Contractor.

2.  LABOR.  With respect to Extra Work - Changes as noted in Paragraph 11 of Part II of this Agreement wherein the Contract Price shall be adjusted for applicable labor, the individual classifications and rates for all labor to be used for which the Contractor will be compensated shall be limited to the classifications and rates listed on the Labor Rate Schedule set forth herein by the Contractor.

Such rates cover and include all charges for the use of all labor, including all applicable taxes, benefits, insurance, supervision, overhead and profit and all other costs incident to the use of such labor furnished by the Contractor.

### EXHIBIT D

EQUIPMENT RATE SCHEDULE

(To be furnished by Contractor)

Operating		Non-Operating

Description of Equipment            		Hourly Rate		Hourly Rate

EXHIBIT D

LABOR RATE SCHEDULE

(To be furnished by Contractor)

Classification            		   Hourly Rate

EXHIBIT E

MINIMUM INSURANCE REQUIREMENTS

Worker’s Compensation Insurance

Worker's Compensation and Employer’s Liability insurance providing statutory coverage A benefits and Employer’s Liability limits of $1,000,000 bodily injury by accident/$1,000,000 bodily injury by disease each employee/$1,000,000 bodily injury by disease, policy limit, in compliance with the laws of the State where all or any portion of the Work is being performed. In the event, Contractor is not a resident of Wyoming, and the performance of the Work in Wyoming will take longer than 6 months, Contractor shall be required to purchase Workers’ Compensation insurance coverage, with statutory liability limits, directly from the State of Wyoming’s monopolistic state fund.  Coverage cannot be purchased from a private insurance company or agent.  Additionally, because Employer’s Liability insurance is not available in Wyoming, Contractor must purchase a “Stop-Gap” endorsement to its Commercial General Liability policy.  Prior to performing any Work on Company’s property in Wyoming, Contractor shall provide satisfactory written evidence to Company that such Workers’ Compensation and Stop-Gap coverage are in place.

General Liability Insurance

General Liability insurance, endorsed to provide coverage for explosion, collapse and underground damage hazards to property of others; Contractual Liability (particularly the applicable provisions of the "General Indemnity" section of this Agreement); Contractors and Products and Completed Operations (for a minimum of two year after acceptance of the Work).  Watercraft exclusions deleted (if Work necessitates the use of watercraft of any kind).  Railroad liability exclusions deleted (if Work is within railroad exclusion limits).

Bodily Injury and

Property Damage		$1,000,000 Combined Single Limit Each Occurrence (Minimum)

Automobile Liability Insurance

Automobile Liability insurance which shall include coverage for all owned, non-owned and hired vehicles.

Bodily Injury and

Property Damage		$1,000,000 Combined Single Limit Each Occurrence (Minimum)

Excess Umbrella Liability Coverage

Bodily Injury and

Property Damage		$10,000,000 Combined Single Limit Each Occurrence (Minimum)

Builder’s Risk Insurance

Builder’s All Risk Insurance, at Company’s option, covering all risks of physical loss or damage to all work performed and property installed, from the start of activity including coverage for items in transit to the Site until completion. Such policy shall include coverage for the interests of the Company, Contractor and Subcontractors in the project. Contractor shall be responsible for the deductible which shall be no greater than $50,000 or whatever is commercially reasonable.

Hull and Protection and Indemnity Insurance

Hull and Protection and Indemnity insurance if the Work necessitates the use of watercraft of any kind.

Hull				Full replacement of the watercraft (Minimum)

P & I	$1,000,000 Each Occurrence or the full valve of the vessel, 	whichever is greater (Minimum)

Aircraft Liability Insurance

Aircraft Liability insurance if the Work necessitates the use of aircraft of any kind.  The policy shall be endorsed to provide coverage for non-owned aircraft as well as Guest Voluntary Settlement.

Bodily Injury and

Property Damage	$500,000    Combined Single Limit Each Occurrence (Minimum)

Additional Requirements

Contractor shall require any Subcontractor at any tier, vendor, supplier, material dealer and others connected with the Work to provide and maintain insurance at all times during the period that their agreement related to Work under this Agreements in force and effect at the Subcontractor's, vendor's, supplier's, material dealer's, or others' own cost, with insurance limits and in form and issuing companies acceptable to Company.

Contractor shall submit to Company at the time Contractor executes this Agreement, a Certificate of Insurance, in form satisfactory to Company or certified copies of the Policies if requested by the Company, evidencing that satisfactory coverages of the type and limits set forth hereinabove are in effect.  Policies providing such coverages shall contain provisions that no cancellation, non-renewal, or material changes in the policies shall become effective except on thirty (30) days advance written notice thereof to Company.  Irrespective of the requirements as to insurance to be carried as provided for herein, the insolvency, bankruptcy or failure of any insurance company carrying insurance of Contractor, the failure of any insurance company to pay claims accruing, or the inadequacy of the limits of the insurance, shall not affect, negate or waive any to the provisions of this Agreement including, without exception, the indemnity obligations of Contractor.

Contractor agrees to require any policies of insurance, except Workers Compensation coverages, which are in any way related to the Work and that are secured and maintained by Contractor or its Subcontractors, to include Company, its parent and affiliated companies, and their directors, officers, employees and agents, as Additional Insured.  Furthermore, Underwriters shall waive all rights of recovery against Company, its parent and affiliated companies which Contractor may have or acquire because of deductible clauses in or inadequacy of limits of, any policies of insurance maintained by Contractor.  All policies of insurance maintained by Contractor shall be primary and not excess or contributory with any insurance or self-insurance maintained by Company.

Contractor agrees to require all such policies of insurance which are in any way related to the Work and that are secured and maintained by Contractor or its Subcontractors, to include clauses providing that each underwriter shall waive its rights of recovery, under subrogation or otherwise, against Company, its parent and affiliated companies and their directors, officers, employees and agents.  All Policies required by the Exhibit “E” shall be purchased from insurance companies reasonably acceptable to the Company.

EXHIBIT F

###### GOVERNMENTAL AUTHORIZATIONS

EXHIBIT G

###### CONTRACTOR’S COMPLETION AFFIDAVIT

located at 												 having entered into a contract with 							      ("Company") dated 				 to construct (remove) the following:

does hereby certify that said contract has been fully and finally completed; that all labor has been fully and entirely paid; that all Federal and State Unemployment and Old Age Benefit Taxes have been paid, or will be paid when due; that all valid State Sales and Use Taxes properly levied on materials, equipment, supplies and services furnished by Contractor have been paid; that all Federal or State Income Taxes required by law to be withheld from employees or others have been withheld and remitted to the proper taxing authority, or will be remitted when due; that all premiums for insurance requirements, all claims for damages of any nature arising from the fulfillment of said contract, all materials, supplies, etc., all labor and bills for materials, supplies, etc., of any and all Subcontractors, have all been paid; that payment has been made in full of all claims for damages for which Contractor is required to indemnify Company, its parent and affiliated companies, hereunder, and that any other items payable by the Contractor under said contract have all been paid.

Contractor agrees to indemnify, save and hold harmless Company from any claims, damages, or expenses arising from Contractor's failure to perform or fulfill any of the acts or obligations referred to above.

Contractor

By

State of

County

, an individual, makes oath and says that he is representing 							 with headquarters at 												 and that he examined the foregoing statement and that it is a true and correct statement of facts in respect to each and every matter set forth therein.

Subscribed and sworn to before me this 		 day of 					 , 199	,

County 					 State.

Notary Public

My commission expires

GENERAL CONTRACTOR'S/ENGINEER'S

PARTIAL LIEN WAIVER

AND AFFIDAVIT OF PAYMENT

The undersigned has performed certain services for and/or supplied plans or materials to ___________________________________________ (“Company”) pursuant to _____________ for use in, upon, or in connection with the property and/or improvements known as the Lost Creek Gathering System (“Site”).  The legal description for the Site is as follows:

Description of Services and/or Materials/Plans Supplied to Site ("Work"):

Last Day Work Performed and/or Materials/Plans Supplied to Site:

Check No. and Amount Paid for Work Through Date of This Lien Waiver:

In consideration of the amount of money paid to the undersigned as set forth above, along with other good and valuable consideration, the receipt and sufficiency of which is hereby acknowledged, the undersigned, by its duly authorized representative, hereby:

a)	waives and releases, but only to the extent of the amount of money paid to the undersigned as indicated above, any and every lien or right to claim or file any and all mechanics' liens, claims of lien or rights of lien against the Site and/or Company, all of the past, present or future owners of the Site, and each of their respective directors, officers, agents, affiliated companies, partners, co-owners, joint venturers, lessees, lenders, successors and assigns (collectively, the "Company Group"), specifically including any right to file a lien under the laws of the State in which the Site is located, for materials or plans furnished, work, services or labor performed, or machinery, tools or equipment supplied to, upon, for use in, or in connection with the Site arising out of the Contract identified above;

b)	represents and warrants to the Company Group that: there are no threatened or pending claims, liens, security interests or encumbrances in the nature of mechanics' or materialmen's liens or otherwise arising out of or in connection with the Work; all taxes connected with the Work (other than income taxes), for which the undersigned is responsible to have been paid; and all of its Subcontractors, materialmen and any other person or entity who or which have furnished or supplied materials, plans, machinery, tools, equipment, fixtures, or apparatus, or performed work, services or labor at the instance of, under or through the undersigned, or who otherwise could claim a lien by, through or under the undersigned or in connection with the Work, have been paid in full or will be paid from the payment identified above for Work performed through the date of this Lien Waiver.

c)	shall defend, indemnify, and hold Company Group harmless against any (i) lien filed by any Subcontractor, materialman and any other person or entity who or which have furnished or supplied materials, plans, machinery, tools, equipment, fixtures, or apparatus, or performed work, services or labor at the instance of, under or through the undersigned, or (ii) loss, liability, or cost, including reasonable attorneys' fees, which Company Group may incur if any of the information given or the representations and warranties made in this Lien Waiver are untrue or alleged to be untrue; and agrees to sign such further releases and take any other actions as may reasonably be requested by Company in order to remove the Company Group and/or the Site from the cloud of any specific lien claims recorded by, for, or through the undersigned; and

d)	acknowledges Company Group's detrimental reliance on all of the foregoing.

DATE:_________________________

Name of Contractor:

By:__________________________________________________________

Name:________________________________________________________

Title:_______________________________________________________

STATE OF_________________________	)

)

COUNTY OF________________________	)

The foregoing instrument was acknowledged before me by __________________________________________________, this _______ day of ____________________________.

Witness my hand and official seal.

Notary Public____________________

My Commission Expires:_______________________

GENERAL CONTRACTOR’S/ENGINEER’S

FINAL LIEN WAIVER

AND AFFIDAVIT OF PAYMENT

The undersigned has performed certain services for and/or supplied plans or materials to ____________________________ (“Company”) pursuant to for use in, upon, or in connection with the property and/or improvements known as the Lost Creek Gathering System, (“Site”).  The legal description for the Site is as follows:

Description of Services and/or Materials/Plans Supplied to Site (“Work”):

Last Day Work Performed and/or Materials/Plans Supplied to Site:

Total Amount Paid for Work:

In consideration of the amount set forth below and for good and valuable consideration, the receipt and sufficiency of which is hereby acknowledged, the undersigned, by its duly authorized representative, hereby:

a)  waives and releases any and every lien or right to claim or file any and all mechanics’ liens, claims of lien or rights of lien against the Site and/or Company, all of the past, present or future owners of the Site, and each of their respective directors, officers, agents, affiliated companies, partners, co-owners, joint venturers, lessees, lenders, successors and assigns (collectively, the “Company Group”), specifically including any right to file a lien under the laws of the State in which the Site is located, for materials or plans furnished, work, services or labor performed, or machinery, tools or equipment supplied to, upon, for use in, or in connection with the Site arising out of the Contract identified above;

b)  represents and warrants to the Company Group that:  there are no threatened or pending claims, liens, security interests or encumbrances in the nature of mechanics’ or materialmen’s liens or otherwise arising out of or in connection with the Work; all of its Subcontractors, materialmen and any other person or entity who or which have furnished or supplied materials, plans, machinery, tools, equipment, fixtures, or apparatus or performed work, services or labor at the instance of, under or through the undersigned, or who otherwise could claim a lien by, through or under the undersigned or in connection with the Work, have been in full; all taxes connected with the Work (other than income taxes) for which the undersigned is responsible have been paid in full.

c)  shall defend, indemnify and hold Company Group harmless against all (i) lien filed by any Subcontractor, materialman and any other person or entity who or which have furnished or supplied materials, plans, machinery, tools, equipment, fixtures, or apparatus, or performed work, services or labor at the instance of, under or through the undersigned, or (iii) loss, liability, or cost, including reasonable attorneys’ fees, which company Group may incur if any of the information given or the representations and warranties made in this Lien Waiver are untrue or alleged to be untrue; and agrees to sign such further releases and take any other actions as may reasonably be requested by Company in order to remove the Company Group and/or the Site from the cloud of any specific lien claims recorded by, for, or through the undersigned; and

d)  acknowledge Company Group’s detrimental reliance on all of the foregoing.

DATE:______________________

Name of Contractor/Engineer

By:_______________________________________________________________

Name:_____________________________________________________________

Title:____________________________________________________________

STATE OF _____________	)

) ss.

COUNTY OF ___________	)

The foregoing instrument was acknowledged before me by _________________, this _____ day of ______________.

Witness my hand and official seal.

_____________________________________

Notary Public

My Commission Expires:______________________

EXHIBIT K

PROGRESS PAYMENT FOR PIPELINE WORK

Full compensation to Contractor for full and complete performance by Contractor of all the Work, compliance with all terms and conditions of this Agreement, and for Contractor's payment of all obligations incurred in, or applicable to, performance of the Work shall be the total Contract Price to be paid upon submittal of invoices in accordance with Paragraph 16 of Part II of this Agreement based upon the following schedule and completion of work:

PAYMENT SCHEDULE

| PAYMENTNUMBER | DESCRIPTION | AMOUNT | INVOICE DATE |
| --- | --- | --- | --- |
| 1 | Progress Payment #1 |  |  |
| 2 | Progress Payment #2 |  |  |
| 3 | Progress Payment #3 |  |  |
| 4 | Progress Payment #4 |  |  |
| 5 | Progress Payment #5 |  |  |
| 6 | Progress Payment #6 |  |  |
| 7 | Progress Payment #7 |  |  |
| 8 | Progress Payment #8 |  |  |
|  | Final Payment |  |  |
| CONTRACT PRICE |  |  |  |  |