Critical Path Items to Financial Closing

(See Closing List for key to acronyms)

Next conference call to discuss status:  Tuesday, April 25, 2000 (FF to distribute dial-in information)

| Issue | Responsibility |
| --- | --- |
| 1. Central Bank - Finalize Central Bank guarantee by Sponsors - Amendments to FIRCE applications - Supplementary Agreement - Status of registration of project documents with Central Bank, including approval of take-or-pay with longer makeup period - Status of registration of subdebt | - Lenders and Enron had conference call on 4/18; FF (Raciti) to distribute revised guarantee by April 23 - OPIC (Mervenne) to signoff once receive new schedule from Enron and reset first payment date - C&P (Unna) to discuss with KfW and provide comments - Enron (Lammers, Gay) to advise Lenders of any developments in discussions between Furnas and Central Bank re extended makeup period - V&E (Barquin) to forward information to FF (Raciti) |
| 2. YPF/Gas Supply - Finalize Sponsor Guarantee re gas supply - Gas Price Differential Guaranty - Status of Amendment to GasBol Transportation Agreement | - Lenders and Enron had conference call on 4/18; FF (Raciti) to distribute revised guarantee on 4/20; FF (Raciti) and C&P (Schumacher) to prepare letter to EPE re fuel supply conditions to loan by 4/25 and Enron (Lammers) to prepare letter to YPF (offer to participate) by 4/25; V&E (Lefler) to draft a Replacement Contract - V&E (Lefler) and Enron (Novak) to coordinate distribution of agreement to Lenders by 4/20 - V&E (Lefler) to advise when it will be executed |
| 3. PPA - Aditivo No. 2 - Aditivo No. 3 - Eletrobrás / Furnas consent and opinion - Force majeure relating to pipeline delays - S&W Site Visit | - Signature of Eletrobrás pending final language of the Legal Opinion - Enron (Lammers) to follow up (Legal Opinion would be on Eletrobras board agenda on 4/18 or 4/25) - Signature of Eletrobrás pending final language of the legal opinion; Enron (Lammers) to follow up (Furnas has already approved the language) - Lenders conveyed final comments to legal opinion; TF (Bonelli) to coordinate delivery of final legal opinion to Maria Aparecida; TF (Bonelli) to prepare draft of Furnas opinion based on Eletrobras opinion; Enron (Novak) to advise re whether Eletrobras will insist on comments to Consent after meeting between Banantine and Fermino - OPIC (Mervenne, Mahaffey), C&P (Shapiro) to advise KfW (Klusener) re preliminary conference call among Barquin, Shapiro, Friedlander, and O'Brien to discuss Lenders' questions re FM; Enron (Lammers) to send Lenders copy of talking paper sent to Furnas; EPE (Powell) to advise of updates upon return to office 4/24 - S&W (Barta) available for site visit in early May; OPIC (Mervenne) has prepared list of issues to be discussed at site visit in early May (e.g., stabilizers needed) (S&W to discuss with Powell and/or ISO/ONS issues re dispatch); Enron (Ayres) to coordinate call between S&W and Siemens; Enron (Gay) to arrange for execution of S&W contract before site visit |
| 4. Governmental Authorizations - Status of IBAMA permit (installation license) - Status of ANEEL letter | - Enron (Lammers) to advise Lenders when receive IBAMA permit (likely to be on the weeks of 4/17 or 4/24), impact on construction schedule, and amendments to EPC Contract - Enron (Lammers) to forward to FF (Raciti) copy of the letter that was sent to ANEEL |
| 5. Amendment to CTA - Extension of Commitments - Cleanup changes | - Enron (Friedlander) and V&E (Barquin) to give comments to Lenders on Amendment No. 1 - Lenders to review list of proposed changes sent by V&E (Rankin); after such review FF (Elorza) to distribute draft Amendment No. 2 |
| 6. Bolivian Security Documents | C&P (Sierra-Escalante) to distribute memo re step-in; conference call tentatively scheduled for 4/27 among V&E, C&P, BA, IA and FF to discuss final changes (if any) to Bolivian Security Documents |
| 7. Brazilian Security Documents | C&P (Sierra-Escalante) to distribute memo re step-in; conference call tentatively scheduled for 4/27 among V&E, C&P, BA, IA and FF to discuss final changes (if any) to Brazilian Security Documents |
| 8. Taxes - Tax issues raised by Citibank - Taxes payable with respect to subdebt | - FF (Raciti) has advised Citibank that according to PWC there is not issue - OPIC (Mervenne) to arrange call with PWC (Martin) and Enron (Hopkinson) re effect on model and whether issue can be addressed by drafting changes (i.e., if tax computed on accrual basis, can document state that interest does not accrue until interest paid?) |
| 9. Liquid Fuel Supply Contract - Translation of signed copy - Petrobrás opinion and consent | - Enron (Novak) to track down translation and send to Lenders - Enron (Novak) to arrange meeting with Petrobras to discuss Lenders' comments to consent and opinion |
| 10. Accounts Agreements - Disbursement Agreement - Cayco Accounts Agreement, TBS Shareholders Account Agreement - Interborrower Agreement | - Sponsors and counsel to provide comments to FF draft of 4/3 - FF (Raciti) to distribute - Sponsors to discuss comments of Lenders |
| 11. Equity Contribution Agreement | Three open points: - Excess Contribution Amount – Enron (Lammers) will propose amount in light of anticipated delays - Dispute resolution – OPIC (Mahaffey) and FF (O'Brien) to discuss - Indemnity language – Enron and OPIC to discuss at business level |
| 12. Amendment to OPIC Loan Agreement; Amendment to KfW Loan Agreement | V&E (Barquin) to coordinate comments from Sponsors to Amendment to OPIC Loan Agreement; C&P (Unna) to prepare draft of Amendment to KfW Loan Agreement |
| 13. Comments to Legal Opinions | Local counsel to provide comments to forms of legal opinions |
| 14. Schedules to Financing Documents | Enron (Rankin) to provide update after revised model distributed FF (Elorza) |
| 15. FOGA | FF (O'Brien) to distribute revised draft incorporating V&E comments; [Enron (Friedlander) and V&E (Rankin) to discuss Citibank comments of 4/6] |
| 16. Insurance | Enron to advise how much coverage for insurance will cost as it expires in April 2001 |
| 17. U.S. Security Documents | Two points: - Sponsors and their counsel to provide comments to 3/3 drafts distributed by C&P - C&P (Unna) to distribute remaining U.S. Security Documents |

Ancillary List to the Critical Path Items to Financial Closing

(See Closing List for key to acronyms)

| Issue | Responsibility |
| --- | --- |
| 1. YPF/Gas Supply - YPF Consent (B) Andina due diligence (C) Amendment to YPF Gas Supply Agreement | - Enron (Lammers) to arrange call/meeting with YPF and Lenders to discuss pending issues – week of 4/24 - OPIC (Mervenne) and FF (Raciti) to confirm that Andina consent has covenants re dedication of reserves; Enron (Lammers) to follow up with Andina re missing information for due diligence - Enron (Lammers) to find out if YPF willing to sign now if not already signed |
| 2. PPA (A) Performance bond | - Enron (Lammers) has advised that performance bond needs to be amended only if increase diesel operation to 300 MW |
| - Liquid Fuel Supply - Environmental issues - Governmental Approvals required in connection with possible increase in diesel usage - Status of need for amendment | - OPIC (Mervenne) to follow up with Moss re compliance with World Bank Guidelines and OPIC Handbook in connection with proposed increase in diesel fuel consumption - TFTS and TRW to advise Lenders re additional permits required for 300 MW on diesel; Enron to advise re status of obtaining same [NB. This will be moved to critical path items list depending on outcome of force majeure claims submitted to Furnas.] - Enron (Lammers) confirmed that none needed for extended diesel usage |