To:	CalPX Participants

From:	PXCC

RE:	PXCC Notice 00-61 – Revised Stage 6.7 Production Implementation Schedule

# Date:	October 25, 2000

- SUMMARY OF STAGE 6.7 PRODUCTION IMPLEMENTATION*

- *Schedule Subject to Change

- DATE				Previous STAGE		        Stage 6.7 STAGE

| Wednesday Oct 25 (Prior to Day-Ahead Finals being published) | - Day-Ahead production run for dispatch date Thursday Oct 26 - Day-of Market Bids (including Supplemental Bids) for dispatch date Wednesday Oct 25 | - No Activity |
| --- | --- | --- |
| Wednesday Oct 25 Day-Ahead: (After Day-Ahead Final schedules, AS Reservations and Zonal Prices are posted) | - (Estimated to be approximately 14:00) Day-Ahead closes on the Previous environment | - (14:00) Connectivity testing - (14:00) Day-Ahead Market opens on Stage 6.7 environment to receive Day-Ahead Standing Bids for dispatch date Friday Oct 27 |
| Wednesday Oct 25 Day-Of: | - (14:30) HA Market will be closed for dispatch date Wednesday Oct 25, HE 19 - 24 adjustment and AS bids - (14:30) Supplemental Bids market will be closed for dispatch date Wednesday Oct 25, HE 17 - 24 Supplemental Bids | - (16:00) First Day-Of Block Auction on Stage 6.7 environment for Hours Ending 1-10 for dispatch date Thursday Oct 26 |

Switch Over to the STAGE 6.7 Stage

- DATE				Previous STAGE		       Stage 6.7 STAGE

| Thursday Oct 26 Day-Ahead: | - No Activity - No longer running on the previous stage | - Day-Ahead production run - (07:00) – First Day-Ahead auction performed in Stage 6.7 environment for dispatch date Friday Oct 27 |
| --- | --- | --- |
| Thursday Oct 26 Day-Of: | - No Activity - No longer running on the previous stage | - (06:00) Second Day-Of Block Auction on Stage 6.7 environment for Hours Ending 11-16 for dispatch date Thursday Oct 26 |

Breakdown of Wednesday Oct 25 Events

14:00 – After Day-Ahead Final Schedules for dispatch date Thursday, Oct 26 have been published, Stage 6.7 Day-Ahead Market will be open for participants to submit standing bids for dispatch date Friday, Oct 27

14:30 – Last Day-Of Adjustment, Ancillary Service Bids for Hour Ending 19 through 24 and Supplemental Bids for Hour Ending 17 through 24 for dispatch date Wednesday, Oct 25 due on the Previous Stage

16:00 – CalPX shall calculate the First Day-Of auction, and publish the auction results for Hours Ending 01 through 10 for dispatch date Thursday, Oct 26 on Stage 6.7

Between 16:00 and 18:00 – Day-Of Final Schedules and Ancillary Services Reservation Schedules for Hour Ending 19 through 24 for dispatch date Wednesday, Oct 25 shall be published to participants on the Previous Stage

Between 18:00 and 21:00 – ISO SI will be shut down completely for the upgrade.  PX will not upload any schedules to the ISO and will NOT accept any schedules during this time

20:45 – Login to the ISO’s conference call at 888-837-2407 (Passcode #722248) for implementation status (If you miss the call, you may also call the PX at 800-464-8831 Option #5 for a status summary)

21:00 – After the ISO successfully upgrades to the new system, PX will open market for all Day-Of bids (including Supplemental Bids) for dispatch date Thursday, Oct 26 and Day-Ahead standing bids for dispatch date Friday, Oct 27

21:45 – First Adjustment and Ancillary Services bids for Hour Ending 01 for dispatch date Thursday, Oct 26 due on Stage 6.7

Note

- Per the ISO, Load and/or Generation Transfers should NOT be scheduled for any Day-Of Market (Hour Ending 1 - 24) for dispatch date Thursday, Oct 26

- Only FIXED TRADES should be scheduled for Day-Of Markets for dispatch date Thursday, Oct 26

- Load and/or Generation Transfers can be scheduled beginning with the Day-Ahead Market for dispatch date Friday, Oct 27

- All times denoted are in PPT