Promising Gas Options OII – I.99-07-003

Schedule For PG&E Tariffs

June 20, 2000

| Date | Action |
| --- | --- |
| June 20, Tuesday | PG&E sends Workshop Issues List to Parties |
| June 23, Friday | PG&E sends revised Tariff Package and Responses To Issues to Parties, except Metering |
| June 28, Wednesday | PG&E sends revised Metering Tariffs and Responses To Metering Issues to Parties |
| June 30, Friday | Parties submit Final Comments on Tariff Package |
| June 30, Friday, 10:00 a.m., Room 301b, 77 Beale St., SF | PG&E Hosts Half-Day Workshop on Metering Issues |
| July 6, Thursday, 1:30 p.m., Room 301b, 77 Beale St., SF | PG&E Hosts Half-Day Tariff Workshop on any Unresolved Issues (Commission Meeting in Morning) |
| July 17, Monday | Advice Letter Compliance Filing with the CPUC |
| August 7, Monday | Protests on Compliance Filing Due (20 days after Advice Letter filed) |
| August 14, Monday | Response to Protests Due (5 business days after protests received) |
| Late August | PG&E (or Energy Division) Hosts Workshop on Compliance Tariffs, if needed |
| Mid to Late September | CPUC Issues Resolution approving tariffs |
| Early October | PG&E submits final Compliance Tariffs effective October 1 pursuant to the Resolution |
| October 1, 2000 | Tariffs Effective for Gas OII Settlement (depending on approval timing, this date could slip, but needs to be the first day of a month, e.g. November 1, 2000) |