Promising Gas Options OII – I.99-07-003

Estimated Schedule For OII and PG&E Tariff Preparation

April 14, 2000

| March 28, Tuesday |  | PG&E sends pro-forma OII Settlement tariffs to parties. |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| April 3, Monday |  | Southern California Settlements: SCGC/TURN, Support for Interim Settlement, and principles for a SoCalGas/CAC/et al Settlement. |  |  |  |  |
| April 6, Thursday |  | PG&E CPAG Meeting. |  |  |  |  |
|  | April 10, Monday |  | PG&E Workshop on Draft OII Tariffs. |  |  |  |
| April 11, Tuesday |  | Prehearing Conference, 10:00 a.m. |  |  |  |  |
| April 17, Monday |  | SoCalGas/CAC/et al Settlement expected to be filed. |  |  |  |  |
| End-April |  | ALJ issues PD for approval of PG&E's OII Settlement. |  |  |  |  |
| April 24, Monday |  | Prehearing Conference, 10:00 a.m. |  |  |  |  |
| May 5, Friday |  | Opening Testimony for SoCalGas |  |  |  |  |
| May 19, Friday |  | Rebuttal Testimony for SoCalGas |  |  |  |  |
| May 24, Wednesday |  | Motions to Strike and Witness Lists |  |  |  |  |
|  | May 25, Thursday |  | PG&E sends revised tariff package to Parties. |  |  |  |
| Late-May |  | Comments and Reply Comments on PD |  |  |  |  |
| May 30, Tuesday |  | Pretrial Hearing |  |  |  |  |
| May 30 to June 9 |  | Evidentiary Hearings |  |  |  |  |
| Mid to Late June |  | Briefing |  |  |  |  |
|  | June 20, Tuesday |  | Parties provide comments on draft PG&E tariffs. |  |  |  |
|  | June 27, Tuesday |  | Meeting in San Francisco to review comments on draft PG&E's tariffs. |  |  |  |
| Mid to Late June |  | PG&E OII Settlement on Commission Agenda (and approved). |  |  |  |  |
|  | TBD |  | PG&E sends final compliance filing package to Parties for final review. |  |  |  |
|  | TBD |  | Parties provide final comments. |  |  |  |
|  | TBD |  | Meeting in San Francisco to finalize tariffs. |  |  |  |
| Mid to Late August |  | PG&E Compliance Tariff Filing (60 days from Decision). |  |  |  |  |
| Early September |  | Protests and Replies on Compliance Filing due. |  |  |  |  |
| Late September or Early October |  | Commission approval of Tariffs to Implement PG&E Gas OII Settlement |  |  |  |  |
| November 1 or December 1 |  | Tariffs effective for PG&E Gas OII Settlement |  |  |  |  |