DRAFT OREGON TIMELINE—Not reviewed NNG

|  | Action | Responsible | participants |
| --- | --- | --- | --- |
| 10.19 | Meeting in Salem with OPUC Staff and customer groups | Susan Ackerman, Carla Kelley | Ackerman, Kelley, Pamela Lesh, Paul Kaufman, Mike Morgan, NNG Counsel, Jay Dudley |
| 10.19 | Draft portions of OPUC testimony and application due | Ackerman, Kelley, Morgan, NNG Counsel. Witnesses: Dick Reiten, Mark Dodson, Bruce DeBolt, Peggy Fowler. | State Team: Ackerman, Kelley, Lesh, Kaufman, Morgan, NNG Counsel, Dudley |
| 10.29 | Draft Remaining Portions of testimony due | NNG Counsel and Morgan | ‘’ |
| 11.07 | File OPUC testimony and applications | ‘’ | ‘’ |
| 11.07 | Open Data Room | ‘’ | ‘’ |
| 11.23 | OPUC Pre-Hearing Conference | ‘’ | ‘’ |
| 11.30 | OPUC Public Meeting | ‘’ | ‘’ |
| 12.19--DEADLINE FOR OPUC, WUTC, SEC, FERC FILINGS |  |  |  |
| 02.01.02 | OPUC Staff and Intervenors Reply Testimony Due | ‘’ | ‘’ |
| 02.22. | OPUC—NNG/PGE file Rebuttal |  | ‘’ |
| 02.25 – 03.01. | Settlement Conferences | ‘’ | ‘’ |
| 03.04 – 03.08. | Hearings | ‘’ | ‘’ |
| 03.22 | Concurrent Opening Briefs | ‘’ | ‘’ |
| 04.05 | Concurrent Reply Briefs | ‘’ | ‘’ |
| 04.30 | OPUC Decision | ‘’ | ‘’ |