Tasking Letter

TECHNICAL SERVICES

PART I - REQUIREMENTS

- The Contractor is required to provide services for the performance of the Scope of Services herein described:

# Prepare Cost estimates for the following cases

- Assume a SPAR at MC 538 and a fixed shelf platform receiving host

- Assume a pipeline MAOP of 2200 psi unless PCS significant reason for change

- Assume a 1300 psi receiving pressure for Cases 1-3

- ** Note: Murphy has assumed 12” SCRs for both oil and gas…Murphy would be interested to know if there is significant savings with smaller sizes.

- Include a list of components to be included at both SPAR and receiving host (metering, chemical injection, pigging, hull piping, SCR, etc.)

- Calculate and document expected operating pressures at the Medusa facility for 40 MBOPD in Case 3 and 60, 80, 110 MMSCFD in Case 1 (same pipe size for all three gas volumes)

Cases

- 110 MMSCFD gas pipeline from MC 538 to WD 152

- 110 MMSCFD gas pipeline from MC 538 to WD 143

- 40 MBOPD oil pipeline from MC 538 to WD 143 (note maximum allowable oil throughput in the designated line size).

- Oil pipeline one incremental line size up from Case 3 from MC 538 to WD 143 (note maximum allowable oil throughput)

# Prepare Proposed installation schedule for Cases 1 and 3

Include time allotments for permitting, route surveys, engineering, design, materials procurement, offshore installation of prelays (plan for 6/02), SCR hook-up from prelaid pipelines to SPAR

Resume of PCS’s deepwater pipelines (designed and or installed)

Include dates that pipelines were installed

Briefly describe recommended plans for corrosion protection and future surveys for both the pipelines and their associated SCRs.

Note: Company will prepare the maps involved.

- Scope of Services under this Tasking Letter are to be performed at: Contractor’s Offices

- Scope of Services under this Tasking Letter will commence on March 7, 2001.  Contractor shall use all reasonable efforts to complete the services by                 , unless sooner terminated or suspended in accordance with the provisions of the Agreement.

- The Company requires that the Scope of Services include:  (Describe any other requirements for the intended performance.)

# PART II - TERMS AND CONDITIONS

The terms and conditions of this Tasking Letter are as set forth in the Professional Services Agreement between Enron North America Corp. and Project Consulting Services, Inc. with the Effective Date of March ___, 2001 (the “Agreement”) and this Tasking Letter is subject to the Agreement.  THE AGREEMENT INCLUDES TERMS, CONDITIONS AND PROVISIONS, AND THIS TASKING LETTER INCLUDES TERMS, CONDITIONS AND PROVISIONS BY INCORPORATING THE TERMS AND CONDITIONS AND PROVISIONS OF THE AGREEMENT, THAT OPERATE TO MODIFY THE LEGAL RIGHTS AND OBLIGATIONS OF THE PARTIES.  In addition to the terms and conditions of the Agreement, Contractor and Company agree as follows with respect to this Tasking Letter:  (Describe the payment terms and conditions for the Scope of Services under this Tasking Letter.)

PART III – COMPENSATION FOR SERVICES

Contractor shall be paid for the Services in accordance with the Fixed Rates manner (hourly or daily) for type or classification of person or skill level, as set forth in Section 4.1.1 of the Agreement.

ENRON NORTH AMERICA CORP.

By:	__________________________________

(Signature)

Name:	__________________________________

Title:	__________________________________

Date:_______________

[more signatures on next page]

Contractor hereby accepts the above Tasking Letter and price as described and/or amended herein.  Contractor shall commence performance (as indicated above or on a specific date).

PROJECT CONSULTING SERVICES, INC.

By:	__________________________________

(Signature)

Name:	__________________________________

Title:	__________________________________

Date:_______________