PRIVILEGED AND CONFIDENTIAL

ATTORNEY WORK PRODUCT

| TO: | Mark Haedicke Sheila Tweed Cc: Chris Calger, Jake Thomas | DATE: | February 16, 2001 |  |
| --- | --- | --- | --- | --- |
| FROM: | Dale Rasmussen | DEPARTMENT: | Legal Department |  |
| SUBJECT: | Legal Risk Analysis – Turbine Acquisition |  |  |  |

Nature of Transaction:	Purchase of GE 7FA turbine for deployment at Project Columbia (Longview, Washington) generating facility.

Amount at Risk:	Overall purchase price of $39,200,000, with approx. $4 million at risk at signing.

Legal Risks:	Legal Risk Rating = 1 (1=low risk; 5=high risk).

Risk	Mitigation/Comments

1.  Failure to Close	$4 million is non-refundable if the parties fail to reach agreement on final Contract of Sale.  Risk is mitigated by course of dealing between ENA and GE, by using master form purchase agreement negotiated between ENA and GE during past 6 months (and references to Pastoria and Blue Dog agreements) as base document, and by imposing a reasonable/good faith negotiation obligation on parties.

2.  Development Risks	Project Columbia has substantially negotiated site control documents that should be signed before March, 2001, and has made substantial progress on permitting, gas transmission, electrical transmission/interconnect, water discharge and water supply arrangements.  No fatal flaws have been identified to date.  Final confirmation of these key inputs is uncertain at this time, however.  Exit strategies involving sale of project are being evaluated, and include a non-binding letter of intent with McCook Metals for the potential purchase of the project.  If the project is not developed the turbine should be readily deployable to another project given current market conditions.

3.   Compressed negotiating schedule	Extremely compressed schedule for committing to turbine purchase.  No time to negotiate complete documentation for purchase, or to confirm all development inputs for project prior to commitment.  Mitigated by reference to master form turbine contract and attached term sheet as basis for negotiation and by ability to re-deploy to other projects.

4.  Other	Front-end payments are higher than would normally be expected.  Project is obligated to negotiate exclusively (6 month term) with GE for provision of long-term service agreement and water treatment system, and non-exclusively for steam turbine and generators.  Attempting to remove obligation regarding water treatment system, which would potentially delay construction schedule.