4-1. Investment Merits of Project LV

Strategic Location

- Project LV is located in North Las Vegas, Nevada, 5 miles from Las Vegas, the fastest growing city in the United States

- The Nevada power market will open for many classes of customers on November 1, 2000, creating a range of opportunities to sell excess power and ancillary services

- Given the projects’ strategic proximity to Mead, Nevada and the SP-15 California market, it will have the optionality to sell merchant power into multiple markets

Existing Merchant Capacity Anchored by Existing PPA

- LV Cogen enjoys the financial stability associated with an anchor PPA and the upside of selling excess megawatts into nearby power markets

PPA Restructuring

- Enron North America has had several conversations with Nevada Power, who has expressed an interest in granting LV Cogen delivery point flexibility

- Renegotiation would give LV Cogen the optionality to fulfill its obligation under the PPA either through market purchases or self-generation

Expansion in Advanced Stage of Development

- Enron North America is in the advanced stages of development of LV Cogen II

- LV Cogen II’s Air Permit was deemed complete by the Air Pollution Control District on June 9, 2000

- Enron North America expects approval of the Air Permit by November 2000

- Turnkey construction bids have been submitted and a limited notice to proceed will be issued on September 1, 2000

Firm Commitment for Turbine Schedule

- The contract for the LM 6000s turbine has been signed with GE and they will be delivered to allow for a March 2002 commercial operations date

- As availability of turbines is expected to be severely limited during the next few years, any project under development without firm rights to equipment is at risk of substantial delays

Significant Barriers to Entry

- ENA believes that there are significant barriers that confront any potential power plant development in the region, including

- access to water rights

- air quality standards

- access to industrially zoned property and existing transmission interconnections and substations

- availability of turbines

- environmental concerns