##### Strictly Confidential

##### INDIA BUSINESS UNIT

Day 1-2: The Announcement (external)

India is 10.5 hrs ahead of CST (3:30 p.m. in Houston is 2:00 a.m. in Mumbai)

| CORPORATE FOCUS (SELLER) |  |  |  |
| --- | --- | --- | --- |
| Action | Description | Responsibility | Timing |
| # Issuing of Press Release | Distribution to identified list of media contacts in Houston and Business Unit offices | Corp. PR / BU PR team | Day of Announcement, between 3:00 and 4:00 p.m. (CST) |
| # Analyst & Media Call in Houston | Key players would discuss details of the transaction to the media (option: KL alone or KL, JS/JS) | Corp. PR | Day of Announcement Between 3:00 and 4:00 p.m. (CST) |
| Newsroom | On-line distribution of press release and a few standard FAQs: Business Unit and Corp. website | Corp. PR / BU PR team | Day of Announcement, one hour after release |
| INDIA BUSINESS UNIT FOCUS (BUYER) |  |  |  |
| ###### Action | Description | Responsibility | ###### Timing |
| Spokesperson | These individuals need: - Message - Q&As - Mumbai spokespersons handle local media inquiries re specific India issues - Houston spokespersons international media inquires re specific India issues - Media inquiries re all other issues referred to Corp. spokespersons | ## Mumbai (local) - Sanjay Bhatnagar - Jimmy Mogal ## Houston (international) - John Ambler - Johan Zaayman Enron Corp. # Mark Palmer - Karen Denne | On-going |
| Stakeholders (in priority) - Chief Minister and state Energy Minister (Mumbai) - Chairman of MSEB and President of DPC (Mumbai) - Ministers of Power and Natural Gas (New Delhi) - Representatives of GE and Bechtel (Mumbai) - Key political leaders e.g. Sharad Pawar of National Congress Party - Others such as key lenders, customers, govt. officials | Personal visits and / telephone calls by Enron India CEO and management Personal visit by Sanjay Bhatnagar plus personal letter from Joe Sutton Personal visit by Sanjay Bhatnagar plus personal letter from Joe Sutton Personal visit by Wade Cline and Ashok Mehta Personal letter from Joe Sutton / Sanjay Bhatnagar with follow up call Personal visits and / or letters Personal visits and / or letters | Below individuals and India PR team Jane Wilson & Sanjay Bhatnagar Jane Wilson & Sanjay Bhatnagar Ashok Mehta & Wade Cline Jane Wilson and Sanjay Bhatnagar Jane Wilson and Sanjay Bhatnagar TBD | Set up appointments with relevant stakeholders two days prior to release Day after Announcement - Mid morning As above Day after Announcement - Mid morning Day after Announcement Day after Announcement Day after Announcement |

Week One:

| INDIA BUSINESS UNIT FOCUS (BUYER) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action | Description | Responsibility |  | Timing |
| Q&A update | Update internal Q&As for India | India PR team |  | On-going |
| News room | If applicable update FAQs: Enron India and Corp. website | Corp. PR/BU PR |  | On-going |
| Spokesperson (process continues) | These individuals need: - Repeated/updated messages - Q&As - Mumbai spokespersons handle local media inquiries re specific India issues - Houston spokespersons international media inquires re specific India issues - Media inquiries re all other issues referred to Corp. spokespersons | ## Mumbai (local) - Sanjay Bhatnagar - Jimmy Mogal ## Houston (international) - John Ambler - Johan Zaayman Enron Corp. # Mark Palmer ## Karen Denne |  | On-going |
| Action | Description | Responsibility |  | Timing |
| Stakeholders Other lenders, partners, govt. officials and Head of Business Associations such as CII, FICCI, US-India Chamber | Personal visit and / or contact secondary stakeholders (deliver letter, phone call) | CEO and Top Management, India PR team |  | Second, third and fourth day after announcement |
| Media tracking | Track all news stories on wire services, TV, etc Distribute clips to India leadership team, copy to Enron Corp. | India PR team |  | Daily after announcement |
| Interviews in country, e.g. 1. Economic Times - Business India - Others, where applicable | Local interviews conducted with CEO and other spokespersons. | India PR team to coordinate, Sanjay Bhatnagar |  | Second day and during week of announcement |
| Stakeholder reaction | Evaluation from management team on their findings and reaction by stakeholders to new entity. Determine whether a visit by Corp. or Joe Sutton is needed to meet with key partners or other stakeholders. | Top Management and India PR team |  | Second day and during week of announcement |

Day 1-2: The Announcement (internal)

| CORPORATE FOCUS (SELLER) |  |  |  |
| --- | --- | --- | --- |
| Action | Description | Responsibility | Timing |
| Voice mail – notification of all employee meeting (Houston employees) | Message from Enron Corp CEO and / or Newco CEO | BU, Corp PR & HR, Ken Lay or Joe Sutton | Day of Announcement (Prior to release – exact time TBD) |
| Email – employee notification (All Houston and international employees) | Message from Enron Corp CEO and / or Newco CEO. Include employee Q&As | BU, Corp. PR & HR, Ken Lay and / or Joe Sutton | Day of Announcement (Coincide with release) |
| All employee meeting (possible, tele conferencing, webcasting, video) (All Houston employees and international employees) | Briefing to employees Enron Corp CEO and / or Newco CEO, defining benefits of the transaction | Corp, BU PR &HR, Ken Lay and / or Joe Sutton | Day of Announcement (One hour before or after release) |
| INDIA BUSINESS UNIT FOCUS (BUYER) |  |  |  |
| Action | Description | Responsibility | Timing |
| Business Unit Management Team briefing | Management Team briefed in confidence by BU CEO about deal and upcoming internal and external communication roll-out | Sanjay Bhatnagar, HR, PR | Day of Announcement (Five hours prior to release) Approx. 9:00 p.m. IST |
| In country employee meeting in Mumbai with teleconferencing or video link to New Delhi / Bangalore Ahmedabad | CEO to meet with employees, defining benefits of the transaction. Answer general questions re deal and HR issues | # Top Management and HR | # Day after announcement (Seven hours after release) Approx. 9:00 a.m. IST |
| Action | Description | Responsibility | Timing |
| Feedback forum including eSpeak by Joe Sutton and HR | Collect suggestions, ideas, etc. from employees (could be a web-based tool). Enron intranet used for updates, new leadership details and policies. | Corp PR, India PR team, HR, Joe Sutton, Sanjay Bhatnagar | Rest of week (next five days) |