ENRON DIRECT CANADA

# RETAIL ACTION PLAN

|  | ISSUE | PRIORITY | RESPONSIBILITY | TIME NEEDED | DEADLINE | STATUS |
| --- | --- | --- | --- | --- | --- | --- |
|  | ## Credit Sign-Off |  |  |  |  |  |
|  | ## ATCO – Gas R11 | H | Bradford | N/A | N/A | Done |
|  | ## ATCO – Gas R13 | H | Bradford | N/A | N/A | Done |
|  | ## ATCO – Power | H | Bradford | N/A | N/A | Done |
|  | ## Utilicorp – Power | H | Bradford | N/A | N/A | Done |
|  | ## Enmax – Power | H | Bradford | N/A | N/A | Done |
|  | ## Epcor – Power | H | Bradford | N/A | N/A | Done |
|  | ## Lethbridge, Red Deer and Ponoka | H | Bradford | N/A | N/A | Done |
|  | ## Guarantees v. L.C.s | H | Bradford/Milnthorp/ Powell | 1 Month | Post EES Canada | Outstanding |
|  | ## Contract Form |  |  |  |  |  |
|  | ## Gas R11 | H | Powell | N/A | N/A | Done |
|  | ## Gas R13 | H | Powell | N/A | N/A | Done |
|  | ## Gas Residential (for licensing purposes) | L | Powell | 1 Month | May 1 | Need to Update Form |
|  | ## Power (-250 MWh/yr) | H | Powell | N/A | N/A | Done |
|  | ## Power (+250 MWh/yr) | H | Powell | N/A | N/A | Done |
|  | ## MTM |  |  |  |  |  |
|  | ## Boardwalk (Signed Amended Agreement) | H | Joslyn | N/A | N/A | ENA Done |
|  | ## Calgary Winterclub | L | Joslyn | 1 Month | May 1 | Needs to be Reviewed |
|  | ## Co-op | L |  |  |  |  |
|  | ## Others (?) | L |  |  |  |  |
|  | ## Gas Contract R11 | H | Joslyn | N/A | N/A | Done |
|  | ## Gas Contract R13 | H | Joslyn | N/A | N/A | Done |
|  | ## Power Contract (-250 MWh/yr) | H | Joslyn | N/A |  | Done |
|  | ## Power Contract (+250 MWh/yr) | H | Joslyn | N/A |  | Done |

|  | ISSUE | PRIORITY | RESPONSIBILITY | TIME NEEDED | DEADLINE | STATUS |
| --- | --- | --- | --- | --- | --- | --- |
|  | ## Execution of Terms and Conditions – WSPs |  |  |  |  |  |
|  | ## ATCO - Gas R11 | M | Powell/Joslyn | N/A | N/A | Postponed |
|  | ## ATCO – Gas R13 | M | Powell/Joslyn | N/A | N/A | Postponed |
|  | ## ATCO – Power | H | Powell/Joslyn |  |  | Done |
|  | ## Utilicorp – Power | H | Powell/Joslyn |  |  | Done |
|  | ## Enmax – Power | H | Powell/Joslyn |  |  | Done |
|  | ## Epcor – Power | H | Powell/Joslyn |  |  | Done |
|  | ## City of Lethbridge | H | Powell/Joslyn |  |  | Done |
|  | ## City of Red Deer | H | Powell/Joslyn |  |  | Done |
|  | ## Town of Ponoka | H | Powell/Joslyn |  |  | Done |
|  | ## Others | L | Powell/Joslyn |  |  | Done |
|  | ## Without Prejudice Letters | H | Powell | 3 Days | April 3 | Done |
|  | ## Execution/Submission of Retail Service Agreements | H | Powell/Joslyn | 3 Days | April 3 | Executed by ED Not the WSPs |
|  | ## Posting of LCs and Parental Guarantees (as required) | H | Powell/Joslyn | 10 Days | April 10 | Some Modification Required |
|  | ## Market Participation Issues |  |  |  |  |  |
|  | ## EDC PPoA Participation |  | Joslyn |  |  | Done |
|  | ## EDC NOVA Account |  | N/A | N/A | N/A | N/A |
|  | ## TA Agreements |  | Joslyn | 1 Week | April 6 | ##### Confirmed N/A |
|  | ## Other |  | N/A | N/A | N/A | N/A |

|  | ISSUE | PRIORITY | RESPONSIBILITY | TIME NEEDED | DEADLINE | STATUS |
| --- | --- | --- | --- | --- | --- | --- |
|  | ## TXU Lease/Office Move |  |  |  |  |  |
|  | ## Walkthrough | M | Joslyn | N/A | March 30 | Done |
|  | ## Insurance | M | Lawrick |  |  | Done |
|  | ## Payments to TXU and Cadillac Fairview | M | Dalgleish |  |  | Done |
|  | ## Copier/Fax | L | O’Neil |  | April 15 | Done |
|  | ## Telecom Link | H | Todd |  | April 15 | Done |
|  | ## Network Link | H | Todd |  | April 15 | Done |
|  | ## Phone System | H | Todd |  | April 15 | Done |
|  | ## Printers ($8K) | M | Joslyn/Todd |  | April 15 | Done |
|  | ## Enron Signage | L | Brian |  | April 15 | Done |
|  | ## Amending Terms and Conditions – WSPs and Distribution Companies (De-enrollment/Termination, Guarantee of Customer Obligations, ATCO Gas Option, Others) |  |  |  |  |  |
|  | ## ATCO – Gas R11 – Need ATCO/EUB Approval | H | Powell/Hemstock/ Huber | 1 Month | May 1 | Issues Identified and Summarized – ATCO Gas South Hearing on June 5th – Send Letter in Advance of Hearing Outlining Issues May 22nd Hearing Scheduled |
|  | ## ATCO – Gas R13 – Need ATCO/EUB Approval | H | Powell/Hemstock/ Huber | 1 Month | May 1 | Issues Identified and Summarized – ATCO Gas South Hearing on June 5th – Send Letter in Advance of Hearing Outlining Issues May 22nd Hearing Scheduled |
|  | ## ATCO – Power | H | N/A | N/A | N/A | Done |
|  | ## Utilicorp – Power | H | Powell/Huber | None | June 1 | EUB Hearing decision pending Agreement by Utilicorp |

|  | ISSUE | PRIORITY | RESPONSIBILITY | TIME NEEDED | DEADLINE | STATUS |
| --- | --- | --- | --- | --- | --- | --- |
|  | ## Enmax (Lethbridge, Red Deer, etc.) – Power | H | Hemstock/Powell | 1 Month | June 1 | Meeeting held April 26th – Powell to provide mark-up |
|  | ## Epcor (Ponoka, etc.) – Power | H | Hemstock/Powell | 1 Month | June | Issues Identified and Summarized – Attempting to Identify Contact |
|  | ## Licensing Requirements |  |  |  |  |  |
|  | ## Amendment to Gas License (Resubmission) | L | Powell/Joslyn | 6 Weeks | June 15 | Resubmit |
|  | ## Power License (Contract Bond Marketing Materials) | H | Deyholos/Joslyn |  |  | Done |
|  | ## Hearings |  |  |  |  |  |
|  | ## ATCO – Gas Hearing (Sale of Production Assets) | M | Huber/Hemstock/Vetsch | Board Process | May 1 | Filed Argument – Awaiting Decision |
|  | ## ATCO – GCRR Methodology (Hedging) | M | Huber/Hemstock | Board Process |  | Hearing Completed – Drafted Argument |
|  | ## ATCO – Gas Hearing (Unbundling) | M | Huber/Hemstock | Board Process |  | Filed Evidence – Hearing May 22nd |
|  | ## Regulatory Staff |  |  |  |  |  |
|  | ## Interim Solution | H | Hemstock | 1 Week | April 9 | Done |
|  | ## Permanent Solution | H | Hemstock | 1 Month | May 1 | Done |

|  | ISSUE | PRIORITY | RESPONSIBILITY | TIME NEEDED | DEADLINE | STATUS |
| --- | --- | --- | --- | --- | --- | --- |
|  | ## Legal Staff |  |  |  |  |  |
|  | ## Interim Solution | H | Keohane | N/A | N/A | Haedicke Approved - Powell Dedicated |
|  | ## Permanent Solution | M | Keohane | 1 Month | May 1 | Done |
|  | ## Customer Target/Database/Prioritization |  |  |  |  |  |
|  | ## Wholesale/Retail “Customer Split” | H | Cross/Milnthorp | 1 Week | May 10 | In Progress |
|  | ## Gas | H | Cross/Dickin/Frers | 1 Month | May 1 | Segmented |
|  | ## Power | H | Cross/Dickin/Frers | 1 Month | May 1 | Segmented |
|  | ## Formalized Credit Process | H | Conwell/Cross | 1 Month | May 10 | Need Sign-off |
|  | ## Credit Pre-approval/Pre-screening | H | Cross/Conwell | 1 Month | May 10 | Commence Early April |
|  | ## Trademark(s) Registration/Domain Registration |  |  |  |  |  |
|  | ## The Power of Choice | L | Powell | 1 Month | May 1 |  |
|  | ## The Power to Choose | L | Powell | 1 Month | May 1 | Confirmation of Approximate Costs Coming from Donahue, Ernst & Young |
|  | ## Freedom to Choose | L | Powell | 1 Month | May 1 |  |
|  | ## “E” Trademark | L | Powell | 1 Month | May 1 |  |
|  | ## Enron | L | Powell | 1 Month | May 1 |  |
|  | ## “Endless Possibilities” | L | Powell | 1 Month | May 1 |  |
|  | ## Enron Direct Website | L | Cross/Watermark | 1 Month | May 1 | Retaining Watermark |
|  | ## Marketing Materials |  |  |  |  |  |
|  | ## Gas | M | Watermark | April 3 | April 23 | Gas Brochure Done – Direct Mailout May 14 |
|  | ## Power | M | Watermark | April 3 | April 8 | In Progress |

|  | ISSUE | PRIORITY | RESPONSIBILITY | TIME NEEDED | DEADLINE | STATUS |
| --- | --- | --- | --- | --- | --- | --- |
|  | ## Boardwalk Amendments |  |  |  |  |  |
|  | ## Load Balancing | H | Powell/Joslyn |  |  | Done |
|  | ## Split R11/R13 | H | Powell/Joslyn |  |  | Done |
|  | ## Fixed Price | M | Joslyn |  |  | Locked In |
|  | ## MTM | L | Joslyn | 1 Month | By Quarter-end | Joslyn to Quantify/Book |
|  | ## Financial Swap | M | Joslyn | Driven by Boardwalk | Driven by Boardwalk | Working on Swap for Nov 80% of March 01 Physical Volume |
|  | ## Settlement System – Power |  |  |  |  |  |
|  | ## Interim Solution | H | Hoogendoorn | Immediate | N/A | Services Agreement Signed with Valeo |
|  | ## Permanent Solution | H | Hoogendoorn/McKeel/ Cross/Hedstrom | 6 Months | Sept 1 | Evaluating Outside Systems |
|  | ## Milnthorp to Clarify with Hedstrom/McKeel | H | Milnthorp |  |  |  |
|  | ## Information Systems – Gas and Electricity |  |  |  |  |  |
|  | ## Billing/Invoicing | H | Hoogendoorn | 2 Days | April 1 | Finished Gas Development |
|  | ## Testing of Billing and Invoicing Systems and Implementation | H | Dalgleish | 3 Days | April 4 | Sent First Batch of Invoices on 4/11/01 |
|  | ## Accounting/Forecasts/SAP |  |  |  |  |  |
|  | ## SAP Implementation | M | Dawes/Dalgleish/ Hoogendoorn | 4 Weeks | April 30 | SAP Checking Ability to Use Customer Relationship System |
|  | ## Cash Flow Model including Power Revenues | L | Poffenroth | 3 Weeks | April 23 |  |
|  | ## Treasury |  |  |  |  |  |
|  | ## Proposal for Collections Bank | H | Joslyn/Cross | 2 Weeks | April 16 | Negotiating Prices |
|  | ## New Bank Account for DD | H | Joslyn/Cross | 1 Week | April 9 | Opened |
|  | ## Automated Solution for Customer Direct Debit | H | Joslyn/Cross | 1 Week | May 1 | In Discussions with Houston |
|  | ## Cash Forecasting | M | Dalgleish/Davies | 2 Weeks | May 15 | Initiated |

|  | ISSUE | PRIORITY | RESPONSIBILITY | TIME NEEDED | DEADLINE | STATUS |
| --- | --- | --- | --- | --- | --- | --- |
|  | ## Reorganization of EDC into EES Canada |  |  |  |  |  |
|  | ## Confirm Status of EES Canada re: Terms and Conditions – WSPs | M | Powell | 2 Months | June 1 | Non-Alberta 1 Gas Potentially Ontario |
|  | ## Confirm Status of EES Canada re: Licensing | M | Powell | 2 Months | June 1 | Registered But Not Licensed in Alberta (Ontario?) |
|  | ## Transfer of Terms and Conditions – WSPs | M | Powell | 2 Months | June 1 | None |
|  | ## Update Gas and Power Forms | M | Powell | 2 Months | June 1 | Ongoing |
|  | ## Update Gas and Power Licensing Requirements | M | Powell | 2 Months | June 1 | Ongoing |
|  | ## Corporate Reorganization | M | Powell | 2 Months | June 1 | Ongoing |
|  | ## Transfer EDC Assets to EES Canada (Transactions/Lease/Equipment/etc.) | M | Powell | 2 Months | June 1 | Ongoing |
|  | ## Recapitalization – EES Canada Sole Shareholder | M | Powell | 2 Months | June 1 | Ongoing |
|  | ## Update Trademark(s) | M | Powell | 2 Months | June 1 | Ongoing |
|  | ## Update Market Participation Requirements (PPoA Participation/NOVA Account/IMO Participation) | M | Powell | 2 Months | June 1 | Ongoing |
|  | ## Ancillary/Legal |  |  |  |  |  |
|  | ## Master Contracts (Gas and Power – Physical and Financial) with ECC/EDC | M | Johnston | 30 Days | May 1 | Completed |
|  | ## Management Services Arrangement (ECC/EDC) | L | Powell | 60 Days | June 1 | Pending #20 |
|  | ## Staff Requirements |  |  |  |  |  |
|  | ## Risk Management | H | Reeves/Gillis | 1 Month | May 1 | Offer Made |
|  | ## Administration | H | Milnthorp | 2 Weeks | April 15 | Done |
|  | ## Commission Structure for Electricity | L | Cross/Milnthorp/ Poffenroth | 1 Month | May 1 | Poffenroth to Take First Cut at Model |
|  | ## Credit | M | Milnthorp/Bradford | 2 Months | June 1 | Otto to Handle in Interim |
|  | ## Call Centre | M | Cross/Woodall | 1 Month | May 15 | Hire Concurrent with New Location |

|  | ISSUE | PRIORITY | RESPONSIBILITY | TIME NEEDED | DEADLINE | STATUS |
| --- | --- | --- | --- | --- | --- | --- |
| 23. | ## Press Release |  |  |  |  |  |
|  | ## Alberta Government | L | Hemstock/Cross |  |  |  |
|  | ## Public Relations | L | Cross/Milnthorp/ Hemstock |  |  |  |
|  | ## Meeting with Government |  | Hemstock/Milnthorp |  | June 15 |  |
| 24. | ## Residential Strategy |  |  |  |  |  |
|  | ## U.K. Model |  | Cross |  |  |  |
|  | ## Strategy |  | Milnthorp/Cross |  |  | Meeting with Shaw on May 15th |