PURCHASE AGREEMENT

By and Between

[ENRON]

AND

FUELCELL ENERGY, INC.

For

Fuel Cell

Direct FuelCell® Powerplants

TABLE OF CONTENTS

ARTICLE I.  DEFINITIONS	5 8

ARTICLE II.  RESPONSIBILITIES OF PURCHASER	11 5

2.1   Purchaser Responsibilities	11 5

ARTICLE III.  RESPONSIBILITIES OF SELLER	12 5

3.1   General Obligations	12 5

3.2   Delivery of Equipment and Documentation	12 5

3.2.1   Delivery to Delivery Point	Error! Bookmark not defined. 5

3.2.2   Installation Services	Error! Bookmark not defined. 5

3.2.3   Impact Recorders	Error! Bookmark not defined.

3.2.4   Maximize Assembly	Error! Bookmark not defined. 5

3.2.5   Documentation Delivery	Error! Bookmark not defined. 5

3.3   Relevant Information	12 5

3.4   Hazardous Materials Notification	13 5

3.5   Employment of Licensed Personnel	13 5

3.6   Customs Clearance	Error! Bookmark not defined. 5

3.6   Customs Clearance	Error! Bookmark not defined. 5

3.7   Not Used	13 5

3.8   Compliance with Governmental Rules	13 5

3.9   Purchaser Review of Vendors	13 5

3.10  Packing and Insurance Surveyor	14 5

3.10.1   Packing Recommendation	14 5

3.10.2   Insurability Certificate	Error! Bookmark not defined.

3.10.3   Notice of Shipment	14 5

3.10.4   Compliance with Recommendation	Error! Bookmark not defined. 5

3.11  Financing Assistance	14 5

3.12  Purchaser Permit Support	14 5

3.13  Not Used	14 5

3.14  Spare Parts	14 5

3.14.1   Commissioning Spares	14 5

3.14.2   O & M Spare Parts	14 5

3.14.2.1   O & M Spare Parts	14 5

3.14.2.2   Purchase of O & M Spare Parts	14 5

3.14.2.3   Delivery of O & M Spare Parts	15 5

3.14.2.4   Use of O & M Spare Parts	15 5

3.15  Key Personnel	Error! Bookmark not defined. 5

3.16  Project Planning and Control	15 5

ARTICLE IV.  REPRESENTATIONS AND WARRANTIES	15 5

4.1   Representations and Warranties of Purchaser	15 5

4.2   Purchaser Supplied Information	Error! Bookmark not defined. 5

4.3   Representations and Warranties of Seller	16 5

ARTICLE V.  PURCHASE AMOUNT AND OTHER CHARGES	17 5

5.1   Purchase Amount	17 5

5.1.1   Purchase Amount	17 5

5.2   Taxes and Contributions	17 5

5.2.1   Seller Responsibility for Personnel Taxes	17 5

5.2.2   Seller’s Responsibility for Taxes	17 5

5.2.3   Not Used	Error! Bookmark not defined. 5

5.2.4   Tax Penalties	Error! Bookmark not defined. 5

5.3   Changes to the Purchase Amount	18 5

5.4   Cancellation	18 5

5.4.1   Cancellation by Purchaser	18 5

5.4.2   Marketing Agreement	Error! Bookmark not defined. 5

5.5   Suspension of Work	19 5

ARTICLE VI.  PAYMENT TERMS	19 5

6.1   Payment of Purchase Amount	19 5

6.1.1   Payment Periods.	20 5

6.1.2   Payment Milestones	Error! Bookmark not defined.

6.1.3   Retention	Error! Bookmark not defined.

6.1.4   Not Used	20 5

6.2   Payment Disputes	20 5

6.3   Payments Withheld or Offset	Error! Bookmark not defined. 5

6.3.1   Payments Withheld	Error! Bookmark not defined. 5

6.3.2   Offset for Liquidated Damages	Error! Bookmark not defined.

6.3.3   Payment of Subcontractors.	Error! Bookmark not defined. 5

6.4   Payment of Liquidated Damages	20 5

6.4.1   Payment of Document Delivery Damages	Error! Bookmark not defined.

6.4.2   Payment of Installation Liquidated Damages	Error! Bookmark not defined.

6.4.3   Payment of Operable Delay Liquidated Damages	Error! Bookmark not defined.

6.4.4   Payment of Heat Rate Liquidated Damages	Error! Bookmark not defined.

6.5   Notices of Nonpayment	Error! Bookmark not defined. 5

6.6   Lien Release	20 5

6.7   Invoices	20 5

6.7.1   Contract Reference	20 5

6.7.2   Address for Invoices	Error! Bookmark not defined. 5

6.7.3   Date of Receipt	21 5

6.8   Method of Payment	21 5

6.9   Payments Not Acceptance of Work	21 5

ARTICLE VII.  EFFECTIVE DATE, COMMENCEMENT OF THE WORK, TERMINATION	21 5

7.1   Effective Date	Error! Bookmark not defined. 5

7.2   Commencement of Work	21 5

7.3   Termination	Error! Bookmark not defined.

ARTICLE VIII.  RELATIONSHIP OF PURCHASER AND SELLER	21 5

8.1   Status of Contractors	Error! Bookmark not defined. 5

ARTICLE IX.  INSPECTION AND CORRECTION OF WORK	21 5

9.1   Inspections	21 5

9.2   Resident Facilities	Error! Bookmark not defined. 5

9.3   Quality Plan	22 5

9.4   Notice	22 5

9.5   Correction of Equipment	22 5

9.6   Not Used	22 5

9.7   Release for Delivery	22 5

ARTICLE X.  DELIVERY AND PERFORMANCE	22 5

10.1   Delivery of Documentation	22 5

10.2   Delivery and Installation of Equipment	23 5

10.2.1   Guaranteed Installation Date	23 5

10.2.1.2   Delivery Restrictions	23 5

10.2.4   Not Used	23 5

10.2.5   Extensions of the Guaranteed Installation Date	23 5

10.2.6   Not Used	Error! Bookmark not defined. 5

10.3   Delay Liquidated Damages	23 5

10.3.1   Installation Liquidated Damages	Error! Bookmark not defined. 5

10.3.2   Not Used	Error! Bookmark not defined. 5

10.4   Heat Rate Guarantee	23 5

10.4.1  Heat Rate Guarantee	23 5

10.4.2   Minimum Heat Rate Guarantee	24 5

10.4.3   Loss Evaluation Guarantee	24 5

10.4.4   Guarantee Value Table	24 5

10.5   Most Recent Performance Test	24 5

10.5.1   Performance Test Required	Error! Bookmark not defined.

10.5.2   Setting Out of Heat Rate Performance Liquidated Damages	Error! Bookmark not defined. 5

10.5.3   Remedy for Failures to Meet Minimum Heat Rate Guarantee	24 5

10.6   Maximum Liabilities for Liquidated Damages	Error! Bookmark not defined.

10.6.1   Maximum Document Liquidated Damages	Error! Bookmark not defined.

10.6.2   Maximum Installation Liquidated Damages	Error! Bookmark not defined.

10.6.3   Maximum Heat Rate Liquidated Damages	Error! Bookmark not defined.

10.6.4   Maximum Operable Delay Liquidated Damages	Error! Bookmark not defined.

10.6.5   Maximum Aggregate Liquidated Damages	24 5

10.7   Liquidated Damages Not Penalty	Error! Bookmark not defined.

10.8   Not Used	24 5

10.8.1   Seller Presence at Tests	24 5

10.8.2   Test Results	24 5

10.8.3   Consumable Spare Parts During Retests	24 5

10.9   Acceptance	24 5

10.10  Manufacturing Slots	24 5

ARTICLE XI.  CHANGE ORDER	25 5

11.1   Adjustment of Purchase Amount	25 5

11.2   Purchaser Requested Change Order	25 5

11.3   Seller Requested Change Order	Error! Bookmark not defined. 5

11.4   Other Change Order	25 5

11.5   Disputes	25 5

11.6   Change Order Pricing	25 5

11.6.1   Method of Pricing	25 5

11.6.2   Cost Plus Basis	25 5

ARTICLE XII.  INTENTIONALLY OMITTED	26 5

ARTICLE XIII.  ORDER OF PRECEDENCE	26 5

13.1   Order of Precedence	26 5

ARTICLE XIV.  WARRANTY	27 5

14.1   Seller’s Warranty	27 5

14.1.1   Primary Warranty Period	27 5

14.1.2   Warranty Clarification	27 5

14.1.3   Warranty Breach Notice	27 5

14.2   Extended Warranty Period	27 5

14.2.1   Continued Warranty on Corrections or Repairs Performed During the Primary Warranty Period	28 5

14.2.2   Extension of Warranty Due to Unavailability	28 5

14.3   Remedy	27 5

14.3.1   Obligations, Responsibilities and Recourse	27 5

14.4   Vendor Warranty	28 5

14.5   Limited Warranty	28 5

14.6   Defective Equipment	29 5

14.7   Termination of Warranty	29 5

14.8   Damage to Other Facility Equipment	29 5

ARTICLE XV.  RISK OF LOSS AND TITLE	29 5

15.1   Risk of Loss	29 5

15.2   Title	29 5

15.2.1   Passage of Title	29 5

15.2.2   Infringement Cures and Defense	30 5

15.3   Seller’s Drawings, Etc. for Use by Purchaser	30 5

15.4   Licensing Procedure	30 5

ARTICLE XVI.  INTENTIONALLY OMITTED	31 5

ARTICLE XVII.  DEFAULT	31 5

17.1   Event of Default by Seller	31 5

17.2   Purchaser's Remedies Against Seller	Error! Bookmark not defined. 5

17.3   General Obligations	31 5

17.4   Payment Obligations	31 5

17.4.1   Determination of Obligations	31 5

17.4.2   Damages and Expenses	Error! Bookmark not defined.

17.4.3   Excess Amounts	31 5

17.4.4   Settlement	Error! Bookmark not defined.

17.5   Events of Default by Purchaser	32 5

17.6   Seller Remedies	Error! Bookmark not defined. 5

ARTICLE XVIII.  FORCE MAJEURE	32 5

18.1   Failure to Perform Due to an Event of Force Majeure	32 5

18.2   Events of Force Majeure	32 5

18.3   Notice of Force Majeure	33 5

18.4   Events of Force Majeure	33 5

18.5   Certain Events Not Excused	34 5

18.6   Continued Performance	34 5

18.7   Not Used	Error! Bookmark not defined. 5

18.8   Force Majeure - Delays	34 5

18.9   Force Majeure - Cost	Error! Bookmark not defined. 5

ARTICLE XIX.  INSURANCE	34 5

19.1   Insurance - General	34 5

19.1.1   All Risk	35 5

19.1.2   Workers Compensation and Employers Liability Insurance	35 5

19.1.3   Commercial General Liability Insurance	35 5

19.1.4   Hull and Protection and Indemnity Insurance	35 5

19.1.5   Business Automobile Liability Insurance	35 5

19.1.6   Aircraft Liability Insurance	36 5

19.1.7   Excess Umbrella Lability Coverage	36 5

19.1.8   Vendors	36 5

19.1.9   Certificate of Insurance	36 5

19.1.10  Other Requirements	36 5

19.1.11  Vendor Waiver of Subrogation	37 5

19.1.12  Compliance with Insurance	37 5

19.1.13 Limitation	37 5

19.2   Purchaser Provided Insurance	Error! Bookmark not defined.

19.2.1   Builder's All Risk	Error! Bookmark not defined.

19.2.2   Marine Cargo Insurance	Error! Bookmark not defined.

19.2.3   Comprehensive General Liability	Error! Bookmark not defined.

19.3   Purchaser Policies	Error! Bookmark not defined. 5

19.3.1   Purchaser's Policies	Error! Bookmark not defined.

19.3.2   Not Used	Error! Bookmark not defined. 5

19.3.3   Primary Insurance	37 5

ARTICLE XX.  INDEMNIFICATION	38 5

20.1   Third Party	38 5

20.2   Notice	38 5

20.3   Employees	Error! Bookmark not defined. 5

20.4   Survival of Obligation	39 5

ARTICLE XXI.  NON-DISCLOSURE OF INFORMATION	39 5

21.1   Proprietary Information	39 5

21.2   Press Releases	39 5

21.3   Confidentiality	Error! Bookmark not defined. 5

ARTICLE XXII.  ASSIGNMENT	40 5

22.1   Assignment by Seller	40 5

22.2   Assignment by Purchaser	Error! Bookmark not defined. 5

22.3   Agreement with Lender	Error! Bookmark not defined. 5

ARTICLE XXIII.  RELATIONSHIP OF THE PARTIES	41 5

23.1   Independent Contractor	41 5

23.2   Responsibilities of Seller as Principal for its Employees	41 5

ARTICLE XXIV.  LIENS AND CLAIMS	41 5

ARTICLE XXV.  NOTICES AND COMMUNICATIONS	41 5

25.1   Notices	41 5

25.2   Effectiveness of Notices	42 5

25.3   Technical Communications	42 5

ARTICLE XXVI.  ARBITRATION	42 5

26.1   Negotiation of Disputes and Disagreements	42 5

26.2   Arbitration Resolution	42 5

26.3   Continuation of Work	43 5

ARTICLE XXVII.  LIMITATION OF LIABILITY	43 5

27.1   Maximum Liability	43 5

27.2   Consequential Damages	43 5

27.3   Releases Valid in All Events	44 5

ARTICLE XXVIII.  DRUG AND ALCOHOL-FREE WORKPLACE	44 5

ARTICLE XIX.  MISCELLANEOUS	44 5

29.1   Validity and Enforceability	44 5

29.2   Governing Law	45 5

29.3   Entire Agreement	45 5

29.4   Agreement Modification	45 5

29.5   Waiver	45 5

29.6   Headings	45 5

29.7   Third-Party Beneficiaries	45 5

29.8   Counterparts	45 5

29.9   Equal Employment Opportunity	45 5

29.10  Cooperation on Site	45 5

EXHIBIT A  PURCHASE PRICE	Error! Bookmark not defined.

EXHIBIT B  SCOPE OF SUPPLY	Error! Bookmark not defined.

EXHIBIT B-1  SPECIFICATION	Error! Bookmark not defined.

EXHIBIT B-2  DRAWING LIST	Error! Bookmark not defined.

EXHIBIT B-2  DRAWING LIST	Error! Bookmark not defined.

EXHIBIT B-3  DOCUMENT REVIEW STATUS	Error! Bookmark not defined.

EXHIBIT B-4  APPROVED VENDORS	Error! Bookmark not defined.

EXHIBIT C  NOT USED	Error! Bookmark not defined.

EXHIBIT D  SAMPLE SURETY BOND	Error! Bookmark not defined.

EXHIBIT E  PERFORMANCE TESTS	Error! Bookmark not defined.

EXHIBIT F  NOT USED	Error! Bookmark not defined.

EXHIBIT G-1  PERFORMANCE TEST CERTIFICATE	Error! Bookmark not defined.

EXHIBIT G-2  PERFORMANCE TEST CERTIFICATE	Error! Bookmark not defined.

EXHIBIT H  NOT USED	Error! Bookmark not defined.

EXHIBIT I  CANCELLATION CHARGE	Error! Bookmark not defined.

EXHIBIT J  QUALITY	Error! Bookmark not defined.

EXHIBIT K  PROJECT PLANNING	Error! Bookmark not defined.

EXHIBIT L  NOT USED	Error! Bookmark not defined.

EXHIBIT M  NOT USED	Error! Bookmark not defined.

EXHIBIT M - 1  SPARE PARTS	Error! Bookmark not defined.

EXHIBIT N – PURCHASE AMOUNT RECONCILIATION	Error! Bookmark not defined.

EXHIBIT N-2  NOT USED	Error! Bookmark not defined.

EXHIBIT N-3 ASSEMBLY OF GENERATOR STEP-UP TRANSFORMERS	Error! Bookmark not defined.

EXHIBIT O  HAZARDOUS MATERIAL NOTIFICATION	Error! Bookmark not defined.

EXHIBIT P  NOT USED	Error! Bookmark not defined.

EXHIBIT Q  NOT USED	Error! Bookmark not defined.

EXHIBIT R  WITNESS - HOLD POINTS	Error! Bookmark not defined.

EXHIBIT S  WAIVER LIENS	Error! Bookmark not defined.

EXHIBIT S-1  SELLER’S CONDITIONAL WAIVER	Error! Bookmark not defined.

PURCHASE AGREEMENT

This Purchase Agreement (this “Agreement”) is made and entered into and effective on the ___ day of  ___,  (the “Effective Date”) by and between [ENRON]., incorporated under the laws of the state of Delaware, with offices located at [] ("Purchaser"), and FuelCell Energy, Inc., a corporation incorporated under the laws of Connecticut (“Seller”), with offices located at [].

RECITALS

WHEREAS, Purchaser has the need to acquire Fuel Cell Direct FuelCell®  Power Plants and associated equipment and services; and

WHEREAS, Seller is in the business of designing, engineering, manufacturing, and installing such equipment and other services related thereto;

WHEREAS, Purchaser wishes to contract with Seller for the design, engineering, manufacture, and installation of such equipment and other services related thereto;

WHEREAS, the parties desire to set forth the terms and conditions under which Seller will provide and Purchaser will pay for purchase such equipment and related services;

NOW, THEREFORE, in consideration of the mutual covenants herein contained, and intending to be legally bound, the parties hereto agree as follows:

ARTICLE I.  DEFINITIONS

[PLEASE NOTE: the definitions have not been updated to reflect changes from the form document]

Capitalized terms used in this Agreement without other definition shall have the meanings specified in this Article I, unless the context requires otherwise.

As used in this Agreement, the terms "herein", "herewith" and "hereof" are references to this Agreement, taken as a whole, the term "includes" or "including" shall mean "including, without limitation," and references to a "Section", "subsection", "clause", "Article", "Exhibit", "Appendix" or "Schedule" shall mean a Section, subsection, clause, Article, Exhibit, Appendix or Schedule of this Agreement, as the case may be, unless in any such case the context requires specifies otherwise.  All references to a given agreement, instrument or other document shall be a reference to that agreement, instrument or other document as modified, amended, supplemented and restated through the date as of which such reference is made, and reference to a law, regulation or ordinance includes any amendment or modification thereof.  A reference to a person includes its successors and permitted assigns.  The singular shall include the plural and the masculine shall include the feminine, and vice versa.

The terms and the definitions set forth herein apply when capitalized.

1.1	Acceptance.  Shall have the meaning as set forth in Section 10.9 10.7.

1.2	Affiliate.  Shall mean a person or entity who, with respect to a specified person or entity, directly or indirectly through one or more intermediaries controls, or is controlled by, or is under common control or ownership with, the person or entity specified.

1.3	Agreement.  Shall mean this Agreement for the purchase of the Equipment, including have the meaning set forth in the Heading and shall include all Exhibits attached hereto, as amended from time to time as provided herein.

1.4	Applicable Laws.  Shall mean any applicable federal, state, municipal or local statute, ordinance or other law, regulation or by-law or any rule, code or direction or any license, consent, permit, authorization or other approval including any conditions attached thereto (whether relating to the environment or otherwise) which has appropriate jurisdiction.

1.5	Cancellation Charge.  Shall have the meaning as set forth in Section 5.4.1(c) Section 5.4.3.

1.6	Change in Law.  Shall mean any change in, or binding change in the judicial or administrative interpretation of, or adoption of, any Applicable Law, which is implemented after the Effective Date, and which has an adverse affect on Seller’s a party’s performance under this Agreement; provided, however, that a change in any federal, commonwealth, state or local income or franchise tax law, workers' compensation, or payroll or withholding tax law shall not constitute a change Change in law Law hereunder.

1.7	Change Order.  Shall have the meaning as set forth in Section 11.2.

1.8	Day or day.  Shall mean a calendar day, including weekdays, weekends, and holidays.

1.9	Delay Event Delivery Point.  Shall mean a location mutually agreed upon by the parties and set forth in the applicable Scope of Work.

1.10	Effective Date.  Shall have the meaning set forth in Section 10.3.1. the Heading.

1.10 Delay Liquidated Damages

1.11	Heat Rate.  Shall have the meaning set forth in Section 10.3. 10.4.1.

1.11 Delivery Point. For all Equipment, delivery shall mean a location designated by Purchaser. [Note: for pricing purposes it is assumed that delivery will be in Connecticut.]

1.12 Document Delivery Date. Shall have the meaning as set forth in Section 10.1.

1.13 Document Liquidated Damages. Shall have the meaning as set forth in

Section 10.1.

1.14 Due Date. Shall have the meaning set forth in Section 10.1.

1.15 Effective Date. Shall have the meaning as set forth in Section 7.1.

[1.16 Heat Rate. Shall mean .

1.17 Heat Rate Guarantee. Shall have the meaning set forth in Section 10.4.1.

1.18 Heat Rate Liquidated Damages. Shall have the meaning set forth in Sections 10.4.3 and 10.4.4.]

1.19

1.12	Equipment.  Shall mean the Units, equipment and materials required to manufacture, supply, and install the Units pursuant to this Agreement.

1.20

1.13	Event of Force Majeure.  Shall have the meaning as defined set forth in Section 18.4.

1.21

1.14	Event of Purchaser Default.  Shall have the meaning as defined set forth in Section 17.5.

1.22

1.15	Event of Seller Default.  Shall have the meaning as defined in Section 17.1. set forth in Section 17.1.

1.23 Excess Termination Costs. Shall have the meaning set forth in Section 17.4.3.

1.24

1.16	Extended Warranty Period.  Shall have the meaning as set forth in Section 14.2.1 14.3.2.

1.25

1.17	Facility.  Shall mean each electric generation plant comprised of the specified number of Units and the Balance of Plant and established in accordance with this Agreement.

1.18

1.26 Guaranteed Installation Date. Shall have the meaning as set forth in Section 10.2.1.

1.27	Hazardous Materials.  Shall mean any hazardous substance or hazardous waste as defined in the Comprehensive Environmental Response, Compensation and Liability Act of 1980, as amended, the Resource Conservation and Recovery Act, as amended, the Hazardous Waste Transportation Act, as amended, and regulations promulgated pursuant to these Acts and any similar applicable law or regulation in the United States defining hazardous substances or hazardous waste, and any equipment containing polychlorinated biphenyls or asbestos that may become friable.

1.28

1.19	Installation Completion.   Shall have the meaning set forth in Section 10.2.1.

[1.29

1.20	Installation Liquidated Damages Date.  Shall have the meaning as set forth in Section 10.3.1.] 10.2.

1.30 Insurability Certificate. Shall have the meaning as set forth in Section 3.10.2.

1.31

1.21	Indemnified Party.  Shall have the meaning as set forth in Section 20.2.

1.32 Insurance Representative. Shall have the meaning as set forth in Section 3.10.1.

1.33

1.22	Interest Rate.  Shall mean the prime rate as published by Citibank at its New York office plus two percent (2%) per annum, provided however, that the Interest Rate shall never exceed the highest applicable lawful rate.

1.34 kW. Shall mean kilowatt.

1.35

1.23	kWh or kwh.  Shall mean kilowatt hour.

1.36

1.24	Lender.  Shall mean any financial institution from which Purchaser is obtaining financing in connection with the a Facility and associated facilities and services. equipment and services.

1.39 Milestone. Shall mean an event that triggers a responsibility of Purchaser to pay a Milestone Payment Amount as set forth and listed in Section 6.1.2.

1.43 Net Cancellation Charge. Shall have the meaning as set forth in Section 5.4.1(d).

1.44

1.25	Notice.  Shall mean any notification of one party hereto by the other party hereto with respect to any matter arising under or in connection with this Agreement, to be given as provided in Section 25.1 hereof..

1.45 Notice to Proceed or NTP. Shall have the meaning as set forth in Section 7.2.

1.46

1.26	O & M Spare Parts.  Shall have the meaning set forth in Section 3.14.2 and as set forth in Exhibit M-1.

1.47

1.27	O & M Spare Parts Amount.  Shall have the meaning as set forth in Section 3.14.2.

1.49

1.28	Patent Indemnities.  Shall have the meaning as set forth in Section 15.2.2.

1.50

1.29	Performance Test.  Shall mean the test(s) conducted at each Site on each Unit in accordance with the Test Procedures test procedures set forth in Exhibit B-1 to determine whether the tested Unit meets Emissions, Heat Rate, Electrical Output and Water Consumption Guarantees guarantees.

1.51

1.30	Performance Test Certificate.  Shall mean the certificate(s) prepared by Seller in the format attached hereto as Exhibit G-1 or G-2 and provided to Purchaser, certifying that Performance Tests have been completed and set, setting forth the results thereof in such detail to reflect the performance of the Units. Such certificate(s) shall also document, and documenting the results of any other tests performed in accordance with the Specification. Purchaser shall co-sign such certificate and quantify Electrical Losses Liquidated Damages, if any. Specifications.

1.52

1.31	Primary Warranty Period.  Shall have the meaning as set forth in Section 14.1.1.

1.53

1.32	Project Manager.  Shall mean the project manager designated by Seller pursuant to Section 3.3(a) hereof.

1.54 Proper Scope Value. Shall have the meaning as set forth in Section 17.4.1. Section 3.3(a).

1.55

1.33	Purchase Amount.  Shall have the meaning set forth in Section 5.1.1, as such amount may be adjusted from time to time. 5.1.

1.56

1.34	Purchaser.  Shall have the meaning set forth in the preliminary statements. Heading of this Agreement.

1.57

1.35	Purchaser's Representative.  Shall mean the individual designated by Purchaser pursuant to Section 2.1(a) hereof, who shall have the responsibility and authority specifically delegated to such individual by Purchaser and made known in writing to Seller. have the meaning set forth in Section 2.1.

1.58

1.36	Related Dispute.  Shall have the meaning set forth in Section 26.2.

1.59 Refund Amount. Shall have the meaning as set forth in Section 17.4.1.

[1.60 Retention Amount. Shall have the meaning as set forth in Section 6.1.3.

1.61 Retention Surety Bond. Shall have the meaning as set forth in Section 6.1.3.]

1.62

1.37	Scope of Supply.  Shall have the meaning as set forth in Exhibit B.

1.63

1.38	Scope of Work.  Shall mean the Equipment and all other design, engineering, manufacture, delivery, transportation, services, equipment, drawings, documentation, supplies and materials to be performed and/or furnished by Seller pursuant to this Agreement including the Scope of Supply.

1.64 Scope Value Due. Shall have the meaning as set forth in Section 17.4.1.

1.65

1.39	Seller.  Shall have the meaning set forth in the preliminary statements. Heading to this Agreement.

1.66

1.40	Site.  Shall mean any part of the land where a Facility is located.

1.67 Specification

1.41	Specifications.  Shall mean the specifications issued by Purchaser mutually agreed upon by the parties for the design, manufacture, assembly, and supply of the Units as set forth in Exhibit B-1.

1.68 Termination Costs. Shall have the meaning as set forth in Section 17.4.2.

1.69 Termination Settlement. Shall have the meaning as set forth in Section 17.4.4.

1.70 Test Procedures. Shall have the meaning as set forth in Exhibit B-1.

1.71

1.42	Unit.  Singularly, any of the fuel cell Direct FuelCell® powerplants and associated equipment that Seller is furnishing Purchaser is purchasing under this Agreement and equipment associated with said transformers.

1.72

1.43	Vendor.  Shall mean any vendor, supplier or subcontractor utilized by Seller in the performance of the Scope of Work hereunder.

ARTICLE II.  RESPONSIBILITIES OF PURCHASER

2.1   Purchaser Responsibilities.  Purchaser recognizes and acknowledges the that it has a duty to reasonably cooperate with Seller, and agrees not to wrongfully interfere with Seller’s agents, employees or Vendors during the performance of this Agreement.  Without limiting the generality of the foregoing or Purchaser’s other obligations under this Agreement, Purchaser shall be responsible for ensuring that the following matters and actions to be are performed by it or its employees or agents on a timely basis:

(a)	designate a Purchaser's Representative and deliver a notice designation of a representative (“Purchaser's Representative”) and delivery a Notice to Seller identifying Purchaser's Representative, within thirty (30) days of the Effective Date, who shall act as the primary point of contact for Seller with respect to the prosecution of the Scope of Work and shall have the authority to bind Purchaser;;

(b) deliver a notice

(b)	delivery of Notice, within thirty (30) days of the Effective Date, to Seller identifying such persons within Purchaser's organization that have authority to approve Change Orders;

pay

(c)	payment to Seller of the sums required to be paid by Purchaser pursuant to the terms of this Agreement;

provide or arrange

(d)	provision or arrangement for adequate road access to the Facility Facilities from the nearest major highway; and

,

provide or cause to be provided those items and services in accordance with Exhibit __ which are specifically identified as being within Purchaser’s scope of supply. [Note: This exhibit will list the activities that the Purchaser has to complete in accordance with the associated timetable to allow the performance tests to be conducted for each Unit.]

(e)	provision of those materials, items and services specifically identified in Exhibit __ in accordance with the timetable set for in such Exhibit __.

ARTICLE III.  RESPONSIBILITIES OF SELLER

3.1   General Obligations.  Except as expressly set forth in this Agreement, Seller shall provide the materials and supplies, technical and professional personnel and supervision as required for Seller to fulfill its responsibilities, tools and equipment, and the services required for performance and timely completion of the under this Agreement and an associated Scope of Work, and shall be responsible for timely completing the Scope of Work in accordance with the terms of this Agreement, including all Exhibits.  In furtherance of the foregoing, Seller shall ensure that all Equipment complies with the Specifications.   References in the Specifications equipment and all material and articles incorporated into the Equipment shall be new and of suitable grade for the purpose intended, unless otherwise specifically provided in this Agreement.

References in the Specification to equipment, material, articles or patented processes by trade name, make, or catalog number, shall be regarded as the standard of quality to be met by Seller.  Seller may, with the prior written consent of Purchaser, use any equipment, material, article, or process that is operationally, technically and functionally equivalent (as judged by Purchaser in its sole reasonable discretion) to that named in the Specification.

3.2   Intentionally Deleted Delivery of Equipment and Documentation.

3.2.1 Delivery to Delivery Point. Seller shall deliver the Equipment to the Delivery Point.

3.2.2 Installation Services . Seller shall offload and install the Units at the Site in accordance with Exhibit N-3. Purchaser shall have the right to approve any subcontractor that Seller desires to employ in carrying out the transportation of the Units and the installation services.

3.2.3 Maximize Assembly. Shipment of each item of Equipment shall be made so that it is complete with all accessories and will arrive at its destination simultaneously.

3.2.4 Documentation Delivery. Seller shall deliver documentation as set forth in Section 10.1 by the dates set forth therein.

3.3   Relevant Information.  Seller shall provide on a timely basis to Purchaser information reasonably necessary to fulfill Seller’s obligation obligations pursuant to this Agreement, including, without limitation:

(a)	within fifteen (15) thirty (30) days of the Effective Date of this Agreement, the identity  of a project manager (the "Project Manager") who shall have full supervision over the completion of  the Scope of Work and who shall act as the primary point of contact with Purchaser regarding all matters relating to the Scope of Work;

(b)	such information as is reasonably requested by Purchaser in dealing with its customer customers and/or any governmental authority in matters relating to the Scope of Work; and

(c)	the project management plan proposed for this Agreement and its associated Scope of Work to include, but not limited to staffing, milestones, scheduling, quality control, transportation, technical interface, and other matters required to successfully manage the project to conclusion [Necessary?  Seems duplicative of the Scope of Work and the Exhibits.  Delete?]; and

(d)	___ days prior to the shipment of a complete Unit, notice Notice that a Unit will be available for shipment. [compare to 3.10.3 and 9.7]

3.4   Hazardous Materials Notification.

(a) Seller warrants to Purchaser that in relation to the Scope of Work, it will use reasonable skill and care to ensure that there will not be Hazardous Material Materials specified or incorporated into the Scope of Work; provided that where in the opinion of Seller this results in any conflict with any relevant statutory requirements or where the Scope of Work would be prejudiced through lack of suitable alternatives, then Seller shall immediately notify provide Notice to Purchaser in writing specifying the conflict or prejudice which has arisen and the substance which Seller wish wishes to stipulate or use and Seller shall not stipulate or use the same without, in each case, the prior written consent of Purchaser, which consent shall not be unreasonably withheld.

(b)  Seller shall immediately, upon the request of Purchaser, promptly certify in writing that to the best of its knowledge that no Hazardous Materials have been specified or incorporated in into the Scope of Work. In the event Seller, with Purchaser's approval, incorporates any Hazardous Materials into the Equipment, Seller shall provide Purchaser with notification as set forth in Exhibit O. [Discuss. This should only apply to the product as received at the site]

3.5   Employment of Licensed Personnel.  Whenever required by applicable governmental law, rule or regulation Applicable Law (applicable under the terms of this Agreement) or prudent engineering and construction practices, Seller agrees to employ licensed personnel to perform engineering, and design, during fulfillment services in the performance of its obligations under this Agreement or other professional services in the performance of the Scope of Work.  Seller shall be responsible for employing and utilizing personnel and for ensuring that its Vendors employ and utilize personnel who possess the proper training and experience and are capable of performing the tasks for which they are employed or utilized.

Seller shall not employ or permit any Vendor to employ in connection with its performance under this Agreement any unfit person or anyone not skilled in the work assigned to such person.

3.6 Customs Clearance. Seller shall perform customs clearance for the Equipment through U.S. Customs, if applicable.

3.7 Not Used.

3.8 Compliance with Governmental Rules. Seller shall comply with government rules in the categories enumerated below.

(a) Seller Conduct. Seller shall comply with applicable regulatory requirements including, without limitation, all Applicable Laws issued or promulgated by units of government and regulatory bodies with jurisdiction over any aspect of the performance of this Agreement by Seller. Seller shall not act in violation of the U.S. Foreign Corrupt Practices Act, and in connection therewith shall not make any payments, loans, or gifts directly or indirectly, to or for the use or benefit of any official employee, agency or instrumentality of any government, political party or candidate thereof, or any other person or entity, the payment of which would violate the laws or policies of the United States, or the country or countries in which the Scope of Work is performed, in whole or in part. Seller shall possess or procure all permits, certificates, and licenses necessary to allow Seller to perform this Agreement at all locations of performance and shall ensure that Vendors have all permits, certificates, and licenses necessary for such Vendors to perform under this Agreement. Seller shall answer promptly and in reasonable detail any questionnaire or other written or oral communications, to the extent the same pertain to compliance with this Section 3.8 (a) or (b) whether such questionnaires or communications are from Purchaser, their outside auditors, or other representatives. Seller further agrees to pay any government assessed penalties, fines, and charges, and associated damages, costs, losses, and expenses (including, without limitation, court costs and attorneys' fees) of whatever kind which Purchaser may incur, be required to pay or be liable for as a result of, in connection with, arising out of or related to any noncompliance of Seller’s performance of this Agreement or any portion thereof with any or all of the above laws, regulations, rules, orders, codes, criteria, standards, ordinances or resolutions.

(b) Employment Practices.

(1) Seller agrees that it shall be at all times during the term of this Agreement in full compliance with all Applicable Laws relative to Seller’s employment of employees and agents of Seller.

Seller agrees to pay any government assessed penalties, fines, and charges, and associated damages, costs, losses, expenses (including, without limitation, court costs and attorneys' fees) of whatever kind which Purchaser may incur, be required to pay or be liable for as a result of, based on, in connection with, related to or arising from Seller or any of their Vendors' noncompliance with this Section 3.8(b).

(c) Scope of Work to Comply with Applicable Laws. Subject to the provisions of Section 3.8 (c) (4);

(1) Seller shall cause the Scope of Work to comply with the Specification and Applicable Laws that were:

(i) in effect on the date this Agreement was signed; or

(ii) were not yet in effect on the date this Agreement was signed, but at such time a change to such valid Applicable Laws, issued or promulgated by units of government and regulatory bodies had passed but was not yet effective.

In the event Seller fail to cause the Scope of Work to so comply with the Specification and Applicable Laws, Seller shall correct such non-complying Scope of Work or portion thereof as necessary to comply with the above. Seller shall bear the costs of correction of such non-complying Scope of Work. In the event that Purchaser reasonably determines that Seller is either not capable of performing the corrections or not capable of performing such corrections in time to meet Purchaser's requirements, Purchaser may, at Seller’s expense, have the corrections made by a third party or make them itself; provided, however prior to Purchaser having the corrections performed by a third party or itself Purchaser shall have provided Seller notice of its determination that it believes Seller is not capable of such performance of work or performing such corrections in a timely manner.

(2) In the event that Seller does not comply with the Specification and Applicable Law, and Purchaser at its sole determination agrees Seller cannot reasonably incorporate the changes necessary for Seller to comply, Purchaser, in its sole discretion, may either terminate the Agreement in accordance with the Article XVII, or direct Seller to complete the Equipment without such changes, in which case Purchaser shall assume full responsibility for obtaining any necessary waivers from the appropriate federal, state or local authorities.

(3) Seller shall, on a reasonable efforts basis, advise Purchaser of pending Applicable Laws of which Seller is aware so that Purchaser may make an informed decision as to whether to have the Equipment designed in anticipation of such pending change as it affects the Scope of Work.

(4) In the event a Change in Law occurs subsequent to the times set forth in Section 3.8(c)(1), Seller shall prepare a request for a Change Order to Purchaser identifying the nature of the change, including any extensions of time to the performance of the Scope of Work and the Purchase Amount. In the event that Purchaser elects to not have Seller comply with such change, Purchaser shall indemnify Seller for such failure to the Scope of Work to comply with such new law requirement.

3.6   Intentionally Deleted.

3.7   Intentionally Deleted.

3.8   Compliance with Applicable Law.  In the performance of its obligations under this Agreement and any Scope of Work, Seller shall comply with all material Applicable Laws.  In the event a Change in Law occurs which effects Seller’s ability to perform in accordance with the Scope of Work and/or to provide the Equipment in accordance with the Specifications, Seller shall prepare and deliver to Purchaser a request for a Change Order identifying the nature of the change, including any extensions of time to perform the Scope of Work or adjustments of the Purchase Amount.  In the event that Purchaser elects to reject such Change Order, Purchaser shall indemnify Seller for any and all liability, damages, fines, penalties, losses or claims arising from Purchaser’s failure to comply with the applicable Change in Law.  Notwithstanding the foregoing, if Seller elects to comply with the Change in Law and Seller has rejected the Change Order submitted by Seller as a result of the Change in Law, Purchaser shall have the right to terminate the applicable Scope of Work.

3.9   Intentionally Deleted Purchaser Review of Vendors.  Seller will notify Purchaser as to the Vendors to be used in performance of the Scope of Work for an item of Equipment or performance of a particular portion of the Work.  Purchaser shall have the right to disapprove any Vendor proposed by Seller for an item of Equipment, other than those listed in Exhibit B-4 for such particular item of Equipment.

3.10  Packing.

3.10.1 Packing Recommendation. Seller shall perform all packaging of package the Equipment to the highest commercial standard in accordance with commercially reasonable practices of the industry to prevent damage during handling and transportation.

3.10.2 Not Used.

3.10.3 Notice of Shipment. Seller shall provide Purchaser with an initial Notice at least fourteen (14) day advance notice of days prior to the expected packing shipping date and the expected loading date of any such shipment, and shall provide two business days advance notice Notice of the actual packing shipping date and the actual loading date of such shipment. Seller shall provide the Purchaser with a stowage and packing plan forty-five (45) days prior to loading. .[compare to 9.7 and 3.3(d)]

3.10.4 Compliance with Recommendation. Seller’s compliance with the Purchaser’s recommendations shall not relieve Seller of its responsibility for risk of loss and damage of the Equipment in accordance with this Agreement through delivery to the Delivery Point.

3.11  Financing Assistance.  Seller shall provide such information as Purchaser may reasonably request in connection with obtaining financing for the Facility including without limitation providing information related to design, engineering and status of the completion of the Scope of Work and Seller’s credentials and experience, and as required perform reasonable travel.  Purchaser shall reimburse Seller at commercially reasonable rates for its time in providing such information not related to the Scope of Work and any travel associated therewith.  Lender and the Lender's engineers and consultants shall have the right to participate in all inspections conducted by Purchaser under this Agreement and to attend all tests of the Equipment.  At Purchaser's request, Seller shall furnish to Purchaser and/or Lender copies of notices given to Purchaser hereunder.

3.12  Purchaser Permit Support.  Seller shall provide all information, data and documents in a timely fashion that Purchaser may reasonably require for Purchaser to obtain applicable permits.

3.13  Not Used Intentionally Deleted.

3.14  Spare Parts. [Applicable?]

3.14.1   Commissioning Spares Parts.  Seller’s representative price list of start-up and commissioning spares spare parts and a representative list of special tools needed during start-up and commissioning are set forth in Exhibit M.  Seller shall within the Purchase Amount provide (i) all spare parts necessary to achieve installation, start up, commissioning, Performance Testing, and (ii) all installation and maintenance tools that are not normally found available in the market place and therefore the attached lists may not be all inclusive. [Discuss]

3.14.2   O & M Spare Parts.

3.14.2.1   O & M Spare Parts.   Exhibit M-1, sets forth the description, estimated quantity, and price of Seller’s best estimate of the O & M Spare Parts required to support an operations and maintenance program for a period of [two (2)] years (“O & M Spare Parts”).  The prices set forth in Exhibit M-1, shall remain fixed for a period of six months from the date of the Notice to Proceed. The prices of the O & M Spare Parts set forth in Exhibit M-1 are not included in the Purchase Amount. [Won’t have spares lists till we conduct first unit acceptance test]

3.14.2.2   Purchase of O & M Spare Parts. Purchaser may purchase O & M Spare Parts at the prices set forth in Exhibit M-1, if purchased within the price validity period set forth in Section 3.14.2.1 [discuss fixed rates].  In the event Purchaser purchases such O & M Spare Parts hereunder, the transaction shall be accomplished by a Change Order pursuant to the provisions of this Agreement or by separate agreement issued by Purchaser.  The value of such Spare Parts purchase shall be known as the “Spare“O & M Spare Parts Amount”.

3.14.2.3   Delivery of O & M Spare Parts.  In the event Purchaser acquires O & M Spare Parts during the price validity period, Seller shall deliver such O & M Spare Parts in accordance with the provisions of this Agreement. Seller shall ensure that all such spare parts are delivered to Purchaser, at the Delivery Point, before energization, but in any case prior to Acceptance applicable Change Order.  Title to O & M Spare Parts procured by Purchaser hereunder shall pass to Purchaser upon the earlier to occur of (a) arrival at the Delivery Point or (b) payment by Purchaser in accordance with Section 3.14.2.2 above.

3.14.2.4  Use of O & M Spare Parts. Should any component fail during energization, commissioning, or testing, spare parts O & M Spare Parts may be withdrawn from the Purchaser’s operations and maintenance stores, if any, and the failed component shall be returned to operating condition.  Seller shall be responsible, at its cost, for replacing any such O & M Spare Parts withdrawn spare parts prior to Acceptance; provided that in the event of any long-lead item which cannot be replaced by Seller within such period(the use of which has been approved in advance by Purchaser, such approval not to be unreasonably withheld or delayed), Seller shall be entitled to deliver such item to Purchaser following Acceptance if Seller demonstrates to Purchaser that such item has been ordered by Seller and Seller provides Purchaser with reasonably security, as requested by Purchaser, for the delivery of such item after Acceptance..

3.15 Key Personnel. Seller shall provide Purchaser with biographical data for Project Manager, the Units engineering manager, Units production manager and installation supervision staff. If, in the reasonable opinion of Purchaser, Purchaser determines such a key person is not adequately performing, Purchaser may require Seller to remove such person from work on the Scope of Work under this Agreement and replace with a satisfactory replacement

3.15  Intentionally Deleted.

3.16  Project Planning and Control.  Exhibit K sets forth the Project Planning and Control system for tracking the progress of the Scope of Work.  Seller shall establish a program, submit reports and data as set forth therein. [will establish project planning and control system after contract]

ARTICLE IV.  REPRESENTATIONS AND WARRANTIES

4.1   Representations and Warranties of Purchaser.  Purchaser makes the following representations and warranties to Seller, each of which is true and correct on the date hereof:

(a)		Purchaser is a corporation organized, existing and in good standing under the laws of the state of Delaware; Purchaser possesses all requisite power and authority to enter into and perform this Agreement, and to carry out the transactions contemplated herein; and Purchaser has all legal power and authority to own and use its properties, and to transact the business in which it is engaged and holds or expects to obtain all franchises, licenses, and permits necessary and required therefor;

(b)		Purchaser's execution, delivery, and performance of this Agreement have been duly authorized by, and are in accordance with, its articles of incorporation and by-laws; this Agreement has been duly executed and delivered for it by the signatories so authorized; and this Agreement constitutes Purchaser's legal, valid, and binding obligation;

(c)		Purchaser is not in breach of, in default under, or in violation of, any Applicable Laws, or the provisions of its articles of incorporation or by-laws, or any franchise or license, or in breach of, in default under, or in violation of any provision of any indenture or any evidence of indebtedness or security therefor, lease, contract, license or other agreement by which it is bound, if such breach, default or violation may result in a material adverse effect on the business or financial condition of Purchaser; and the execution and delivery of this Agreement and the performance of its obligations hereunder will not constitute or result in any such breach, default or violation; and

(d)		no suit, claim, action, arbitration, or legal, administrative or other proceeding is pending or threatened against Purchaser that would affect the validity or enforceability of this Agreement, the ability of Purchaser to fulfill its commitments hereunder in any material respect, or that could result in any material adverse change in the business or financial condition of Purchaser.

4.2   Purchaser Supplied Information. PURCHASER DISCLAIMS ALL WARRANTIES, WHETHER EXPRESS OR IMPLIED, OF ANY KIND CONCERNING INFORMATION PROVIDED TO SELLER BY OR ON BEHALF OF PURCHASER PURSUANT TO OR IN FURTHERANCE OF THE SERVICES PROVIDED PURSUANT TO THIS AGREEMENT, INCLUDING, BUT NOT LIMITED TO, ANY WARRANTY THAT THE INFORMATION IS ACCURATE, CORRECT, COMPLETE, FIT FOR ANY PARTICULAR USE OR CAN BE USED WITHOUT INFRINGING ANY PATENT, COPYRIGHT, TRADEMARK, OR OTHER INTELLECTUAL PROPERTY RIGHTS OF THIRD PARTIES UNDER THE INTELLECTUAL PROPERTY RIGHTS OF THE WORLD. Except to the extent that the information provided by Purchaser to Seller is in the form of a specification or performance requirement specifically called out in this Agreement, it is Seller’s responsibility to ensure that the information provided to Seller by Purchaser is accurate, correct, complete and fit for the particular purpose(s) for which Seller may utilize it Intentionally Deleted.

4.3   Representations and Warranties of Seller.  Seller makes the following representations and warranties to Purchaser, each of which is true and correct on the date hereof:

(a)	It is duly organized, existing and in good standing under the laws of its jurisdiction of formation Delaware; that it possesses all requisite power and authority to enter into and perform this Agreement, to carry out the transactions contemplated herein, and to conduct business in each of the locations where any portion of the Scope of Work is to be performed; and Seller has all legal power and authority to own and use its properties and to transact the business in which it is engaged and holds or expects to obtain all franchises, licenses, and permits required therefor;

(b)	Seller’s execution, delivery, and performance of this Agreement have been duly authorized by, and are in accordance with, its articles of incorporation and by-laws; this Agreement has been duly executed and delivered for it by the signatories so authorized; and this Agreement constitutes Seller’s legal, valid, and binding obligation;

(c)	Seller is not in breach of, in default under, or in violation of, any applicable statute, law, ordinance, decree, rule, or regulation of any governmental authority, Applicable Law or the provisions of  its articles of incorporation or by-laws or any franchise or license, or in breach of, in default under, or in violation of, any provision of any indenture or any evidence of indebtedness or security therefor, lease, contract, license or other agreement by which it is bound if such breach, default or violation may result in a material adverse effect on the business or financial condition of Seller; and the execution and delivery of this Agreement and the performance of its obligations hereunder will not constitute or result in any such breach, default or violation;

(d)	no suit, claim, action, arbitration, or legal, administrative or other proceeding is pending or threatened against Seller that would affect the validity or enforceability of this Agreement, the ability of Seller to fulfill its commitments hereunder in any material respect, or that could result in any material adverse change in the business or financial condition of Seller;

(e) Seller will use its skill, efforts and judgment to further the interests of Purchaser, to furnish efficient business administration and supervision, and to furnish at all times an adequate supply of workers and materials;

(f)	Seller has the right and authority to convey and grant all the rights of ownership as set forth in Section 15.2.

Without limiting the foregoing, Seller represents and warrants that the design, engineering, manufacture, delivery, installation, training and other services, and equipment, materials and information provided to Purchaser by Seller hereunder will not infringe on any third party's patent, copyright, trademark, trade secret or other intellectual property rights;

(g) All services, equipment, materials and information, including without limitation the documentation delivered pursuant to Section 10.1, presented to Purchaser for acceptance hereunder are complete, accurate, and authentic and meet the requirements of this Agreement; and

(h)

(g)	Equipment of the same type and model number which is sold by Seller or its Affiliates to other clients is of the same manufacturing technology as the Equipment provided under this Agreement; such equipment has not demonstrated trends of failure due to design, engineering, manufacturing processes or materials used therein during normal installation, start-up, commissioning, testing or operation of the equipment through periods equivalent to the Primary Warranty Period, or Extended Warranty Period as applicable, except as expressly stated in writing to Purchaser; and

(i)

(h)	Any and all hardware, software and firmware product delivered (as a component of a system, part of a piece of equipment, or as a stand alone item) under this Agreement shall be able to:

- accurately process date data (including but not limited to accepting input, providing output and calculating comparing and sequencing) from, into and between the Twentieth and Twenty-First Centuries, including (but not limited to) leap year calculations;

(2)	respond to and process two digit year input without creating any ambiguity as to the century; and

(3)	store and provide date input information without creating an ambiguity as to the century, provided that such hardware, software and/or firmware is operated in accordance with the manufacturer recommendations, (a copy of which shall be provided to and explained to the Purchaser).  [Applicable?]

ARTICLE V.  PURCHASE AMOUNT AND OTHER CHARGES

5.1   Purchase Amount.

5.1.1 Purchase Amount. The purchase amount for the Units Equipment and their the services associated Scope of Work with the Equipment (including the assembly and installation as described in Exhibit N-3) shall be as stated in Exhibit A the applicable Scope of Work (the "Purchase Amount"), which is fixed and not subject to escalation; provided, however that the purchase price for each Unit shall not exceed those amounts set forth on Exhibit A. The Purchase Amount shall be subject to increases or decreases only as provided set forth in Section 5.3 for Change Orders with respect to the Scope of Work approved in accordance with Article XI. The Purchase Amount shall be complete compensation for Seller to perform its obligations under this Agreement.

5.2   Taxes and Contributions.

5.2.1   Seller’s Responsibility for Personnel Taxes.  Seller Each party assumes full responsibility for and agrees to pay all contributions and taxes payable under all Applicable Laws pertaining to social security laws, unemployment compensation laws and income tax laws as they apply to Seller’s and Vendor’s employees engaged in the performance of the Scope of Work. Seller acknowledges that Purchaser has no responsibility for such taxes as they apply to Seller, Seller’s employees or the employees of Vendors. itself and its employees or agents resulting from the performance of such party’ obligations under this Agreement or a Scope of Work.

5.2.2 Seller’s

5.2.2   Purchaser’s Responsibility for Taxes.  Seller is Purchaser shall be responsible for taxes arising out of its performance of the Work including import duties (if any), harbor taxes, personal and corporate taxes. [ The Purchase Amount excludes any US federal, state or local jurisdiction imposed taxes imposed as a result of the purchase by Purchaser of the Equipment under this Agreement.  Such taxes shall include taxes on property, license privilege, sales, use, excise, gross receipts, valued added, or similar tax taxes which may now or hereafter be applicable to, measured by, or imposed upon with respect to the transaction, Seller’s Scope of Work, its sale, its value, its presence in such taxing jurisdiction or its use, or any services performed in connection therewith. Such taxes are for the account of Purchaser and in connection with this Agreement and the associated Scopes of Work.  Purchaser agrees to pay any such tax when due or reimburse Seller within 25 days after the date of Seller’s invoice to Purchaser for any such tax which it is required to pay.  Purchaser further agrees] Should Purchaser be exempted from any such tax it shall provide Seller with certification prior to transfer of title of such Work, or at the time the certification is obtained, whichever first occurs.

5.2.3 Not Used.

5.2.4 Tax Penalties. Seller further agree to pay any tax, interest, penalty, fines, costs, losses and expenses (including, without limitation, court costs and attorney’s fees) of whatever kind, which Purchaser may incur, be may be incurred or required by law to pay be paid, or be liable for as a result of, arising from, in connection with, related to or based on any failure of Purchaser to withhold any amounts from any payments made or any amounts which Seller fails to pay in connection with, as a result of, arising from or based on the Scope of Work or otherwise comply with this Section 5.2.2 5.

5.3   Changes to the Purchase Amount. The Purchase Amount may only be adjusted by Change Order pursuant to Article XI. Seller’s entitlement to an increase in the Purchase Amount shall be conditional upon:

- Seller having used reasonable endeavors to mitigate the cost increase (except for Purchaser’s exercise of options);

- Seller having given notice Notice of the need for an increase in accordance with the terms of this Agreement; and

- the cost increase not being attributable to Seller’s default.

5.4   Cancellation. [To be discussed.]

5.4.1  Cancellation by Purchaser For Convenience.  Once an Order has been entered and accepted, Purchaser may not cancel the Order for convenience.  Seller may not cancel for convenience except as set forth in Section 5.5.

5.4.2  Cancellation For Breach.  Either party may cancel this Agreement because of a Event of Seller Default or Event of Purchaser Default, as the case may be.

5.4.3.  Effect of Cancellation.  In the event either party cancels this Agreement or a portion of a Scope of Work, the[The following terms shall govern cancellation occur:

- Seller shall immediately cease all work on the canceled portion of the Scope of Work, cancel all orders for components and supplies relating to the canceled Scope of Work on best terms available (whether pursuant to Seller’s rights under its agreements with its Vendors or otherwise) and return to the stock of its Vendors any reusable components and supplies. Purchaser shall have the right to require completion of;

- If Purchaser cancels the Agreement or any portion of the Scope of Work canceled;

- If Purchaser cancels Units ordered pursuant to this Agreement, Purchaser shall pay to Seller a net cancellation charge (the “Net Cancellation“Cancellation Charge”) which is equal to the Cancellation Charge total of the values set forth in Exhibit I at the time Purchaser issues a cancellation Notice to Seller less:

- any amounts previously paid with respect to the canceled Scope of Work; and

- credits for components and supplies of the canceled Scope of Work that are returned to Seller’s or Vendor’s stock.

The cancellation charge (the “Cancellation Charge”) shall not exceed the values set forth in Exhibit I at the time Purchaser issues a cancellation notice to Seller;

In the event Purchaser cancels the Agreement for its convenience, Purchaser shall pay as a net cancellation charge the applicable Cancellation Charge less any amounts previously paid or refund of any amounts overpaid with respect to this Agreement (the “Net Cancellation Charge”). Purchaser shall pay the Net

- Purchaser shall pay such Cancellation Charge to Seller within ten (10) business days of determination of the charge Cancellation Charge by mutual agreement of the parties.  Any dispute regarding the amount to be paid not resolved within thirty (30) days of a notice the Notice canceling this Agreement or all or a portion of the Scope of Work will be resolved pursuant to the provisions of Article XXVI hereof; and

Upon cancellation, the

- The work in progress and other supplies identified as the material or Equipment which was specifically produced for this Agreement and canceled shall be the property of Purchaser (title shall pass to Purchaser upon Purchaser’s payment of the Cancellation Charge) and shall be disposed of according to Purchaser’s instructions.] [acceptable?].

- 5.4.2 Marketing Agreement. Not applicable.

5.5   Suspension of Work.

5.5.1   Purchaser shall be entitled to suspend at any time the carrying out of the whole or any part of the Scope of Work.

5.5.2 In the event Purchaser suspends the Agreement, Seller shall be entitled to a partial payment of the Purchase Amount, based on the percentage completion of the suspended Unit or Units.

5.5.3  Seller shall during any suspension store, preserve, protect and otherwise secure and protect the Equipment and advise Purchaser of such.

5.5.4Upon Purchaser rescinding such a suspension, unless such suspension was issued in accordance with Section 5.5.5, Seller may submit a request for an equitable adjustment for all reasonable costs associated with such suspension in the Purchase Amount and the affected [Installation Date ] in accordance with Section 10.2.

5.5.5 Seller shall not be entitled to an equitable adjustment as a result of a suspension directed by Purchaser nor shall it be eligible for a payment in accordance with Section 5.5.2 if such suspension is necessary by reason of default (including but not limited to default under Section 17.2 on the part of Seller; or to cause proper or safe execution of the Scope of Work, unless (i) or (ii) arose from any act or default of Purchaser.

5.5.6Upon Purchaser lifting a suspension, Seller shall examine the Scope of Work and make good any deterioration or loss in the suspended Scope of Work.  Seller in its request for an equitable adjustment in accordance with Section 5.5.4 may request a Change Order for additional compensation for such inspection and making good except that Seller shall not be entitled to such increase if such defect, loss or deterioration was a result of poor workmanship, defects in material or failure to protect and preserve the suspended Scope of Work in accordance with good industry practice.

5.5.7If Purchaser suspends an Order placed pursuant to this Agreement for more than [nine (9) consecutive months], Seller may terminate this Agreement for its convenience.  Before taking such action, Seller must give Purchaser the option by written notification to rescind the suspension.  If Purchaser does not rescind the suspension within seven days of receipt of the notice, the affected Order, shall be canceled. [The Equipment produced in connection with the Order shall be the property of Purchaser and shall be disposed of according to Purchaser’s instructions so long as Purchaser compensates Seller for the work completed as of the time of cancellation.]

ARTICLE VI.  PAYMENT TERMS

6.1   Payment of Purchase Amount.

6.1.1   Payment.  Upon Acceptance of a Unit, Seller shall invoice Purchaser for the Purchase Amount related to that Unit and/or the associated Equipment and services. Payment of the Purchase Price for the Unit Amount shall be due within ten (10) days of receipt of the invoice.

6.1.2	Payment for O & M Spare Parts. Payment of the O & M Spare Parts Amount, to the extent Purchaser orders O&M Spare Parts, shall be due and payable by Purchaser to Seller within thirty (30) days of:

(i)	Seller’s proper delivery of all of the O&M Spare Parts to the Delivery Point in accordance with the terms of the applicable Change Order or separate purchase agreement issued hereunder; and

(ii)	Purchaser's receipt of a properly prepared an invoice for such O & M Spare Parts Amount.

6.2   Payment Disputes.  Payment shall not prejudice the right of Purchaser to protest or question the correctness thereof or compliance of the Scope of Work or any portion thereof with this Agreement or prejudice or constitute a waiver of any right of Purchaser hereunder.  Any amount questioned by either party and found to be in such party's favor shall be refunded or paid, as appropriate.  In the event an amount is withheld because of a dispute, and it is subsequently determined that the disputed amount or a portion of the disputed amount was due and payable, interest shall accrue at the Interest Rate commencing on the date the payment would have been payable if the dispute had not occurred.  Seller’s acceptance of partial payment of the Purchase Amount shall not be deemed to constitute a waiver of the right to receive amounts which are then in dispute, and Seller and Purchaser shall use their best efforts to resolve all disputed amounts as soon as practicable.  Any undisputed amounts not paid when due shall bear interest at the Interest Rate.

6.3   Payments Withheld or Offset. Intentionally Deleted.

6.3.1 Payments Withheld. Purchaser may withhold payment or a portion thereof in an amount and to such extent as may be reasonable necessary, subject to the dispute resolution provisions of Article XXVI, to protect Purchaser from loss because of:

6.4   Intentionally Deleted.

(a) defective work or Equipment not remedied pursuant to Section 9.5 or the warranty provisions of Article XIV or the failure of Seller to perform work or provide Equipment in accordance with the provisions of this Agreement;

(b) third party suits, stop notices or liens for which Seller is liable under this Agreement, whether directly or pursuant to any indemnification obligation hereunder, (other than those provided for by insurance, bonds or other security) made on or filed with Purchaser or with respect to the Site or the project and not cleared by Seller by payment, deposit or otherwise to the reasonable satisfaction of Purchaser within ten (10) days after receipt by Seller of written notice from Purchaser requesting such action; and

(c) uninsured damage to Purchaser or Vendor which results solely from Seller’s failure to obtain or maintain the insurance required by the provisions of Article XIX or from any action or inaction by Seller or any Vendor which excuses any insurer from liability for any loss or claim otherwise covered by insurance.

6.3.2 Payment of Subcontractors. Seller shall promptly pay, in accordance with the terms and conditions set forth in the respective subcontract, each Vendor the amount to which said Vendor is entitled. Seller shall, by an appropriate agreement with each Vendor, require each Vendor to make timely payments to its laborers, contractors and Vendors in a similar manner.

6.4 Not Used..

6.5 Notices of Nonpayment. If Purchaser receives written notice from any Vendor of Seller that Seller has failed to pay such Vendor for labor, materials, services and/or equipment related to the Scope of Work, Purchaser may, upon thirty (30) days notice to Seller, withhold payment from Seller in the amount claimed by the Vendor as due and owing, unless Seller notify Purchaser in writing within such thirty (30) days that Seller disputes the Vendor's claim. Purchaser may continue to withhold such amount until Purchaser receives written notice from such Vendor that such amount has been paid in full by Seller

6.5   Intentionally Deleted.

6.6   Lien Release.  Seller represents that all amounts reflected on invoices submitted by Seller for payment are accurate, just, due and owing under the terms of this Agreement. Purchaser shall not be required to make a Milestone Payment Amount unless such invoice is accompanied with the conditional waiver of liens as set forth in Exhibit S-1 or the applicable Scope of Work.  Seller represents that all services, equipment, materials and information for which Seller seeks payment are free and clear of liens, claims, security interests and encumbrances arising in favor of Seller and its Vendors, and other persons or entities able to make a claim by reason of having provided labor, materials or equipment relating to performance of this Agreement or any portion thereof.  Seller agrees and represents that in submitting an invoice, Seller waives and releases all liens, claims, security interests and other encumbrances arising in favor of Seller by reason of having provided labor, materials or equipment relating to performance of this Agreement or any portion thereof, to the extent of such invoice.  In the case of payment of the Retention Amount, Seller shall not be entitled to payment of such Retention Amount unless and until Seller submits to Purchaser an affidavit in the form set forth in Exhibit S.] Notwithstanding the foregoing, Seller shall maintain a lien on any Equipment that has not been paid for by Purchaser in full and Purchaser acknowledges and agrees that such lien exists and will execute and/or record any documentation requested by Seller to evidence said lien.

6.7  Invoices.

6.7.1 Contract Reference.  Each invoice will reference CONTRACT # __________ and shall].

6.7.2 Address for Invoices. Invoices will be mailed or hand carried to :

[Enron, ---------, Houston, Texas  77002, Attn: ---------------].  In the event this address is going to change, Purchaser shall promptly provide Seller with prior Notice such change.  The date Attn: ]

Purchaser anticipates that this address may change, and will notify Seller of such change, prior to the change.

6.7.3 Date of Receipt. Date of receipt of invoice by Purchaser will be evidenced by date stamp, or other generally accepted date receipting system.

6.8   Method of Payment.  Payment will be made by wire transfer unless otherwise requested by Seller.  Payments to the Seller shall be made to the following address:

[]

6.9   Payments Not Acceptance of Work.  No payment made by Purchaser hereunder shall be considered or deemed to represent that Purchaser has inspected the work or Equipment or checked the quality or quantity thereof or that Purchaser knows or has ascertained how or for what purpose Seller has used sums previously paid, and shall not be deemed or construed as an approval or acceptance of any work or Equipment or as a waiver of any claim or right Purchaser may have hereunder.  All payments shall be subject to correction or adjustment in subsequent progress reviews and payments. [Discuss]

ARTICLE VII.  EFFECTIVE DATE, COMMENCEMENT OF THE WORK PURCHASE ORDERS

7.1 Effective Date. The Effective Date of this Agreement is _____.

7.2 Commencement of Work.

7.1  Purchase Orders.  Purchaser shall provide Seller with a Purchase Order (an “Order”) in substantially the form of Exhibit __ setting forth the quantity and specifications of the Equipment or services it would like to purchase pursuant to this Agreement.  The parties will execute a Scope of Work setting forth the accepted terms of the Order, the associated deliverables by each party, the performance schedule under which the parties will operate to achieve delivery of the relevant Equipment and services, the agreed upon Specifications and the Purchase Amount.  The performance schedule set forth in the Scope of Work shall include a date on which Seller shall commence work upon receipt of an Order [procedure to be defined].. [If this is a single contract, this section is not applicable].

ARTICLE VIII. RELATIONSHIP OF PURCHASER AND SELLER

8.1 Status of Contractors. Seller shall perform and execute the provisions of this Agreement as independent contractor, and none of Seller or their subcontractors, nor any of their respective employees or agents shall be deemed for any purpose to be an agent, servant, employee or representative of Purchaser. Seller shall be solely responsible for the performance of the Work, and the Work shall be performed by Seller according to their own methods and at their own risk, subject only to compliance with the provisions of this Agreement.

ARTICLE VIII.  INTENTIONALLY DELETED

ARTICLE IX.  INSPECTION AND CORRECTION OF WORK

9.1   Inspections. Seller shall provide Purchaser and Lender, or their designated representatives access to the Scope of Work at all times wherever in preparation or progress and shall work closely with Purchaser in performing this Agreement.  Purchaser, or its designated representative, shall have the right from time to time during this Agreement and during normal business hours to audit, observe, inspect, examine, review and test Seller’s performance of this Agreement; provided, however that Purchaser has provided Seller with ten (10) days written notice of such desire to audit, observe, inspect, examine, review and or test, Seller’s performance of this Agreement.  Purchaser's rights to inspect under this Section 9.1 shall include but not be limited to manufacturing schedules; compliance with Specification Specifications; workmanship; dimensional tolerances; production tests; production inspections; assembly of components; panel inspection and testing; or witnessing testing of Equipment at any stage of design, procurement, production, or manufacture at Seller’s work workplace or those of its Vendors to verify that the Equipment conforms to the specified requirements of this Agreement. However, any observance, inspection or review of performance of this Agreement shall not constitute or be deemed to be actual control or a right to control Seller, its employees, agents, personnel, Affiliates, or Vendors.  Purchaser's inspection of any part of the Equipment shall in no way affect Seller’s obligations obligation to perform the Scope of Work in accordance with the Specification Specifications and all other terms of this Agreement, and any audit, examination, inspection, review, or testing by Purchaser shall not constitute acceptance or prejudice, be a waiver, or be deemed to be a waiver of any of Purchaser's rights hereunder or of its rights to reject defective performance of this Agreement or release Seller from any obligation under this Agreement.

9.2   Resident Facilities. If reasonably requested by Purchaser, Seller will provide facilities as reasonably available for a resident quality representative in Seller’s work and those of its major component vendors Intentionally Deleted.

9.3   Quality Plan.  Seller shall maintain a quality plan compliant with ISO 9001, 1994 and with the quality assurance plan set forth in Exhibit J, detailing:

(i)	specific authorities and responsibilities;

(ii)	procedures, methods and work instructions; and

(iii)	inspection and test plans.

In the event of a conflict between Exhibit J and ISO 9001, 1994 the higher standard of the two (2) shall prevail.  [acceptable? Discuss Timing]

9.4   Notice.  Seller shall provide not less than fourteen (14) days notice Notice prior to any of the witness or hold points as set forth in Exhibit R.  Seller shall not proceed past an established hold point prior to the date for such hold point specified in the advance notice Notice of such hold point given by Seller to Purchaser, unless Purchaser has witnessed the activity or given written approval to proceed past the hold point.  In the event Seller provides the appropriate advance notice Notice to a hold point and, Purchaser does not must either witness the hold point or give written notice Notice to Seller releasing the hold point, Seller shall be granted an appropriate extension to the respective Guaranteed Installation Date within ten (10) days or be deemed to have automatically given such release.

9.5   Correction of Equipment.  Prior to Acceptance, Seller shall, at its sole cost and risk, promptly correct any part of the Equipment which is defective or not in accordance with this Agreement, regardless of the stage of its completion or the time or place of discovery of such defects and regardless of whether Purchaser has previously paid for or accepted such part of the Equipment through oversight or otherwise. Seller shall replace or correct such defective work or condition such that the Equipment is in accordance with this Agreement, including the Specification Specifications.  Seller may repair (making an item functional, but not necessarily conforming the work to its original specification) Specifications) the Equipment or a portion of the Equipment only with Purchaser's written consent which will not be unreasonably withheld.

9.6   Intentionally Deleted

9.6 Not Used.

9.7   Release for Delivery.  In addition to other conditions set forth in this Agreement, prior to Seller performing any Equipment export packing and prior to actual shipment, Seller shall, at least seven (7) days in advance, request in writing to Purchaser's Representative for release to ship such Equipment.  Purchaser's approval shall not be unreasonably withheld provided Seller has met the requirements of this Agreement.[compare to 3.10.3 and 3.3(d)]

ARTICLE X.  DELIVERY AND PERFORMANCE

10.1   Delivery of Documentation.  Immediately following the acceptance of an Order, the parties shall meet to establish a document review plan and schedule. Any delay by Seller to submit such documentation in accordance with the schedule shall extend the date by which Purchaser must perform its obligations, but shall not serve as a basis for a Seller requested Change Order.  [Seems better to build into the Purchase Order process if we go that route]

10.2   Delivery and Installation of Equipment.

10.2.1   Establishment of Delivery, Installation and Acceptance Dates. Each Order Scope of Work shall specify the expected dates of Delivery (“Delivery Date”), Installation (“Installation Date”) and Acceptance Dates(“Acceptance Date”) for each Unit and its associated Equipment. Seller shall (i) cause the Equipment to be delivered to the Delivery Point in undamaged condition in accordance with the Specification and the Order Specifications on or before the Delivery Date, (ii) use commercially reasonable efforts to install the Equipment in accordance with Exhibit N-3, (“Installation Completion”) ] on or before the Installation Date, and (iii) and conduct and satisfactorily complete the Performance Tests at the Site on or before the Acceptance Date.  Seller may employ a Vendor to carry out the delivery of the Equipment and/or the installation services.

10.2.2   Delivery Restrictions.  Seller shall use appropriately licensed and insurable carriers in a commercially reasonable manner. Delivery of each Unit shall be considered complete when the Unit is delivered (and other such items of Equipment as necessary so as to not impede the continuous progress of completion of the [Facility]) applicable Facility) to the Delivery Point in a complete and undamaged condition.  Purchaser shall have the right to inspect the Equipment for completeness, condition and packing prior to loading on Seller’s carrier.  Purchaser shall have the right to inspect the Equipment for completeness and condition upon delivery to the Delivery Point as applicable for the purposes of determining actual delivery.  Purchaser reserves the right to reject damaged Equipment at any location.  In the event a portion of the Equipment is damaged or defective upon delivery to the Delivery Point, delivery will not be considered to have occurred, unless as determined by Purchaser:

(i)	such damage will not prevent erection of such Equipment and/or Unit; and

(ii)	Seller is able to repair or replace such damaged Equipment without delaying or interrupting assembly, erection and testing of the Equipment; and

- Such damage once repaired by Seller will not adversely affect the performance, reliability, or longevity of the Unit.

10.2.4 Not Used.

10.2.5

10.2.3  Extensions of the Installation Date.  A Delivery Date,

10.2.5.1 A Deliver, Installation and Date or Acceptance Date may only be extended by Change Order.  Seller’s entitlement to an extension of time shall be conditional upon:

(a)	Seller having used reasonable endeavors to mitigate the delay;

(b)	Seller having given notice in accordance with the terms of this Agreement; and

(c)	the delay not being attributable to Seller’s default.

10.2.6 Not Used.

10.3 Not Used.

10.3.1 Not Used.

10.3.2 Not Used

10.3   Intentionally Deleted.

[

10.4  Performance Guarantees.

10.4.1   Heat Rate Guarantee.  Seller guarantees that the Heat Rate heat rate as measured for each of the Units

as demonstrated during the Performance Test, shall be __BTU/kWh (the “Heat Rate”). In the event the Units exceed this Heat Rate exceeds the Minimum Heat Rate Guarantee, Seller shall take all necessary actions to correct, retest the deficient Unit and cause the deficient Unit to meet the Minimum Heat Rate Guarantee.  Failure to meet the Heat Rate Guarantee shall prevent Acceptance, unless Purchaser explicitly waives this guarantee in writing.

10.4.2   Electrical Output Guarantee.  [to come]

10.4.3   Emissions Guarantee. [to come]

10.4.4   Water Consumption Guarantee. [to come]

10.5     Not Used.

10.5.1 Not Used.

10.5.2 Not Used.

10.5.3 Remedy for Failures to Meet Performance Guarantees.  The failure to achieve the Performance Guarantees performance guarantees set forth in Section 10.4 by the Acceptance Deadline [to be defined] Date shall constitute a default under this Agreement.

10.8

10.6   Testing.

10.8.1

10.6.1   Seller Presence at Tests. Seller shall have the right to be present or to have a representative present at the Performance Tests.  Purchaser shall provide Seller with a thirty (30) days initial notice Notice and a five (5) days confirmation notice Notice in advance of the Performance Test.

10.8.2

10.6.2   Test Results. Upon the completion of each Performance Test, Purchaser will issue a Performance Test Certificate setting forth the results achieved during such test.  In the case of multiple Performance Tests, performance shall be measured by the most recent Performance Test.

10.8.3

10.6.3   Consumable Spare Parts During Retests.  The cost of consumable spare parts during retests caused by Seller’s failure to achieve the Heat Rate Guarantee shall be to Seller’s account.

10.9

10.7   Acceptance.  Upon the successful completion of the Performance Tests for a Unit, Seller shall submit a certificate Performance Test Certificate to Purchaser indicating that a Unit has achieved the Performance Standards and it ready for Acceptance.  Purchaser shall within five (5) days of receipt of such certificate, either Performance Test Certificate, sign such certificate acknowledging concurrence or reject such certificate specifically stating the reasons for such rejection. Acceptance for each Unit (and its associated Equipment) shall occur upon the issuance of the acceptance (“Acceptance”).  Notwithstanding the foregoing, Acceptance of the last Unit to be installed in a Facility shall occur when all of the following have occurred:

(a)	the issuance of a Performance Test Certificate by Purchaser as a result of the Unit having met the [Performance Standards]. Acceptance of the last Unit to be installed in a Facility shall occur when all of the following have occurred: ;

(a) the issuance of a Performance Test Certificate by Purchaser as a result of a Performance Test indicating that the final Unit has met the [Performance Standards];

(b) all O & M Manuals

(b)	all O & M manuals and special tools required hereunder shall have been delivered by Seller to Purchaser;

Seller has delivered to Purchaser a waiver of liens in form as shown in Exhibit-S that have been or could have been placed upon the Equipment and that there are no outstanding claims of Seller or any Vendor with respect to the Equipment for that particular Facility;

- all of the Units in the Facility have achieved Installation Completion, and there are no punch list items remaining to be completed.

10.10

10.8  Manufacturing Slots.  Prior to the acceptance of an Order, Seller will identify the manufacturing slots in Seller’s manufacturing schedule and Seller shall not change the manufacturing slots without Purchaser's prior written agreement. Purchaser shall only withhold such written agreement if, based upon the reasons given by Seller and verified by Purchaser, Purchaser believes that such change would result in a delay of the Units.  [Not sure that we can agree to this and even if we do it should be moved into the purchase order discussion.]

ARTICLE XI.  CHANGE ORDERS

11.1

1.1   Adjustment of Purchase Amount.  The Purchase Amount shall be subject to adjustment in accordance with the terms of this Agreement solely for (a) Purchaser-directed changes in the Scope of Work (b) changes in the Scope of Work proposed by Seller and approved by Purchaser (c) a Change in Law (d) Force Majeure, or (e) suspension by Purchaser.

11.2   Purchaser Requested Change Order.  If Purchaser either party desires to make any change in the Scope of Work (a "Change Order") including, without limitation, any alteration in the Scope of Work, (which whether by way of additions, modification or omission is not intended to cover that which a prudent Seller should have provided as part of the Scope of Work) Purchaser shall advise Seller, and Purchaser and Seller that party shall advise the other party, and the parties shall consult concerning the need for the Change Order, and the estimated cost and impact on the delivery date set forth in Section 10.2, Delivery Date and the Purchase Amount. Thereafter, Purchaser either party may request, and Seller shall upon receipt of such request prepare promptly thereafter receive, a detailed estimate of the cost of such change, taking into account the effect of such change on the Scope of Work and other agreed upon and contemplated Change Orders.  Purchaser shall review Seller’s estimate, and if Purchaser accepts or the parties otherwise If the parties mutually agree as to the Change Order, it shall be endorsed by Purchaser executed by the parties.  Thereafter, the parties shall promptly adjust the delivery date set forth in Section 10.2, and Delivery Date, the Purchase Amount [and any other Exhibits requiring adjustment to reflect the Change Order][?].  In the event Seller proceeds with any proposed changes in the Scope of Work prior to execution of a Change Order, Seller shall do so at its own risk.  Purchaser has no obligation to pay Seller for any additional cost and Seller is not entitled to any extension of time for performance as a result of any change implemented by Seller without an executed Change Order.

11.3   Seller Requested Change Order. If Seller determines that a condition or the occurrence of an event requires a change in the Scope of Work, Seller shall within fifteen (15) days of being aware of the occurrence or condition of the event prepare and deliver to Purchaser a request for a Change Order which shall describe such condition or event in detail. Within fifteen (15) days following delivery of such request, or such other period as may be agreed upon by the parties, Seller shall specify the adjustment to the Scope of Work, the delivery date as set forth in Section 10.2 and/or the Purchase Amount requested by it. Following receipt of such request, Purchaser shall determine whether any changes to the Scope of Work, the delivery date set forth in Section 10.2 and/or the Purchase Amount shall be effected, but failure by Purchaser to approve any such changes shall not affect or modify any of Seller’s obligations hereunder or cause an increase in the Purchase Amount and/or extension of the delivery date. If Seller propose changes in the Scope of Work to Purchaser, Seller shall not make such changes without receiving the prior written consent of Purchaser which shall be reflected on a Change Order, in accordance with the procedures as described in Section 11.2 Intentionally Deleted.

11.4   Other Change Order.  Except as otherwise provided by Sections Section [3.8(c)], if after the date of this Agreement there shall be any change of or in Applicable Laws Change in Law that will require a material change in the Specification Specifications, Seller shall prepare a Change Order form in accordance with the provisions of Section 11.3 11.2.  Upon Purchaser's consent, which shall not be unreasonably withheld, such Change Order shall be implemented.

11.5   Disputes.  In the event of an unresolved dispute regarding a Change Order, the parties agree that the matter shall be submitted to expedited arbitration in accordance with Section 26.

11.6   Change Order Pricing.

11.6.1   Method of Pricing.  All changes to the Agreement shall be either lump sum, or unit price.  If either method cannot be agreed upon, the additional work shall be paid on a cost plus basis.

11.6.2   Cost Plus Basis.  The following procedures will be used for all calculations of cost plus basis Change Order Orders:

- For all labor up to and including Project Manager, engineers, designers and foreman actually engaged in scope change work, Seller will receive their actual payroll plus fifteen percent (15%) thereof for overhead and profit, plus employer's actual contribution or payment for insurance coverage rated on basis of payroll, together with social security and unemployment tax or other employer's tax contribution based payroll.  Time sheets for direct labor expended in the performance of scope change on cost plus basis, will be approved daily by both Seller’s Project Manager and Purchaser's Representative. No cost plus payment will be made for the services of the superintendent or other supervisory or administrative personnel unless specifically authorized and specifically approved by Purchaser's Representative on an individual case basis; and

- Actual material costs (as evidenced by invoices from suppliers or vendors showing Seller as purchaser, plus ten per cent (10%) thereof for Seller’s overhead and expenses plus any applicable sales or use taxes assessed and paid in conjunction with such material purchases; and

- Charges for use of equipment shall be by agreement of Purchaser's Representative and Seller’s Project Manager, which agreement shall be noted on Purchaser's authorization for such work.

- Charges for third party shop equipment or services as evidenced by their invoices, plus five percent (5%) thereof.

- All such billings for work on the cost plus basis shall comprise the total of charges accumulated under subparagraphs (a) through (d) above and be supported by certified daily payroll records approved by both Seller’s Project Manager and Purchaser's Representative, a detailed list of equipment and material used and any third party invoices.

- Should Seller perform any scope change without advance written authorization from Purchaser's Representative, as specified above, such work will be at Seller’s expense.

- Modifications or changes in the Specification Specifications which are within the general scope of the Agreement documents may be made at any time by Purchaser's Representative written order to Seller.

ARTICLE XII.  INTENTIONALLY OMITTED

ARTICLE XIII.  ORDER OF PRECEDENCE

13.1   Order of Precedence.  This Agreement shall be read as a whole and in the event of a conflict between documents, the Articles of this Agreement shall take precedence over the Exhibits and a Scope of Work shall take precedence over this Agreement and the Exhibits.

ARTICLE XIV.  WARRANTY

14.1   Seller’s Warranty.

14.1.1   Warranty.  Seller warrants that for a period of twelve months following the Acceptance Date (the “Primary Warranty Period”): [Discuss effect of Acceptance delays not caused by FCE on warranty term]

(a)	the Equipment and all other materials and articles furnished hereunder are new,  not repaired (except as permitted by Purchaser) and of suitable grade for the purpose intended, and are free from defects in design materials, manufacture and workmanship;

(b)	the Scope of Work was performed in a good and workmanlike manner and in accordance with the degree of care, skill and diligence consistent with industry standards; and

- the Equipment conforms to the Specification Specifications and other material requirements of this Agreement;.

14.1.2   Warranty Clarification.  Seller shall have no obligation for correction, repair or replacement of the Equipment in accordance with this Article XIV to the extent that a defect is the result of:

(i)	assembly, use or service of the Equipment or any relevant part thereof by Purchaser or its contractors other than in conformance with Seller’s or their Vendor's specifications, manuals or written instructions (except as specifically set forth in this Agreement); or

(ii)	a Purchaser directed change in the design or construction of the Equipment which Seller reasonably disputes as not being in accordance with good workmanship or generally accepted professional engineering standards, provided that Seller has given Purchaser written notice Notice of its dispute prior to performing any such change and such dispute ultimately is resolved in Seller’s favor.; or

(iii)	[degradation in accordance with Seller’s degradation curves included in the Specifications.]

Seller also shall have no obligation for defect in the Equipment under this Section 14.1.2 to the extent that, after the commencement of the Primary Warranty Period to the extent such defect arises out of Purchaser failing to notify Seller within a reasonable time after an Equipment defect becomes apparent, not to exceed thirty (30) days from the date supervisory level personnel of Purchaser responsible for the Facility become aware of such defect.

14.1.3   Warranty Breach Notice.  In the event Purchaser determines that a defect exists, Purchaser shall notify provide Seller with Notice of such a defect in writing (fax notification followed by mailed notice) Notice) describing the nature of the breach.

[14.2   DFC Module Warranty.]

14.3   Remedy.

14.3.1   Obligations, Responsibilities and Recourse.  For twelve months following Acceptance (the “Primary Warranty Period”) During the Primary Warranty Period, if Seller’s warranties (other than Seller’s warranty under Section 14.2) are breached, Seller shall repair, replace, and/or correct the applicable portion of the Scope of Work such that it meets the requirements of this Agreement immediately on an expedited basis and at no cost to Purchaser.  Seller shall provide a service engineer to begin corrective action on the Equipment as soon as reasonably possible after receipt by Seller of Purchaser's notice Notice referred to in Section 14.1.4 14.1.3 but not later that five (5) days after receipt of such notice Notice.  Seller shall as its sole expense disassemble, remove, replace and reinstall the Equipment to the extent necessary while minimizing the downtime required for Seller to perform its Warranty warranty obligation.  Purchaser shall provide Seller with full and free access to the Equipment to perform its warranty obligations under this Agreement, so long as such access does not unreasonably interfere with operation of the Facility.  Any change to parts or equipment that would alter conformance with the Specification Specifications may be made only with prior written approval of Purchaser in accordance with the terms of Article XI hereof.  If, after notification of such defect in materials or workmanship, Seller shall unreasonably delay to commence, continue or complete making good such defect(s), Purchaser may then, following written notice to Seller, correct such defect(s) in accordance with this Agreement, and Seller shall be liable for all reasonable costs, charges and expenses incurred by Purchaser in connection with such reasonable repair or replacement and shall forthwith pay to Purchaser an amount equal to such costs, charges and expenses upon receipt of invoices certified by Purchaser.  In an emergency where delay would cause serious risk of loss or damage, Purchaser may take such actions as necessary to mitigate such risk and correct the deficiency with oral notice followed up immediately with written confirmation of the notice to Seller in accordance with Section 14.1.4.  Such emergency actions shall be to the account of Seller.

14.3.2   Continued Warranty on Corrections or Repairs Performed During the Primary Warranty Period.  With respect to any portion of the Equipment corrected, repaired, modified or replaced as a result of a defect manifesting during the Primary Warranty Period, Seller shall warrant such portion of the Equipment in a like manner for a period of twelve (12) months from the date of such modification or correction (the "Extended Warranty Period"), but in no event shall the Extended Warranty Period extend more than twelve (12) months beyond the expiry expiration of the Primary Warranty Period.

14.3.3   Extension of Warranty Due to Unavailability.  Notwithstanding Section 14.2.1 14.3.2, the Primary Warranty Period or Extended Warranty Period shall be extended by a period equal to the period during which the Units were unable to operate due to Seller failing to perform one or any of its obligations.

14.4   Vendor Warranty.  Seller shall be responsible for enforcing the warranties of all Vendors through the Primary Warranty Period, or, if applicable, the Extended Warranty Period.  In the event of Seller insolvency or Purchaser's termination of Seller for default, Vendor warranties shall automatically be assigned to Purchaser.  Any Vendor warranties that are still in existence at the end of the Primary Warranty Period, or the Extended Warranty Period, as the case may be, shall automatically be assigned on such date to Purchaser.  Thereafter, Seller shall provide reasonable assistance to Purchaser in connection with the enforcement by Purchaser of any Vendor warranty.

14.5   Limited Warranty.  THE WARRANTIES CONTAINED AND REMEDIES FOR BREACH OF WARRANTY CONTAINED IN THIS AGREEMENT ARTICLE XIV ARE THE EXCLUSIVE WARRANTIES AND REMEDIES BY SELLER APPLICABLE TO THE EQUIPMENT AND IS THE ASSOCIATED SERVICES AND ARE EXPRESSLY IN LIEU OF ANY OTHER WARRANTIES, EXPRESSED OR IMPLIED, INCLUDING ANY IMPLIED WARRANTY OF SATISFACTORY QUALITY (MERCHANTABILITY) OR FITNESS FOR A PARTICULAR PURPOSE, OR ANY OTHER WARRANTY EXPRESSED OR IMPLIED AGAINST VICES OR DEFECTS, LATENT OR OTHERWISE.  SELLER NEITHER ASSUMES NOR AUTHORIZES ANY OTHER PERSON TO ASSUME FOR IT ANY OTHER WARRANTY OBLIGATION IN CONNECTION WITH THE EQUIPMENT OR ANY PART THEREOF.

14.6   Defective Equipment.  Notwithstanding the foregoing, Seller shall have no obligation hereunder if the Equipment becomes defective in whole or in part as a result of repairs not made by Seller (unless Seller have defaulted in making such repairs), or as a result of the Equipment not having been operated and maintained in accordance with Seller’s written operating limitations and maintenance instructions, or accepted industrial practice.

14.7   Termination of Warranty.  In the event that Purchaser or a third party undertakes major unauthorized alterations or repairs to the equipment (other than normal maintenance as set out in Seller’s instruction manuals, approved emergency repairs, and replacing defective parts with Seller approved spares) without Seller’s written consent, any warranty applicable to the Equipment adversely affected by such alterations or repairs shall be terminated.  If a defect covered by the warranty is discovered by Purchaser and Purchaser does not:

(i)	immediately take reasonable action to mitigate the damage consequent to the occurrence of the defect; and

(ii)	allow Seller to correct the defect,

Seller shall not be responsible for repair of that part of the damage attributed to Purchaser's failure to take such action.

14.8   Damage to Other Facility Equipment.  Seller shall be responsible for replacing/repairing damage to any part of the Units caused by a failure of the Equipment during the Primary Warranty Period, or Extended Warranty Period as the case may be.  In the event that an Equipment failure during the Primary Warranty Period or Extended Warranty Period causes damage to portions of the Facility other than the Unit, Seller shall, in addition to repairing the Unit, be responsible for the deductibles for physical loss or damage associated with Purchaser's operating insurance.  Seller’s liability for the deductible shall be the lesser of the actual deductible or $500,000.  In the event the Equipment is of new technology, and as such is not insurable under Purchaser's operating insurance, Seller at their expense shall be responsible for all damage to the Equipment and Facility arising out of an Equipment failure during the Primary Warranty Period, or Extended Warranty Period if applicable.

ARTICLE XV.  RISK OF LOSS AND TITLE

15.1   Risk of Loss.  Seller shall bear the risk of loss and damage with respect to the Equipment until Acceptance; provided, however, if Seller is required to perform any work on the Equipment after Acceptance, Seller shall reassume risk of loss and damage for such affected Equipment for the period that such later work is being performed.

15.2   Title.

15.2.1   Passage of Title.  Title to Equipment, drawings, specifications, O&M manuals and like materials will pass from Seller to Purchaser at Acceptance, unless Purchaser has paid more than fifty percent of the Purchase Amount prior to delivery to the Delivery Point, in which case title passes to Purchaser upon delivery of the Equipment to the Delivery Point provided that Purchaser has paid the Purchase Amount in full.  Seller warrants that legal title to and ownership of the Equipment (including, subject to the use and disclosure limitations in Article XXI, all calculations, as-built, arrangements drawings, detailed engineering drawings and other drawings and documentation required by Purchaser in connection with the operation and maintenance of the Equipment) shall be free and clear of any and all liens, claims, security interests or other encumbrances when title thereto passes to Purchaser.

15.2.2   Infringement Cures and Defense.  In the event a suit or proceeding is brought against Purchaser, Purchaser, Lender, operator or their affiliates, (the "Patent Indemnities") for infringement of any patent, copyright, trademark, trade secret or other intellectual property right, Seller shall Indemnify and hold harmless Patent Indemnities, their authorized agent, and anyone directly or indirectly employed by either of them from and against all claims, damages, losses and expenses (including attorneys' fees) arising out of any infringement of patent rights or copyrights incident to the use or production of the Equipment or incorporation therein of any invention, design process, product or device not specified in the Agreement, and shall defend all such claims in connection with any alleged infringement of such rights.  Seller shall pay all costs and expenses of any such action or suit or threat thereof, including compensation and expenses of experts and counsel of its choice and selection and Seller shall also pay and hold Patent Indemnities free and harmless from expenses incurred or any damages or other sums awarded or assessed in any such action or suit including costs resulting from imposition of any injunction against Patent Indemnities. Patent Indemnities may be represented by counsel of their own selection and expense, but agrees to; provided, however that Patent Indemnities give Seller prompt notice of such claim, Seller has complete control over the defense of such claim and Patent Indemnities cooperate fully in the defense of any such action or suit and to furnish all the evidence in its control.

Nothing herein shall authorize Seller to settle any such suit or action as referred to in this Section 15.2.2 without prior authorization from the affected Patent Indemnitee if, by such settlement, the affected Patent Indemnitee shall be obliged to make any monetary payment, part with any property or any interest therein, to assume any obligation or restriction upon operation of the Equipment or Facility or production of electricity to be subject to any injunction or to grant licenses or other rights under its patent or other industrial or intellectual property rights.

In the event a Patent Indemnitee is as a result of such suit or proceeding prevented from using such alleged infringing Equipment or other deliverables, Seller shall at its option and expense:

(i)	obtain the right to continued use of the Equipment or other deliverables under this agreement Agreement;

(ii)	correct or modify the infringing aspect of the Equipment or other deliverables under this Agreement so that it becomes non-infringing; or

(iii)	replace the infringing Equipment or other deliverables under this Agreement with equivalent non-infringing Equipment or other deliverables.

THIS SECTION IS AN EXCLUSIVE STATEMENT OF ALL THE DUTIES OF THE PARTIES RELATING TO PATENTS INTELLECTUAL PROPERTY AND DIRECT OR CONTRIBUTORY PATENT INFRINGEMENT OR MISAPPROPRIATION AND OF ALL THE REMEDIES OF PURCHASER RELATING TO ANY CLAIMS, SUITS, OR PROCEEDINGS INVOLVING PATENTS.  Compliance with this Section as provided herein shall constitute fulfillment of all liabilities of the parties under the Agreement with respect to patents, copyright, trademark, trade secret or other intellectual property rights.

15.3   Seller’s Drawings for Use by Purchaser.  All drawings, documents, engineering and other data furnished or to be furnished by Seller (other than proprietary data furnished by Seller and Vendors) in performing the Scope of Work may be used by Purchaser, Purchaser's operation or subsequent owner for the purpose of constructing the Facility, including but not limited to operation, maintenance, repair and alteration of the Equipment.  In the event any information covered by Section this 15.3 includes intellectual property rights, proprietary information, copyrighted information of a third party, or any information or property requiring a license to use, manufacture, sell, reproduce, distribute by any means, perform publicly or display such material, Seller shall secure the necessary copyright, license or release to allow Purchaser, Purchaser's operation or subsequent owner to use such information for the purposes stated in the preceding sentence.  Purchaser agrees to abide by the terms of any such license or release.

15.4   Licensing Procedure.  Seller grants Purchaser a non-exclusive, irrevocable license to use the Equipment, software and hardware supplied under this Agreement for operating, maintaining and repairing the Facility.  Purchaser shall have no right to the source code; provided, however in the event Seller or Seller’s vendor its applicable Vendor discontinue maintenance of such software, Seller shall on a best efforts basis attempt to obtain such source code for Purchaser.  The non-exclusive license granted herein to Purchaser may transferred by Purchaser (and Purchaser's operator for the sole purpose of operating the Facility), Lender(s), or successor to subsequent owners of the Facility.

ARTICLE XVI.  INTENTIONALLY OMITTED

ARTICLE XVII.  DEFAULT

17.1   Event of Default by Seller.  Seller shall be in default hereunder upon the occurrence of any one of the following events, which shall be events of default (each an "Event of Seller Default") if not cured within thirty (30) days following delivery to Seller of a notice of Notice describing such event from Purchaser, or, if not curable in such thirty (30) Day day period, if Seller has not commenced the cure within such period as agreed by Purchaser and Seller and does not thereafter diligently pursue such cure to completion as agreed; provided that the event described in paragraph (d) below shall be an Event of Seller Default upon its occurrence, with no cure period:

(a)	Seller shall have assigned or transferred this Agreement or any right or interest herein except as expressly permitted by this Agreement;

(b)	any representation made by Seller in this Agreement shall have been materially false or misleading when made;

- Seller shall have defaulted in its performance under any material provision of this Agreement, including the failure to achieve Milestones;

- Seller’s performance is such that it has failed to achieve Acceptance on or before the Acceptance Deadline Date for a Unit or Units.[Discuss. This shouldn’t be grounds for default].

(e)	any proceeding is instituted against Seller seeking to adjudicate Seller as a  bankrupt or insolvent, or Seller make a general assignment for the benefit of its creditors, or a receiver is appointed on account of the insolvency of Seller, or Seller file a petition seeking to take advantage of any other law relating to bankruptcy, insolvency, reorganization, winding up or composition or readjustment of debts and, in the case of any such proceeding instituted against Seller (but not by Seller), such proceeding is not dismissed within sixty (60) days of such filing.

17.2   Purchaser's Remedies Against Seller. The provisions of Article XXVI hereof notwithstanding, and without limitation of Purchaser's rights, Purchaser or its assignee shall have the right to terminate this Agreement or any order entered into pursuant to this Agreement (in whole or in part) by delivery of a notice of termination to Seller, in addition to any rights and remedies that may be available at law or in equity or as provided herein Intentionally Deleted.

17.3   General Obligations.  [to be discussed]

17.4   Payment Obligations.

17.4.1   Determination of Obligations.  [to be discussed]

17.4.2   Damages and Expenses. [to be discussed]

17.5   Events of Default by Purchaser.  Purchaser shall be in default hereunder upon the occurrence of any one of the following events, which shall be events of default (each an "Event of Purchaser Default") if not cured within thirty (30) days following delivery to Purchaser of a notice Notice of such event from Seller or if not curable in such thirty (30) day period, if Purchaser has not commenced the cure within such period and does not thereafter diligently pursue such cure, provided that the event described in paragraph (d) below shall be an Event of Purchaser Default upon its occurrence:

(a)	Purchaser shall have assigned or transferred this Agreement or any right or interest herein except as expressly permitted by this Agreement;

(b)	any representation made by Purchaser in this Agreement shall have been materially false or misleading when made;

(c)	Purchaser shall have defaulted in its performance under any material provision of this Agreement; or

(d)	any proceeding is instituted against Purchaser seeking to adjudicate Purchaser as a bankrupt or insolvent, or Purchaser makes a general assignment for the benefit of its creditors, or a receiver is appointed on account of the insolvency of Purchaser, or Purchaser files a petition seeking to take advantage of any other law relating to bankruptcy, insolvency, winding up or composition or readjustment of debts and in the case of any such proceeding instituted against Purchaser (but not by Purchaser) such proceeding is not dismissed within sixty (60) days of such filing.

17.6   Seller Remedies. The provisions of Article XXVI hereof notwithstanding, if an Event of Purchaser Default shall have occurred and be continuing, Seller shall have the right to terminate this Agreement by delivery of a notice of termination to Purchaser, in addition to any rights and remedies that may be available at law or in equity. In the event of Purchaser Default under Section 17.5(d) based upon an action or proceeding instituted against Purchaser, such notice of termination by Seller shall not be given until sixty (60) days after such filing Intentionally Deleted.

ARTICLE XVIII.  FORCE MAJEURE

18.1   Failure to Perform Due to an Event of Force Majeure.  Subject to the terms of this Article XVIII, either party shall be excused from performance and shall not be considered to be in default with respect to any obligation hereunder, to the extent its failure of performance is due to an Event of Force Majeure.

18.2   Events of Force Majeure.  Events of Force Majeure shall be limited to the circumstances set forth in clause 18.4 but only if, and to the extent:

(i)	such circumstance is not within the reasonable control of the party affected;

(ii)	such circumstance, despite the exercise of reasonable diligence, can not be prevented, avoided or removed by such party;

(iii)	such event materially adversely affects (in cost and/or time) the ability of the affected party to fulfil fulfill its obligations under the Agreement;

(iv)	the affected party has taken all reasonable precautions, due care and reasonable alternative measures in order to avoid the effect of such event on the affected party's ability to fulfill its obligations under the Agreement and to mitigate the consequences thereof;

(v)	that such event is deemed as a Event of Force Majeure under any related project document(s); and

(vi)	such event is not the result of any failure of such party to perform any of its obligations under the Agreement, provided however that each such circumstance invoked by a party as affecting it's ability to perform shall be an Event of Force Majeure if such party has acted in a reasonable and prudent manner.

18.3   Notice of Force Majeure.  As soon as possible following the date of commencement of any Event of Force Majeure, if either party desires to invoke such Event of Force Majeure as a cause for delay in the performance of any obligation hereunder or as potential adjustment of the Purchase Amount, it shall promptly (but not later than seventy-two (72) hours upon learning of such Event of Force Majeure), advise provide the other party in writing with Notice of such date.  Notices shall be in accordance with Section 25.1. Within seven (7) days, Seller the affected party shall provide in writing to the other party a description the event and reasonable alternative measures which the affected party has taken in order to avoid the effect of such event on such party's ability to fulfill its obligations under the Agreement and to mitigate the consequences thereof, and the nature and expected duration of such Event of Force Majeure. Seller shall provide additional information concerning the event as reasonably requested by Purchaser (including, without limitation, updating of any information already provided under this Section 18.3).  Within a reasonable time following the date of termination of such Event of Force Majeure, the party having invoked such Event of Force Majeure as a cause for such delay or potential adjustment of the Purchase Amount shall submit to the other party as soon as practicable, reasonable proof of the nature of such delay and its effect upon the Guaranteed Installation Date or the basis for an adjustment of the Purchase Amount.  The burden of proof to demonstrate that a Force Majeure event has occurred and affects the claiming parties ability to perform, rests with the claiming party. The parties will meet within ten (10) days after receipt of the notice Notice by the unaffected party to discuss appropriate measures to mitigate the impact of the Event.  The parties shall thereupon consult with one another concerning the effect of such Event of Force Majeure and an extension of the Guaranteed Installation Date described in Sections 10.2 or 10.3 or, if applicable, an adjustment in the Purchase Amount described in Section 5.1.1 shall be made by the parties to take into account such effect on the ability of Purchaser and Seller to reschedule project activities to avoid or minimize overall delays or additional costs resulting from the Event of Force Majeure.  The parties:

(i)	shall make all reasonable efforts to prevent and reduce to a minimum and mitigate the effect of any delay or potential adjustment of the Purchase Amount occasioned by any Event of Force Majeure including recourse to alternate acceptable source sources of services, equipment and materials and construction equipment; and

(ii)	shall use their best efforts to ensure resumption of normal performance of the Agreement after the occurrence of any Event of Force Majeure and shall perform their obligations to the maximum extent practicable as agreed between the parties.

18.4   Events of Force Majeure.  Subject to the provisions of Sections 18.2 and 18.5, an Event of Force Majeure shall mean the following:

(a)	explosions, fires, nuclear radiation contamination, hurricanes, earthquakes, floods, natural disasters, epidemics, other acts of God, and any other similar circumstances;

(b)	war and other hostilities (whether declared or not), revolution, public disorders, insurrection, rebellion, sabotage, acts of public officials or terrorist action;

(c)	any action or relative material inaction taken by any national or local government or judicial authority after the date of this Agreement, including without limitation any order, legislation, enactment, judgement, ruling or decision;

- national or regional strikes which are not specific to Seller’s manufacturing facilities (such strikes not being Force Majeure Events);

- Strikes at the Site not arising out of Seller’s performance of work at or near the Site;

- Accidents in transportation resulting from any of the Events of Force Majeure listed in Subsection 18.4 (a).

(g)	delays resulting from unforeseen extreme weather conditions.

18.5   Certain Events Not Excused.  Notwithstanding that an Event of Force Majeure may otherwise exist, the provisions of this Article XVIII shall not excuse:

(a)	late delivery of equipment or materials caused by Seller, or caused by any of the subcontractors of Seller if Seller could have avoided such late delivery by exercising all reasonable endeavors as a prudent equipment supplier;

(b)	late performance by Seller caused by Seller’s failure to engage qualified subcontractors and suppliers Vendors or to hire an adequate number of personnel or labor or by inefficiencies on the part of Seller.

(c)	failures or delays due to problems relating to the development of the fuel cell technology or the manufacturing process to produce the technology.

18.6   Continued Performance.  Upon the occurrence of any Event of Force Majeure, the parties shall endeavor to continue to perform their obligations under the Agreement so far as reasonably practicable and Seller shall during the period of such circumstances protect and secure the Works in such manner as Purchaser shall require. Seller shall notify Purchaser of the steps he proposes to take including any reasonable alternative means for performance of the Works not prevented by the Event of Force Majeure. a commercially reasonable manner.

18.7 Not Used

18.7   Intentionally Deleted.

18.8   Force Majeure - Delays.  If either party becomes unable to perform all or part of its obligations under the Agreement because of an Event of Force Majeure, and such party has properly invoked and observed the provisions of Section 18.3 in respect thereof, such party shall be permitted a delay in the performance of its obligations affected by the Event of Force Majeure and an extension of the Guaranteed Installation Date.

18.9	Force Majeure - Cost. Seller shall bear its own delay costs occasioned by any event of Force Majeure for the first ninety (90) Day period during the occurrence or continuance of each such Event of Force Majeure. If an Event of Force Majeure continues beyond such ninety (90) Day period, provided Seller has properly invoked and observed the provisions of Section 18.3 in respect thereof, Seller shall be entitled, subject to the provisions of Section 11.3, to recover costs occasioned by each such Event of Force Majeure which accrue after each such ninety (90) Day period pursuant a Purchase Amount adjustment in accordance with Section 5.5 and Article XI hereof. Intentionally Deleted.

ARTICLE XIX

ARTICLE XIX

[This article needs to be reviewed by FCE’s coverage provider – also much of it is not applicable – also subrogation waiver is harsh]

19.1   Insurance - General.  Seller shall procure at its own expense and maintain in full force and effect at all times throughout Seller’s performance under this Agreement to include Seller’s performance of its warranty obligation with responsible insurance carriers insurance as set forth in this Agreement.

19.1.1   All Risk.  Seller shall purchase and maintain insurance to the full replacement cost of the Equipment during the process of fabrication, in the factory, during transportation, installation and testing, until Acceptance.

19.1.2   Workers Compensation and Employers Liability Insurance.  Seller agrees to comply with workers compensation laws of each jurisdiction where the Scope of Work is performed, and to maintain a Workers Compensation and Employers Liability policy.   This policy shall be endorsed, if applicable, to provide all state coverage, alternate employer, voluntary compensation coverage and occupational disease with the limits set forth below. If the work is to be performed  on or near navigable U.S. waters, the policy shall include coverage for United State Longshoreman's and Harbor Worker's Act, Death on the High Seas Act, Jones Act, or their equivalent as required by the applicable laws in the jurisdiction where such work is performed.

Workers Compensation	Statutory

Employers Liability		$1,000,000 Each Accident

$1,000,000 Disease

Each Employee (Minimum)

19.1.3   Commercial General Liability Insurance.  Seller shall maintain Commercial General Liability Insurance, endorsed to provide coverage for: Explosion, Collapse and Underground hazards; Contractual Liability (particularly applicable to the provisions of the "General Indemnity" section of this Agreement); and Products and Completed Operations (for a minimum of one year after completion of the Scope of Work) with the following limits:

Bodily Injury and		$1,000,000 Combined Single Limit

Property Damage		Each Occurrence, (Minimum)

19.1.4   Hull and Protection and Indemnity Insurance.  Seller shall ensure that if any owned or non-owned watercraft of any kind is used for performance of the Scope of Work, Hull and Protection and Indemnity Insurance shall be provided for the vessels in the amounts as follows:

Hull			Full replacement value of the watercraft.

P&I			$1,000,000 Each Occurrence or the full value of the vessel, whichever is greater.

Such insurance may be provided by the vessel operator, by the vessel charter agreement, or by Seller as Seller deems appropriate.

19.1.5   Business Automobile Liability Insurance.  Seller shall provide Business Automobile Liability Insurance which shall include the following coverage for all owned, non-owned and hired vehicles:

Bodily Injury 	  	$1,000,000 Each Person  (Minimum)

$1,000,000 Each Occurrence (Minimum)

Property Damage 	$1,000,000 Each Occurrence (Minimum)

or

Bodily Injury and 	$1,000,000 Combined Single Limit

Property Damage 	Each Occurrence (Minimum)

19.1.6   Aircraft Liability Insurance.  If the Scope of Work necessitates the use of aircraft, Seller shall provide Aircraft Liability Insurance which shall be endorsed to provide coverage for non-owned as well as Guest Voluntary Settlement, with limits of:

Bodily Injury and	$10,000,000 Combined Single Limit

Property Damage	Each Occurrence.

Such insurance may be provided by the aircraft operator, by the aircraft charter agreement, or by Seller as Seller deems appropriate.

19.1.7   Excess Umbrella Liability Coverage.  Seller shall provide Excess Umbrella Liability coverage with minimum limits of:

Bodily Injury and	$5,000,000 Combined Single Limit

Property Damage 	Each Occurrence.

19.1.8   Vendors.  Seller shall require its Vendors and others connected with the Scope of Work  to provide and maintain insurance at all times during the period that their agreement related to the Scope of Work under this Agreement is in force and effect at the Vendor's, or other's own cost, with insurance limits which at minimum meets levels as required for similar contracts and is customary for the applicable industry.

19.1.9   Certificate of Insurance.  Within twenty (20) days of execution of this Agreement, Seller shall submit to Purchaser a certificate of insurance, in form satisfactory to Purchaser, evidencing that satisfactory coverage of the type and limits set forth hereinabove are in effect.  Policies providing such coverage shall contain provisions that no cancellation or material changes in the policies shall become effective except on sixty (60) days advance written notice thereof to Purchaser.  Irrespective of the requirements as to insurance to be carried as provided for herein, the insolvency, bankruptcy or failure of any insurance company carrying insurance of Seller, the failure of any insurance company to pay claims accruing, shall not affect, negate or waive any of the provisions of this Agreement including, without exception, the indemnity obligations of Seller.

19.1.10  Other Requirements.  Seller shall be responsible for the payment of all deductible and self insurance retention amounts with respect to the insurance required to be maintained by it pursuant hereto.  All Seller insurance shall:

(a)	Specify Purchaser’s Lender, and such other parties as Purchaser may require as additional insured for all insurance coverage other than Worker's Compensation Insurance, or its equivalent as required in jurisdictions other than the United States;

(b)	Provide that Purchaser shall have the right, but not any obligation, to pay any premiums if Seller shall fail to do so, and such payment of premiums by Purchaser shall be at Seller’s expense, either by direct charge or setoff;

- For all insurance coverage related to Scope of Work, waive any right of subrogation against Purchaser, Lender, their parent and affiliated companies and their directors, officers, employees and agents, and all other named and additional insured and any other right of the insurer to any setoff or counterclaim or any other deduction, whether by attachment or otherwise, in respect of any liability of Purchaser, Lender, or any other named or additional insured; and

(d) 	For all other insurance other than as stated in (c) immediately above, waive any right of subrogation against Purchaser, Lender and all other named and additional insured and any other right of the insurer to any setoff or counterclaim or any other deduction, whether by attachment or otherwise, in respect of any liability of Purchaser, or any other named or additional insured.

19.1.11  Vendor Waiver of Subrogation.  Seller agrees to require all policies of insurance which are in any way related to the Scope of Work and that are secured and maintained by Seller’s first tier Vendors to include clauses providing that each Underwriter shall waive its rights of recovery, under subrogation or otherwise, against Purchaser, Lender, their parent and affiliated companies and their directors, officers, employees and agents. In the event that an insurer of a second tier or below vendor attempts to exercise its rights of recovery under subrogation or otherwise, against Purchaser and Lender, their parent and affiliated companies and their directors, officers, employees and agents, Seller shall indemnify and defend Purchaser and Lender against such action if such action arises out of or is in any way related to this Agreement.

19.1.12  Compliance with Insurance.  Seller and their directors, officer, representatives, agents and employees shall comply with all the terms of the policies of insurance referred to in Section 19.1 and in any Delay in Start-Up and Business Interruption Insurance obtained by Purchaser.  Seller and their directors, officers, representatives, agents and employees shall comply with the procedures for claims, notification and administration under the aforesaid insurance policies and shall not do or omit to do anything which might render voidable policies of insurance or entitle insurers to avoid liabilities thereunder.  Seller shall ensure that all major subcontractors shall be subject to provisions identical to this Section 19.1.12.

19.1.13 Limitation.

19.1.13.1  In the event that Seller breaches its obligations under the first two sentences of Section 19.1.12 of the Agreement and such breach results in an insurer avoiding, in relation to Seller, any policy of insurance obtained by Purchaser pursuant to Section 19.2 of the Agreement, Seller shall not be regarded as an additional insured under such policy and any waiver of subrogation in favor of Seller included in that policy pursuant to Section 19.2 shall not apply.

19.1.13.2  In the event that any Subcontractor fails to comply with the procedures for claims notification and administration under any policy of insurance obtained by Purchaser pursuant to Section 19.2 of the Agreement or does anything which might render any such policy of insurance voidable or entitle insurers to avoid liability thereunder and as a result thereof an insurer avoids in relation to that Subcontractor any such policy of insurance, that Subcontractor shall not be regarded as an additional insured under such policy and any waiver of subrogation in favor of that subcontractor included in that policy pursuant to Section 19.2 of the Agreement shall not apply.

19.3 Not Used..

19.3.2 Not Used.

19.3.3

19.2    Primary Insurance.  All policies of insurance referred to in herein shall be endorsed to specify that for activities at the Site, they are primary to and not excess to or on a contributing basis with any insurance or self-insurance maintained by the Purchaser and Seller (and its affiliate) or any Subcontractors in respect of losses arising out of or in connection with the Works at the Site. Contractor's insurance under Section 19.1 shall be primary for losses away from the Site.

ARTICLE XX.  INDEMNIFICATION

20.1   Third Party.  SELLER AGREES TO INDEMNIFY, PROTECT, DEFEND, AND HOLD HARMLESS PURCHASER ITS DIRECTORS, OFFICERS, EMPLOYEES, AGENTS, AFFILIATES AND CONTRACTORS, AND THE DIRECTORS, OFFICERS EMPLOYEES, AGENTS, AND CONTRACTORS OF PURCHASER'S AFFILIATES, FROM AND AGAINST ANY AND ALL DEMANDS, LIENS OR OTHER ENCUMBRANCES ON PURCHASER OR ITS PROPERTY (INCLUDING THE FACILITY), CLAIMS, SUITS AND CAUSES OF ACTION OF THIRD PARTIES AGAINST PURCHASER AND ANY AND ALL LIABILITY, COSTS, EXPENSES, AND JUDGMENTS INCURRED IN CONNECTION THEREWITH (INCLUDING, WITHOUT LIMITATION, COURT COSTS AND ATTORNEY'S FEES), WHETHER ARISING IN EQUITY, AT COMMON LAW, OR BY STATUTE, OR UNDER THE LAW OF CONTRACTS, TORTS (INCLUDING, WITHOUT LIMITATION, NEGLIGENCE AND STRICT LIABILITY WITHOUT REGARD TO FAULT) PERTAINING TO PERSONAL INJURY OR PROPERTY CLAIMS, OF EVERY KIND OR CHARACTER, AND WHETHER OR NOT DUE IN PART TO PURCHASER'S CONCURRENT NEGLIGENCE OR OTHER FAULT, BREACH OF CONTRACT OR WARRANTY, OR STRICT LIABILITY WITHOUT REGARD TO FAULT, BASED UPON, IN CONNECTION WITH, RELATING TO OR ARISING OUT OF THE AGREEMENT OR SELLER’S ACTIONS OR INACTIONS UNDER THIS AGREEMENT, INCLUDING, WITHOUT LIMITATION, ANY FAILURE TO COMPLY WITH ANY APPLICABLE LAWS, RULES, REGULATIONS, ORDINANCES, ORDERS, CODES, RESOLUTIONS OR STANDARDS AND INFRINGEMENT OF ANY THIRD PARTY'S OWNERSHIP OF INTELLECTUAL PROPERTY RIGHTS, AND EVEN IF DUE IN PART TO PURCHASER'S CONCURRENT NEGLIGENCE OR OTHER FAULT, BREACH OF CONTRACT OR WARRANTY, OR STRICT LIABILITY WITHOUT REGARD TO FAULT; PROVIDED, HOWEVER, THAT SELLER’S CONTRACTUAL OBLIGATION OF INDEMNIFICATION SHALL NOT EXTEND TO THE PERCENTAGE OF DAMAGES OR INJURIES ATTRIBUTABLE TO PURCHASER'S NEGLIGENCE OR OTHER FAULT, BREACH OF CONTRACT OR WARRANTY, OR TO STRICT LIABILITY IMPOSED UPON PURCHASER AS A MATTER OF LAW.  THIS INDEMNIFICATION OBLIGATION SHALL APPLY REGARDLESS OF THE AMOUNT OF INSURANCE COVERAGE HELD BY SELLER, INCLUDING THAT UNDER ANY WORKER'S COMPENSATION ACT OR EQUIVALENT AS REQUIRED BY THE APPLICABLE JURISDICTION, DISABILITY ACT, OR OTHER ACT OR LAW WHICH WOULD LIMIT THE AMOUNT OR TYPE OF DAMAGES, COMPENSATION, OR BENEFITS PAYABLE BY OR FOR SELLER, AND SHALL NOT BE LIMITED BY ANY INSURANCE CARRIED OR PROVIDED BY SELLER IN ACCORDANCE WITH THIS AGREEMENT OR OTHERWISE.

20.2   Notice.  If any party entitled to indemnification hereunder (the "Indemnified Party") intends to seek indemnification under this Article from Seller with respect to any action or claim, the Indemnified Party shall give Seller notice prompt Notice of such claim or action upon the receipt of actual knowledge or information by the Indemnified Party of any possible claim or of the commencement of such claim or action, which period shall in no event be later than the lesser of:

(a)	fifteen (15) business days prior to the last Day day for responding to such claim or action; or

(b)	one-half of the period allowed for responding to such claim or action.

Seller shall have no liability under this Article XX for any claim or action for which such notice Notice is not provided, if the failure to give such notice Notice prejudices Seller.  Seller shall have the right to assume the defense of any such claim or action with counsel designated by Seller and reasonably satisfactory to the Indemnified Party; provided, however, that if the defendants in any such action include both the Indemnified Party and Seller, and the Indemnified Party shall have reasonably concluded that there may be legal defenses available to it which are different from or additional to those available to Seller, the Indemnified Party shall have the right to select separate counsel to assert such legal defenses and to otherwise participate. the obligation to cooperate with such defense.

20.3 Employees. Neither party nor its directors, officers, employees, agents, Affiliates or representatives, nor any independent contractor engaged by it in connection with the performance of this Agreement, shall be deemed an employee of the other party. Neither party shall bring any claim against the other party or its directors, officers, Affiliates, agents, representatives, employees or independent contractors with respect to any liability for compensation under an applicable State or Federal Worker's Compensation Act or equivalent as required by the relevant jurisdiction, including, but not limited to, Worker's Compensation and/or employer's liability claims of employees

20.3   Intentionally Deleted.

20.4   Survival of Obligation.  The duty to indemnify under this Article XX will continue in full force and effect notwithstanding the expiration or termination of this Agreement.

ARTICLE XXI.  NON-DISCLOSURE OF INFORMATION

21.1   Proprietary Information.  Any information concerning the parties which is designated in writing as proprietary and/or confidential and disclosed to the other party incident to the performance of Scope of Work pursuant to this Agreement is disclosed in confidence and the transferee shall not publish or otherwise disclose it to others without the written approval of the transfer or, provided, however, that nothing herein shall limit either party's rights to disclose data which:

(a)	was developed on its own or furnished to it prior to this Agreement without restriction;

(b)	becomes generally available to the public through no fault of either party; or

(c)	is received by either party from a third party without restriction and not in breach of this Agreement.

Furthermore Purchaser or Seller may provide any such information to any governmental authority having jurisdiction and asserting a right to obtain such information, but only to the extent required to do so by law. This clause shall survive the termination of this Agreement.

21.2   Press Releases.  Seller agrees that it is in Purchaser's interest to limit information of strategic value disseminated to the independent power industry regarding this Facility.  To the extent that Seller desires to issue press releases, advertisements in the trade press, tombstones in the financial or trade press then Seller must obtain Purchaser's written release to do so.  [Mutual approval] 21.3 Confidentiality. [Seller acknowledges that Purchaser's business is highly competitive and that Purchaser's books, records, documents and technical information concerning its products, equipment, services, processes, procurement procedures, pricing techniques, the names of and other information (such as credit and financial data) concerning Purchaser's customers and business affiliates, all comprise confidential business information and trade secrets of Purchaser which are valuable, special and unique proprietary assets. Seller further acknowledges that protection of Purchaser's confidential business information and trade secrets against unauthorized disclosure and use is of critical importance to Purchaser in maintaining its competitive position. Accordingly, Seller hereby agree that he will not, at any time during or after the term of this Agreement, make any unauthorized disclosure of any confidential business information or trade secrets of Purchaser or make any use thereof, except for the benefit of, and on behalf of Purchaser. However, Seller’s obligation under this Section 21.3 shall not extend to information which is or becomes part of the public domain or is available to the public by publication or otherwise through no wrongful act or omission or noncompliance with this Section by Seller or their agents. The provisions of this Section 21.3 shall survive the termination of this Agreement. Seller agrees and acknowledges that money damages would not be sufficient to remedy for any breach of this Section 21.3 by Seller, and Purchaser shall be entitled to specific performance and injunctive relief as remedies for such breach or any threatened breach. Such remedies shall not be deemed the exclusive remedies for a breach of this Section 21.3 by Seller but shall be in addition to all remedies available at law or in equity to Purchaser including recovery of damages from Seller. For the purposes of this paragraph, the term "Purchaser" shall also include affiliates of Purchaser.]

Seller shall deliver to Purchaser all Purchaser confidential information provided or disclosed to or used or acquired by Seller,

21.3   Return of Confidential Information. Both parties shall return to the other party such party’s confidential or proprietary information, including all information developed, derived, or created therefrom, or portions thereof, upon the earlier of:

(i)	the ending of the need for the information for performance of the Scope of Work; or

(ii)	Purchaser's such party's request;

(iii)	the completion of the Scope of Work for which it was provided, disclosed used or acquired; or

(iv)	termination or suspension of this Agreement.

Seller may retain a single copy of all information upon which its Scope of Work is based for record purposes only.  In the event Seller releases Purchaser's confidential information to a third party, Seller shall require such third party to enter into a confidentiality agreement similar to this Section 21.3 with Seller, and Seller shall retrieve all such released confidential information, including any and all copies of the confidential information and all information developed, derived, or created therefrom, upon the earlier of the events set forth above in this Section 21.3.

Neither party shall challenge the other party’s ownership rights in such confidential information.  No documents, data, materials or information available to Seller as set forth in this Section 21.3 or produced in whole or in part under this Agreement shall be the subject of an application for copyright by or on behalf of Seller without the prior written consent of Purchaser.

Either party shall be entitled to disclose the terms and conditions of this Agreement and any data or information acquired by it under or pursuant to this Agreement without the prior consent of the other party:

(a)	to any Affiliate of such party;

(b)	to potential engineering, procurement and construction contractors, and other such parties such parties in connection with the construction, operation, financing or operation of a Unit or Facility;

(c)	to potential Lenders and investors;

(d)	to the extent required by the rules of a relevant and recognized stock exchange;

(e)	to the extent required by law or pursuant to an order of any court of competent jurisdiction, provided that the original disclosing party is given notice and adequate time to seek a protective order applicable to the information before it is disclosed;

(f)	to any insurer under a policy of insurance required to be taken out by either party under the Agreement; or

(g)	to directors, employees, agents and officers of such party;

(h)	to Connecticut Resource Recovery Association, and other potential assignees

provided that the disclosing party determines in good faith that the recipient has a legitimate need to see such data or information, and the recipient has been made aware of and has agreed to be bound by the requirements of this Article XXI.

ARTICLE XXII.  ASSIGNMENT

22.1   Assignment by Seller.  This Agreement may be assigned by either party without the other party’s not be assigned by Seller without the prior written consent of Purchaser, which shall not be unreasonably withheld.

22.2 Assignment by Purchaser. This Agreement or any right or obligation contained herein (including the right to place an order), or any Order may be assigned by Purchaser without Seller’s consent to:

(i)	an Affiliate;

(ii)	a joint venture, partnership, or other similar entity in which Purchaser or Purchaser's Affiliate is a venturer, partner or participant;

(iii) Lender;

(iv)	the Owner of a Facility, including, but not limited to, Connecticut Resource Recovery Association;

(v) to

- any entity for the purposes of financing or sale of  a Facility, or for the construction of a Facility;

- a successor in interest by virtue of a merger or acquisition.

Except for (i) through (v) above, this Agreement may be assigned by Purchaser to other parties a party only upon the prior written consent of Seller the other party, which consent shall not be unreasonably withheld or delayed.  When duly assigned in accordance with the foregoing, this Agreement shall be binding upon and shall inure to the benefit of the assignee, and Purchaser the assignor shall have no further liability under this agreement Agreement; any other assignment by Purchaser shall be void and without force or effect.

22.3  Agreement with Lender. Seller agrees that if requested by Purchaser, Seller shall enter into a direct agreement with Lender under which Lender is permitted to "step into" this Agreement. Intentionally Deleted.

22.4 Assignment after Acceptance. Notwithstanding the foregoing, this Agreement (or any right or obligation arising hereunder) or any Order may be assigned without Seller’s consent following Acceptance.

22.4 Intentionally Deleted.

22.5 Direct Agreement with a Permitted Assignee. If an Order or a part of this Agreement is assigned in accordance with this Agreement, then, upon request, Seller shall enter into a contract directly with the permitted assignee (a “Facility Agreement”). The terms of the Facility Agreement shall be substantially the same as the terms of this Agreement and the Order, unless Seller agrees otherwise

22.5 Intentionally Deleted.

ARTICLE XXIII.  RELATIONSHIP OF THE PARTIES

23.1   Independent Contractor.  Seller undertakes performance of this Agreement as an independent contractor.  Nothing herein shall create a relationship of employer and employee, joint venture, or partnership between Purchaser and Seller, their agents, representatives, employees Affiliates, Vendors or subcontractors, for any purpose whatsoever.  Nothing herein shall create a relationship of principal and agent between Purchaser and Seller, their agents, employees, representatives or subcontractors.  Neither party shall have the authority to bind or obligate the other in any manner as a result of the relationship created hereby.  Purchaser shall not have the right to control the manner(s) or prescribe the method(s) by which Seller perform this Agreement.  Seller shall be wholly responsible for supervision and the methods of performance.  Seller is entirely and solely responsible for its acts and the acts of its agents, employees, representatives, Affiliates, and Vendors engaged in the performance of this Agreement.  Seller shall provide qualified Seller’s personnel who shall be and remain solely the employees of Seller, and at no time or in any manner shall said personnel be considered as or deemed to be employees of Purchaser.  Purchaser's general coordinative efforts, suggestions and procedures with respect to the Scope of Work and Purchaser's right of inspection, review and observation of the performance of this Agreement shall not make Seller or their employees, employees of Purchaser.

23.2   Responsibilities of Seller as Principal for its Employees.  Seller has complete and sole responsibility as a principal for its agents, Vendors and all other hires to perform or assist in performing the Scope of Work.

ARTICLE XXIV.  INTENTIONALLY DELETED LIENS AND CLAIMS

Seller shall not directly or indirectly create, incur, assume or suffer to be created by it or any Vendors, employees, laborers, materialmen or other suppliers of goods or services any claim, lien, security interest, charge or other encumbrance on the Equipment or any part thereof or interest therein and Seller shall immediately notify Purchaser of the assertion of any lien, claim, security interest or other encumbrance against the Equipment or any part thereof. Seller shall remove immediately any lien, claim, security interest or other encumbrances against Purchaser, Purchaser's property, or Purchaser's Affiliates' property, or the Equipment arising in favor of Seller or their Vendors or other persons or entities by reason of having provided labor, materials or equipment related to performance of this Agreement and to pay any damages, costs, losses and expenses (including, without limitation, court costs and attorneys' fees) of whatever kind which Purchaser may incur, be required to pay or be liable for as a result of, in connection with, arising out of, or related to any such lien, claim, security interest or other encumbrance. In the event of a lien from a Vendor, supplier or service provided is levied, Seller shall immediately post a letter of credit against such lien. Upon the failure of Seller promptly to pay or discharge any lien claim, security interest or other encumbrance as required hereby within twenty (20) days of notice of the existence thereof from any source, Purchaser may, but shall not be obligated to, pay or discharge such lien claim, security interest or other encumbrance and, upon the payment or discharge thereof, shall be entitled to recover from Seller the amount thereof together with all expenses incurred by Purchaser in connection with such payment or discharge.

ARTICLE XXV.  NOTICES AND COMMUNICATIONS

25.1   Notices.  Any notice pursuant to the terms and conditions of this Agreement shall be in writing and either:

(a)	delivered personally;

(b)	sent by certified mail, (return receipt requested);

(c)	sent by a recognized overnight mail or courier service with delivery receipt required; or

(d)	sent by confirmed facsimile transfer:

Commercial - Legal:

If to Seller:					If to Purchaser:

Either party may change its address or the person to be notified by a notice delivered in accordance with this section.

25.2   Effectiveness of Notices.  Notices shall be effective when received at the address specified.

25.3   Technical Communications.  Notwithstanding communications and notices the addresses as set forth in Section 25.1, the parties will route routine and technical communications as follows:

If to Seller:					If to Purchaser:

ARTICLE XXVI.  ARBITRATION [to be discussed]

[26.1   Negotiation of Disputes and Disagreements.  In the event of any dispute or disagreement arising out of or relating to the implementation or performance of this Agreement, which the parties hereto have been unable to settle or agree upon within a period of thirty (30) days after the dispute or disagreement arises, each party shall nominate a senior officer of its management to meet at a mutually agreed time and place not later than forty five (45) days after the dispute or disagreement has arisen to attempt to resolve such dispute or disagreement.  Should a resolution of such dispute or disagreement not be obtained within fifteen (15) days after the meeting of senior officers for such purpose, or if such meeting does not take place within sixty (60) days after the dispute or disagreement has arisen either party may then by notice to the other submit the dispute to arbitration in accordance with the provisions of Section 26.2.

26.2   Arbitration Resolution.  With respect to arbitration resolution, the parties agree that:

(a)	In the event of dispute between Purchaser and Seller concerning the interpretation of any provision of this Agreement or the performance of any of the terms of this Agreement such matter or matters in dispute shall be finally settled under the arbitration rules of the American Arbitration Association by three arbitrators, one appointed by each party, and the third, who shall be the chairman will be selected by the two appointed arbitrators and failing agreement by the chairman of the American Arbitration Association.  The language of the arbitration shall be English and the place of the arbitration shall be New York, New York;

(b)	The decision of the arbitrators shall be final and binding upon the parties;

(c)	If any dispute to be referred to arbitration under this Agreement raises issues which are, in the opinion of the Purchaser, substantially the same as or connected with issues raised in a dispute between any of the following entities (and their successor in title and assigns):

(i)	Purchaser; and

(ii)	Power Purchaser,

then such latter dispute shall constitute a "Related Dispute";

(d)	If a Related Dispute has already been referred to arbitration in accordance with arbitration provisions identical (mutatis mutandis) to this clause or, if the dispute under this agreement has already been referred to arbitration under this clause, then:

(i)	the dispute under this Agreement shall be referred to the arbitrators appointed to determine the Related Dispute; and

(ii)	the arbitrators shall have power to join one or more defendants or third parties or consolidate actions as provided by applicable law.

26.3   Continuation of Work.  Pending final resolution of any dispute other than a dispute over Purchaser's failure to pay the Purchase Amount in accordance with Section 6.1, Purchaser and Seller shall continue to fulfill their respective obligations hereunder.

ARTICLE XXVII.  LIMITATION OF LIABILITY

27.1   Maximum Liability.  Seller’s maximum aggregate liability for claims by Purchaser arising out of Seller’s performance of this Agreement whether arising from tort (including negligence), breach of contract or any other cause of action is limited to one hundred percent (100%) of the Purchase Amount; provided, however, that the foregoing limitation of liability of Seller shall not apply to the following:

(i)	under Article XX (Indemnification);

(ii)	under Article XXIV (Liens and Claims);

(iii) Section 3.8(a) and 3.8(b), (Compliance with Governmental Rules);

(iv) Section 5.2 (Taxes);

(v)	Article XIX obligation to maintain insurance;

(vi)	arising from or related to environmental harm caused by an action or inaction of Seller, its agents, employees or Vendors during the performance of the Scope of Work;

(vii)	resulting from the gross negligence or willful misconduct of Seller, their agents, employees or Vendors; or

(viii)	patent or copyright infringement in accordance with Section 15.2, or.

(ix) Article XXI (Non-Disclosure of Information).

which liabilities shall not be limited.

Additionally, any liability of Seller provided for by the proceeds of the insurance maintained pursuant to Article XIX shall not be counted toward any of the foregoing limitations of liability.

27.2   Consequential Damages.  [Except for liquidated damages specifically provided for herein], with respect to claims between the parties, in no event shall Seller be liable to Purchaser for special, indirect, or consequential damages of any nature whatsoever, including losses or damages caused by reason of unavailability of the Equipment, shutdowns or service interruptions, loss of use, loss of profits or revenue, inventory or use charges, cost of purchased or replacement power, interest charges or cost of capital or claims of Purchaser's customers, whether as a result of breach of contract, breach of warranty, tort liability (including negligence or strict liability), or otherwise, and whether arising before or after completion of the Scope of Work. The preceding shall not limit Seller’s obligation to indemnify Purchaser under Article __ for third party claims. In no event shall Purchaser be liable hereunder for special, indirect, or consequential damages of any nature whatsoever, including, but not limited to, loss of use, loss of profits or revenue, or inventory or use charges, whether as a result of breach of contract, breach of warranty, tort liability (including negligence or strict liability) or otherwise IN NO EVENT SHALL SELLER BE LIABLE TO PURCHASER FOR SPECIAL, INDIRECT, PUNITIVE, OR CONSEQUENTIAL DAMAGES OF ANY NATURE WHATSOEVER, INCLUDING LOSSES OR DAMAGES CAUSED BY REASON OF UNAVAILABILITY OF THE EQUIPMENT, SHUTDOWNS OR SERVICE INTERRUPTIONS, LOSS OF USE, LOSS OF PROFITS OR REVENUE, INVENTORY OR USE CHARGES, COST OF PURCHASED OR REPLACEMENT POWER, INTEREST CHARGES OR COST OF CAPITAL OR CLAIMS OF PURCHASER'S CUSTOMERS, WHETHER AS A RESULT OF BREACH OF CONTRACT, BREACH OF WARRANTY, TORT LIABILITY (INCLUDING NEGLIGENCE OR STRICT LIABILITY), OR OTHERWISE, AND WHETHER ARISING BEFORE OR AFTER COMPLETION OF THE SCOPE OF WORK. IN NO EVENT SHALL PURCHASER BE LIABLE HEREUNDER FOR SPECIAL, INDIRECT, OR CONSEQUENTIAL DAMAGES OF ANY NATURE WHATSOEVER, INCLUDING, BUT NOT LIMITED TO, LOSS OF USE, LOSS OF PROFITS OR REVENUE, OR INVENTORY OR USE CHARGES, WHETHER AS A RESULT OF BREACH OF CONTRACT, BREACH OF WARRANTY, TORT LIABILITY (INCLUDING NEGLIGENCE OR STRICT LIABILITY) OR OTHERWISE.

27.3   Releases Valid in All Events.  Releases, disclaimers and limitations on liability expressed herein shall apply even in the event of the negligence, strict liability, fault or breach of contract (including other legal bases of responsibility such as fundamental breach) of the party whose liability is released, disclaimed or limited.

ARTICLE XXVIII.  DRUG AND ALCOHOL-FREE WORKPLACE

The parties desire to provide a safe and productive work environment.  The parties believe that the use, possession and/or distribution of illegal/unauthorized drugs and alcohol presents a serious threat to the safety of employees, visitors and others at the job site, or other premises owned, leased, or occupied by Purchaser.  All Seller’s and Seller’s Vendors' and Subcontractors' employees associated with the Work under this Agreement must agree to compliance with Purchaser's drug and alcohol policy [Number 1200-2, dated September 11, 1995] including: [Discuss whether this section conforms to FCE’s current policy]

(1)	while on or entering the Site or other premises owned, leased, or occupied by Purchaser, search of personal and professional possessions, including but not limited to automobiles, trucks, briefcases, lunchboxes, and person for illegal drugs.  Failure to consent to such search shall be grounds for immediate removal from the Site or other premises owned, leased, or occupied by Purchaser;

(2)	drug testing at any time while on the Site or other premises owned, leased or occupied by Purchaser.  Failure to do so or failing any such test shall be grounds for immediate removal from the Site or other premises owned, leased, or occupied by Purchaser; and

(3)	failure of a Seller’s or Vendor's employee to agree and abide by these requirements will be grounds for immediate removal from the job site or other premises owned, leased, or occupied by Purchaser from any work associated with the Scope of Work under this Agreement.

[ACCEPTABLE?]

ARTICLE XIX.  MISCELLANEOUS

29.1   Validity and Enforceability.  The invalidity or unenforceability of any portion or provision of this Agreement shall not affect the validity or enforceability of any other portion or provision.  Any invalid or unenforceable portion or provision shall be deemed severed from this Agreement, and the balance of the Agreement shall be construed and enforced as if the Agreement did not contain such invalid or unenforceable portion or provision.  Notwithstanding the provisions of the preceding sentence, should any term or provision of this Agreement be found invalid by any governmental authority having jurisdiction thereof, the parties shall immediately renegotiate in good faith such term or provision of the Agreement to eliminate such invalidity.

29.2   Governing Law.  This Agreement, its interpretation and any disputes relating to, arising out of or connected with this Agreement, shall be governed by the laws of the state of [New York], without regard to its conflicts of law provisions.

29.3   Entire Agreement.  This Agreement, and the Exhibits attached hereto constitute the entire agreement between the parties with respect to the subject matter hereof, and there are no oral or written understandings, representations or commitments of any kind, express or implied, not set forth herein.  This Agreement supersedes all prior agreements between the parties with respect to the subject matter hereof, except that this Agreement does not supercede the [Alliance Agreement, etc.]

29.4   Agreement Modification.  No oral or written modification of this Agreement either before or after its execution shall be of any force or effect unless such modification is in writing and signed by the party to be bound thereby.

29.5   Waiver.  The waiver by any party of any breach or failure to enforce any of the terms, covenants or conditions of this Agreement shall not in any way affect, limit, modify or waive the future enforcement of such terms, covenants or conditions.

29.6   Headings.  The headings contained herein are included solely for the convenience of the parties and are not to be used as a basis for interpreting the various sections of this Agreement.

29.7   Third-Party Beneficiaries.  The provisions of this Agreement are intended for the sole benefit of Purchaser and Seller, and there are no third-party beneficiaries other than assignees contemplated by the terms herein.

29.8   Counterparts.  This Agreement may be executed in counterparts, each of which when so executed and delivered shall be an original, and all of which, when taken together, shall constitute one and the same instrument.

29.9   Equal Employment Opportunity.  To the extent performance of any Scope of Work is performed in the United States, the parties hereto agree that the provisions of to comply with Applicable Laws regarding Equal Employment Opportunities including, if applicable Executive Order 11246, as amended, and the Rehabilitation Act of 1973 (Section 503, Public Law 93-112, as amended), the Vietnam Era Veteran's Readjustment Assistance Act of 1974, as amended (including the provisions of the "Equal Opportunity" clauses), and the regulations promulgated pursuant to the above, each of which are hereby incorporated into this Agreement by reference as if fully set out.

29.10  Cooperation on Site. To the extent Seller is required to perform services on Site it shall cooperate with other contractors on Site so as to coordinate work and schedules.

IN WITNESS WHEREOF, the parties have caused this Agreement to be executed as of the date and the year first above written.

[ENRON]							FUEL CELL FUELCELL ENERGY, INC.

Purchaser							Seller

By:  ____________________________			By:  ____________________________

Title:  _________________________			Title:  _________________________

Date:  __________________________ 			Date:  __________________________

Deletions appear as Overstrike text

Additions appear as Double Underline text