PACIFIC GAS AND ELECTRIC COMPANY
CHAPTER 1
METERING SYSTEM CONSTRAINTS

PACIFIC GAS AND ELECTRIC COMPANY
CHAPTER 1
METERING SYSTEM CONSTRAINTS

TABLE OF CONTENTS

A.	Introduction	2-1

B.	Overview	3-1

C.	Constraints Regarding Schedule and Costs – Revising Hours in an Existing Period or Changing Seasonal Boundaries	4-2

Cost	5-3

D.	Schedule and Costs – Adding a New Period	6-6

E.	Constraints Regarding Schedule and Costs – Combining Existing TOU Periods	7-8

F.	Constraints Regarding Schedule and Costs – Changing TOU Periods for Agricultural Customers only.	8-8

PACIFIC GAS AND ELECTRIC COMPANY

CHAPTER 2

METERING SYSTEM CONSTRAINTS

# Introduction

This testimony responds to issues related to programming TOU meters raised in the April 11, 2001 Assigned Commissioner’s Ruling (ACR).  The ACR directs PG&E to further address the constraints associated with reprogramming TOU meters and, specifically, why it would not be feasible to reprogram meters for some rate schedules before June1.  The ACR directs PG&E to include data regarding the number of meters that are currently installed and the times to reprogram these meters.  The ACR further directs PG&E to provide information indicating whether it can implement changes in TOU periods for agricultural customers only.

Revising TOU periods are discussed in four distinct scenarios:

- adding a new period,

- revising the hours in an existing period,

- combining existing TOU periods, and

- changing the seasonal boundaries.

# Overview

PG&E’s TOU meters are programmable measurement devices which store metered usage into pre-programmed, time and seasonal differentiated registers internal to the meter.  Changes to the parameters associated with these registers require reprogramming the meters.

Reprogramming requires:

- modification and testing of software used to accomplish meter reprogramming;

- distribution of that software and loading it into the laptop computers used by PG&E’s meter technicians;

- training the technicians so they understand and are able to test the successful reprograms;

- identification of the accounts and specific meters to be reprogrammed;

- dispatch the accounts and meters to be reprogrammed; and,

- field visits to reprogram the meters.

These activities are depicted in detail in Tables C-1 and C-2 (below)

A relatively small number of PG&E’s accounts (approximately 2,100) have hourly interval capability and phone based information retrieval systems.  The TOU time periods and/or seasons could be redesigned for these particular meters without physically reprogramming the meters, although billing system constraints exists (discussed in “Billing System Constraints”).  Should the time periods or seasons require modification for any portion of the remaining 171,400 TOU meters on TOU rate schedules, that portion would require field reprogramming.

PG&E currently has approximately 173,500 TOU meters installed on active TOU accounts.

| Customer Size/Schedule | TOU/Interval Meter Count |
| --- | --- |
| Greater than 500 kW E-19 Voluntary Small Commercial Agricultural Residential | 700 / 2,100 6,400 25,000 38,000 100,000 |
| Total | 173,500 |

# Constraints Regarding Schedule and Costs – Revising Hours in an Existing Period or Changing Seasonal Boundaries

The schedule and costs for field reprogramming TOU meters in order to revise the hours in an existing period (scenario 2, section A, above) or change seasonal boundaries (scenario 4, section A, above), are identical.  The following table outlines the specific tasks required, presents a timeline for the accomplishment of those tasks, and provides an estimated cost to reprogram a total of 10,000 meters.

Table C-1

Process to Reprogram In-Service TOU Meters

Up Front Work Only

Two processes are required before the field technicians can reprogram the new TOU rate schedule in our existing meters.  The two processes may be done concurrently.

| Process 1a) |  | Create and distribute one (1) new TOU rate schedule for one (1) meter type. See Table 2 for meter types. |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Assumptions: - An existing TOU meter type used and programmed at PG&E, no new meter types. - One (1) new TOU rate schedule is prepared for three (3) meter types (see Table 2) |  |  |  |  |  |  |
| - Step | Task |  | Worker(s) and time needed | # Cost |  |  |
| 1 | Change or add seasons, holidays, and create a new calendar |  | Software Engineer: 1 day per meter type | $2,400 |  |  |
| 1 | Modify TOU hours and/or add TOU time period to create new rate schedule. |  | Software Engineer: 1day per meter type 1 week total elapsed time | $2,400 |  |  |
| 2 | Load and test new software on Internet for Distribution |  | Software Engineer time: 2 days per meter type. 2 week total elapsed time | $4,800 |  |  |
| 3 | Develop and write instructions for Meter Technicians. |  | Software Engineer time: 2 days per meter type 4 week total elapsed time | $4,800 |  |  |
| 4 | Download new meter software into laptop computer. |  | Meter technician: Download software into 170 laptop meters. Two downloads to correct software errors. 2 weeks 6 weeks total elapsed time. | $34,000 |  |  |
| 5 | Overview and training on new software |  | 10 Supervisors, 4 Metering Specialists, 137 Meter Technicians and apprentices. 1 hour of Training per meter type 8 weeks total elapsed time. | $44,400 |  |  |
| All Steps of 1a) | Get a new TOU rate schedule prepared in three types of TOU meters so the meter technicians can begin meter work. |  | 8 weeks of elapsed time | $ 92,800. |  |  |

| Process 1b) Select Meter Data, Dispatch job orders, And Process MITSS Records |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Assumptions: - 10,000 Meter upload batch - 10% of the selected sites will require exception handling due to existing data discrepancies or on site Load Research equipment. |  |  |  |  |  |  |  |
| - Step |  | Task | Worker(s) and time needed | Cost |  |  |  |
| 1 |  | Identify meters / sites based on specific program criteria | Meter Engineer: 2 days to select meters for reprogramming | $1600 |  |  |  |
| 2 |  | Create MITSS upload file with data from EMI and LCIS | Programmers: 40 hours per upload | $3400 |  |  |  |
| 3 |  | Upload to MITSS - monitor EMI and MV90 population processes | Programmers: 20 Hours | $1700 |  |  |  |
| 4 |  | Fix EMI Exceptions - 10% of total | 48 hours EMI clerical time | $2400 |  |  |  |
| 5 |  | Manually enter Load Research exceptions - 10% of total | Meter Event Group Analyst: 70 Hours | $4410 per 1000 LR sites |  |  |  |
| 6 |  | Monitor Assign and Action process | Programmer : 40 Hours | $680 |  |  |  |
| 7 |  | Division Clerical - Print and Distribute Tags | Clerk: 128 hours | $6400 |  |  |  |
| 8 |  | Reentry of completed tags @ 25 per hour | 400 hours clerical time | $20,000 |  |  |  |
| 9 |  | MEG support for Division clerical data discrepancies, entry issues, questions | 20 hours MEG time | $1260 |  |  |  |
| All steps |  | Process 1b) | 4 Weeks total elapsed time | Total Process 1b) $41,840 per 10,000 meters |  |  |  |
| Process 2) Meter Technician Field Visits to Program New Rate |  |  |  |  |  |  |  |
| 1 | Field Visit to Program New Rate |  | Meter Technician: Unit Cost per Meter | $105 per meter |  |  |  |

Field work may begin after Process 1a) is completed and Process 2a) is completed through step 7.

Table C-2

Summary Cost Estimate for 10,000 Meters

To Be Programmed with a New TOU Rate

| This Estimate does not include Billing or Records Department Time |  |  |  |  |
| --- | --- | --- | --- | --- |
| Process 1a) | 8 weeks | 3 meter types |  | $100,000 |
| Process 1b) | Concurrent with 1a) |  |  | $410,000 |
| Process 2) | 4 weeks (after process 1) |  |  | $1,050,000 |
|  |  | Estimate |  | $1,560,000 |
| Process 1a) | 8 weeks |  | 3 meter types | $100,000 |
| Process 1 b) | Concurrent with 1a) |  |  | $410,000 |
| Process 2) | 4 weeks (after process 1) |  |  | $1,050,000 |
|  |  |  | Estimate | $1,560,000 |

In summary, PG&E’s processes require approximately 2 months to modify, test and distribute reprogramming software, train meter technicians and dispatch accounts and meters to be re-programmed, at which point PG&E’s meter technicians operating within normal work schedules (and deferring non-mandated, lower priority work) are able to visit and re-program approximately 10,000 meters per month.

Recognizing the urgency which this work could require, I estimate that an accelerated schedule, deferring all metering work (other than safety) for employees required for the reprogramming effort, could be developed which would:

- Reduce the up-front work (processes 1a and b) software modification, testing, distribution and work dispatch) from 8 weeks to 3 to 4 weeks (increasing costs from $510,000 to approximately $610,000); and,

- Increase the numbers of meters which are reprogrammed in the field to a monthly rate of 20,000 to 25,000 (increasing cost per meter from $105/meter to approximately $150/meter).

The limiting resource for field reprogramming is the availability of meter technicians.  Currently, there are 137 field metering technicians responsible for the installation, calibration and maintenance of all high-end electric meters used for billing purposes.  PG&E has no other workgroups trained to re-program TOU meters.  While training other classifications is possible, and contracting may be similarly possible, it is unlikely either alternative would assist in accelerating the re-programming effort for this summer.

In summary, PG&E could accomplish necessary up-front work on an accelerated schedule in approximately three weeks from the time it learns the TOU period requirements.  At that time, field reprogramming can begin at an absolute maximum of 20,000 to 25,000 meters per month.  If the TOU period requirements are obtained by May 1, 2001, a total of approximately 5,000 meters can be reprogrammed by June 1, 2001 at a total cost of approximately $1,360,000.

# Schedule and Costs – Adding a New Period

The schedule and costs for field reprogramming TOU meters in order to add a new TOU period (item 1, above) are identical to those discussed in section b), above.  There are however significantly increased challenges with metering associated adding a new TOU period.  In addition, billing system constraints exists (discussed in “Billing System Constraints).”

Table D-1

Types of TOU Meters

|  | Types of TOU Meters |  |  |  |
| --- | --- | --- | --- | --- |
| Meter Manufacturer | TOU Meter Type | % of in-service TOU Population | Maximum TOU Periods | Restriction |
| ABB | A1T and A1R | 27% | 4 |  |
| Schlumberger | MT100 | 28% | 3 |  |
| Schlumberger | MT200 | 11% | 4 | Single-phase only |
| Siemens | DCMS | 11% | 3 |  |
| Schlumberger | SVX and Vectron | 9% | 4 |  |
| Siemens | DXMS | 8% | 4 |  |
| General Electric | T90 and TM91 | 2% | 4 | 2/29/04 bug |
| ABB | EM2430 | 2% | 4 |  |
| Siemens | Quad4/4+ | 1% | 4 |  |
| General Electric | kV | 1% | 4 |  |
| TOTAL |  | 100% |  |  |

The first problem with adding a new TOU period is that (as shown in Table D-1, above) approximately 40 percent of PG&E’s TOU meters are only capable of retaining 3 TOU periods.  If a requirement to add a fourth TOU period is necessitated for accounts where one of these meters is present, a new meter would be required (in addition to the tasks outlined in Section C, above.  This would increase the cost for that account by approximately $300 (the cost of a new meter).  Other costs would be identical.

The second problem is PG&E’s meter readers use a hand-held recording device which is currently capable of recording only 3 TOU time periods.  It is not feasible to reprogram or acquire new meter reader hand-held recording devices for this summer.  An alternative method of obtaining the usage would be to assign lap-top computers to the meter readers for this purpose.  This would be feasible for a limited number of accounts where specific employees would be assigned to obtain the 4 period TOU reads.  For large numbers of (4) time period accounts (e.g., tens of thousands) substantial restructuring of, and additions to, PG&E’s meter reading workforce would be required.  I have not estimated those costs.

In summary, PG&E could accomplish necessary up-front work on an accelerated schedule in approximately three weeks from the time it learns the additional TOU period requirements.  At that time, field reprogramming and new meter installation can begin at an absolute maximum of 20,000 to 25,000 meters per month.  If tPhe additional TOU period requirements are obtained by May 1, 2001, a total of approximately 5,000 meters can be reprogrammed and/or installed by June 1, 2001 at a total cost of approximately $2,110,000.  Additional meter reading costs would also be incurred based on the number of accounts involved.

# Constraints Regarding Schedule and Costs – Combining Existing TOU Periods

PG&E believes no field reprogramming would be required.  Specifically, existing TOU periods would be billed at identical rates.  Thus, there are no metering related constraints.  Billing system modifications would address this scenario.

If reprogramming were required, the analysis in section C would apply.

# Constraints Regarding Schedule and Costs – Changing TOU Periods for Agricultural Customers only.

Assuming a requirement to change the TOU periods or seasons were required for PG&E’s 38,000 agricultural accounts, the costs and schedule analysis presented in section C would apply.

The expected schedule for a program of this magnitude would require approximately four to five months from the time the TOU periods were defined and cost approximately $4,500,000.

The most compressed schedule possible to accomplish this work would require approximately ten weeks from the time the TOU periods were defined and cost approximately $6,310,000.

If additional time periods were added to agricultural TOU rate schedules, the costs would rise as discussed in section D, above.