TO:  Distribution

FROM:  Jim Steffes

RE:  Follow-up from 5/8/00 Meeting

The following items are next steps in developing the Regulated Commodity risk management process.

- Undertake “Bridge analysis” of key rate curves

- Review the “Top 20” rate curves based on Net Position (listed in Scott Stoness’ 5/8 memo page 5).

- Review the “80/20” curves with pending deals (listed in Scott Stoness’ 5/8 memo page 6 plus any other relevant curves from unlisted deals).

- EES URM to provide to Government Affairs the rate curves and key regulatory assumptions within these rate curves by 5/12 (we did not set a date – Jim Steffes / Harry Kingerski / Scott Stoness need to discuss).

- Government Affairs identifies regulatory assumption issues with rate forecast by 5/19 (assumes 5/12 receipt of key regulatory assumptions).

- Exception resolution meeting on 5/22.

- Management report complete on 5/31.

- Develop Daily Position Report

- EES URM and Government Affairs to discuss DPR report design after 5/22 Exception meeting.

- EES complete first structure of DPR by 6/30.

- Begin Monthly Review Analysis of rate curves (begin one month from close of #1)

- Develop Quarterly Assessment of Net Position

I hope this properly captures the next steps.  If anyone wants to add or subtract from this process, please let me know.  Thanks.