Budget for Premium 2000 & Beyond 2000

1. Project Status

- Premium2000 phase 1 start:	2000 May

# Target CGC:		Pusan, Pohang, Kumi, Chongju, Daehan

Launch Date: 	2001 Feb 28

- Schedule change:	2001 Jan

Launch Date: 	Pusan & Pohang(2001 May 7)

Chongju & Kumi(2001 Jun 4)

Daehan(NA)

- Schedule change :	2001 Apr

Launch Date: 	Pusan & Pohang(2001 Jun 10)

Chungju & Kumi(2001 July )

- Post implementation starts: 2001 Jun 10

- Premium2000 Phase2: 7month

###### Target CGC: 		Choongnam, Chonnam, Kangwon, Iksan

Launch Date:		2002 Jan (Draft)

2. Budget Increase (Summary)

- Budget vs. Actual(Capital+Operation)			1US$=1300won

| (BWON) | Budget | Actual | Difference |
| --- | --- | --- | --- |
| Premium2000 phase1 | 13.8($10.6M) | 18.1($13.9M) | 4.3($3.3M) |
| ##### Premium2000 phase2 |  | 2.8($2.2M) | 2.8($2.2M) |
| Premium2000 sub total | 13.8($10.6M) | 20.9($16.1M) | 7.1($5.4M) |
| Beyond2000 | 3.5($2.7M) | 3.0($2.3M) | -0.5($0.4M) |
| TOTAL |  |  |  |

B. Budget vs. Actual(Financial View)

| (BWON) | Difference | Carried Over | Total |
| --- | --- | --- | --- |
| Premium2000 phase1 | 4.3($3.3M) | 0.6($0.5M) | 4.9($3.8M) |
| ##### Premium2000 phase2 | 2.8($2.2M) | 0 | 2.8($2.2M) |
| Premium2000 sub total | 7.1($5.4M) | 0.6($0.5M) | 7.7($6.0M) |
| Beyond2000 | 0.5($0.4M)) | 1.9($1.5M) | 2.4($1.8M) |
| Total |  |  | 10.1($7.8M) |

- Premium 2000 Phase1 Budget Increase : 4.9BW($3.8M)

A. Capital Budget			      3.5 BW($2.7M)

- Budget : 13.8 Billion Korean Won(BW)

- Projected Budget : 16.7 BW

(year 2000 : 11.2 BW,  year 2001 : 5.5 BW)

- Description for Budget increase

- Non-budgeted item:      	       1.7 BW

- Overage : 		              1.0 BW

- Others :   	                      0.8 BW

B. Operating budget                	1.4 BW($1.1M)

- First production month maintenance: 	0.9 BW

- Operation                            0.5 BW

- Premium2000 Phase2 Budget(Operation):2.8 BW($2.2M)

- 4 CGCs ERP Implementation : 		2.8 BW

5.  Beyond 2000  Budget Increase : 		2.4 BW($1.8M)

A. Capital budget				1.9 BW($1.5M)

- Budget : 3.5 BW

- Projected Budget : 3.0 BW

(year 2000 : 0.6 BW,  year 2001 : 2.4 BW)

- Description for Budget increase

- Unused portion from 2000 budget carry over : 1.9 BW

### B. Operating budget 			  	0.5 BW($0.3M)

Appendix: Detail

1. Premium 2000 Phase1				unit : thousand Korean Won

Original Budget (Approved BOD)			13,800,000

Projected Budget				       16,696,523

year 2000	 year 2001

Budget	 11,800,000 	 2,000,000

# Actual	 11,235,778 	 5,460,745

GAP	    564,222 	(3,460,745)

Not carried over

- Daehan reduction that should  have been in Budget      2,500,000

- Carry over from year 2000		                  564,222

396,523  Over Budget

|  |  | unit: thousand Won |
| --- | --- | --- |
|  | Year 2000 | year 2001 |
| Consulting | 5,363,346 | 2,822,149 |
| H/W | 2,139,018 | - |
| S/W | 2,799,283 | 1,866,188 |
| N/W | 309,560 | - |
| Others * | 624,571 | 772,408 |
| Total | 11,235,778 | 5,460,745 |
| * maintenance, leased line, office, adm. Etc |  |  |

2. Premium2000 Phase2(Choongnam, Kangwon, Chonnam, Iksan)								unit : thousand Korean Won

Implementation	Consulting	       2,593,998

other consulting	         240,000

total	             2,833,998

3. Beyond 2000					unit : thousand Korean Won

A. Original Capital Budget (Approved BOD)			   3,500,000

Projected Budget				          3,019,942

year 2000	year 2001

Budget	 2,500,000 	 1,000,000

Actual	   556,922 	 2,463,020

GAP	 1,943,078 	(1,463,020)

Not carried over

- Carry over from year 2000			 1,943,078

480,058 	Ahead of budget

B. New Operating Budget                             451,767

|  |  | Unit: thousand Won |
| --- | --- | --- |
|  | year 2000 | year 2001 |
| Consulting | 479,222 | 2,072,287 |
| H/W | 52,574 | 77,000 |
| S/W | 3,560 | 193,463 |
| Others * | 21,566 | 120,270 |
| Total | 556,922 | 2,463,020 |
| * maintenance, leased line, office, adm. Promotion Etc |  |  |