January __, 2001

Mr. Lynn DeKrey

Project Manager

Siemens Westinghouse Power Corporation

4400 Alafaya Trail

Orlando, FL 32826-2399

Dear Mr. DeKrey:

In response to your letter faxed to Mr. Dan Schultz on December 8, 2000, Enron is surprised that Siemens Westinghouse now claims that delivery of the subject generator had occurred per the terms of our turbine purchase agreement prior to the event that damaged the unit. Your current position is inconsistent with your written correspondence to us dated July 26, 2000 and the phone conversation that followed where you claimed that a Force Majeure event had occurred and the aforementioned letter was your confirmation. We are further troubled in that your letter seems to indicate that you may have not made the necessary arrangements to deliver a replacement generator in April, 2001 as you previously committed in your letter dated September 29, 2000.

We would like to meet with you to resolve this matter as soon as possible, and toward that end, I will call you to arrange a meeting. In the meantime, please feel free to call me at (713) 853-9298 with any questions or comments you may have.  In addition, any future correspondence regarding this matter should be directed to me at 1400 Smith Street, EB3148d Houston, TX  77002.

Sincerely,

Ron Tapscott

Director

Enron North America

Cc Ben Jacoby, ENA