EPC Term Sheet

Rio Gen Project

DATE:  April 19, 2000

Revision: 11

| Terms and Conditions |  |  |
| --- | --- | --- |
| - Parties |  | “Contractor”: Enron Engineering & Construction Company (or one or more affiliates thereof). Owner: Rio de Janeiro Generation Ltda |
| - Basis of Project |  | Owner intends to enter into a power purchase agreement (the “PPA”) with Electro for the supply of electrical power. Contractor’s proposal is prepared without the benefit of the terms of a PPA, therefore the proposal is based on it own merits. If the executed PPA imposes requirements in addition to those set out in the proposal, Contractor’s performance price and time shall be adjusted. |
| - Project Description: Country: Location: Equipment Configuration: Nominal Output: Primary and Emergency Fuels: |  | Brazil Seropédica, in the state of Rio de Janeiro, Brazil (the “Site”) Combined cycle (2 on 1) (2 each MHI 501FD CTG) 500 MW Natural Gas with diesel as emergency fuel |
| - Scope of Work |  | - Contractor shall design, procure and construct the Facility in accordance with the Scope of Work as set forth in EECC’s proposal dated April 2000. - The Facility will consist of two MHI 501 FD combustion turbine generator sets, 2 HRSGs and one steam turbine with the appropriate balance of plant as described in the Scope of Work. The Scope of Work includes the installation of the Owner provided MHI 501FD turbine generator sets; provided however the Owner is responsible for purchase and delivery of such to the Site. |
| - Engineering Release |  | Owner is to issue a preliminary engineering release which release will authorize Contractor to : - Perform basic engineering for the Facility - Complete the solicitation of and selection of the HRSG, ST, Step Up Transformer and other selected long lead items of equipment, - Obtain Owner concurrence on the selection of the HRSG and ST vendor by the Engineering Release, - Release the HRSG, ST, step up transformers and other long lead item vendors to commence engineering of such items the Engineering Release - Enter into Letters of Intent and contracts with HRSG, STG, transformer vendors, design companies, and construction subcontractors. Concurrent with Contractor’s above activities Owner shall be performing various activities in preparation for the Notice to Proceed including: - Cause to be conducted and completed Geotech / Hydrology studies to allow Contractor to complete its major equipment foundation designs prior to Notice to Proceed - Locate and obtain necessary rights of way. - Causing the slow down lane on the Dutra to be designed and constructed. - Complete the noise study and land acquisition. In the event Owner cancels the project prior to NTP, Contractor shall be reimbursed for its labor (using EECC’s standard multiplier for Enron projects) plus actual costs including subcontractor cancellation costs. |
| - Conditions Precedent to the Notice to Proceed Effective Date |  | - Financial closure, or Owner demonstrates to Contractor’s reasonable satisfaction that it has the financial ability to pay the Base Contract Price. Such financial assurance shall remain valid until financial close.; - Applicable permits obtained by Owner (including any rights to build); - Site Geotechnical complete and provided to Contractor; - Existing underground drawings provided; - Grid analysis completed; - Applicable rights of way obtained; - Environmental permissions in place and construction related requirements are met; - Site utilities available (construction water of [TBD] GPM and construction electricity of 2MW at 13.8kv; - Full and unrestricted access to the Site; - Applicable insurance in place; and - A minimum of 60 days have passed since the Engineering Release. - Owner has completed and provided the site survey to Contractor. - At least 60 days has passed since reaching an agreement with Owner on the selection and placement of order of the HRSG and STG vendor. - Owner has executed the purchase contract with MHI for the supply of the combustion turbine generator sets. Note: If NTP is not issued within 90 days after the Engineering Release such failure shall be a deemed Owner directed suspension of work for which Contractor shall be eligible for a Change Order for the costs associated with the suspension. |
| - Contract Price |  | Contractor agrees to perform the Scope of Work for a fixed lump sum price of $ 143,441,000 U. S. dollars (the “Base Contract Price”). $400,000 U.S. dollars are to be paid to the Contractor at time of Engineering Release. Base Contract Price does not include the contract price of the MHI combustion turbines packages (including auxiliaries) as set out in the MHI contract. The Base Contract Price includes a Provisional Sum of $6,197,000 for the transportation of Equipment (less the MHI CTG & package) to the Site. Such amount will be firmed up during contract negotiations. The Base Contract Price includes a provisional sum of $600,000 for noise baffling that may be required to cause the Facility to meet the Far Field Noise Level Guarantee. Upon completion of the detailed noise study Contractor will make a recommendation to Owner as whether such baffling will be required. The Base Contract Price includes a provisional sum of $12,903,000 for two (2) HRSGs. Such amount will be firmed up during contract negotiations. |
| - Taxes |  | (a) The Contract Price includes: 1) All non Brazilian Taxes associated with the work; - The following taxes imposed by Brazil: - Corporate taxes (subject to (d) below); - Personal taxes; - Export taxes (b) The Contract Price excludes the following taxes: TBD - Brazilian Customs Duty; - IPI; - ICMS - AFRMM - ISS, - CPMF - IOF - PIS, - COFINIS - any taxes related to the MHI turbine (c) The Contract Price is based on the premise that the contracts will not be viewed by the Brazilian tax authorities as a Technical Assistance agreement, Cost Sharing Agreement, Services or Management Agreement. (d) The Contract Price premises that there will be no Brazilian withholding taxes imposed payments made for profits, work and/or services to be performed outside of Brazil under an offshore contract. To the extent that there is a Brazilian withholding tax imposed on such payments, Owner shall gross up such payments such that Contractor receives its Contract Price after such Brazilian withholding taxes. The parties will use multiple contracts (onshore/offshore) to the extent that they minimize taxes. |
| - Change Orders |  | The Base Contract Price and Guaranteed Completion Date shall be subject to adjustment by change order for the following: - Change in Scope of Work - Owner Delay (including (1) delay in delivery of MHI documentation from the documentation delivery schedule set out in the MHI contract, (2)delay in the delivery of either or both the Owner provided MHI turbines & packages and/or Take Over Liquidated Damage Events as described in Article 10.3 of the MHI turbine contract) - Force Majeure - Change in Law - Site Conditions which differ from what can be reasonably extrapolated from Geo-tech data - Delay receiving utilities in accordance with project schedule - Grid Instability or unavailability of dispatch delaying Contractors start up- commissioning or performance testing |
| - Validity Period |  | The Offshore portion of the Contract Price shall remain valid provided that the Notice to Proceed Effective Date occurs prior to January 1, 2001 (the “Validity Period”). The Onshore portion of the Contract Price is based upon costs as of April 17, 2000. |
| - Escalation |  | Upon expiry of the Validity Period the Offshore portion of the Contract Price shall be escalated at - on a pass through basis on what is obtained from the ST, HRSG and step up transformer vendors, - 4% per annum on the offshore balance of plant procurement, design and project management, for a period of 12 months after which the price is subject to renegotiations prior to NTP. The Escalation of the Onshore portion of the contract price shall be determined during contract negotiations. |
| - Cancellation |  | Owner may cancel the Project prior to NTP at any time subject to agreed cancellation schedules. |
| - Suspension |  | Owner may suspend for up to 12 months subject to escalation, extension of completion dates and adjustment to the Contract Price. Additionally Owner shall reimburse Contractor on a monthly basis, reasonable suspension costs, including care of the works, storage and interest payments on any unpaid amounts. Restart of project after a suspension is subject to prior agreement on escalation, extensions, and price adjustment. |
| - Payment |  | All payments shall be in U.S. dollars (and in required in Reais for the onshore portion) in accordance with an agreed monthly milestone payment schedule on a net 15 days basis. |
| - Retention |  | Owner may retain the last 5% of the Base Contract Price through to Substantial Completion at which point the retention will be reduced to 2 ½% until the expiry of the Primary Warranty Period. Contractor shall be paid the last 5% in accordance with the Milestone Payment Schedule provided Contractor submits a Letter of Credit in the same amount. The Letter of Credit shall remain valid through the Primary Warranty period. |
| - Schedule Guarantees: Substantial Completion: Final Completion: |  | Contractor guarantees that it will achieve “Substantial Completion” of the Facility by no later than 28 months after the Notice to Proceed Effective Date. The Guaranteed Completion Dates is based on the premise that: - Owner causes gas (ready for use in the combustion turbine) to be available at Site by not later than 14 months after the Notice to Proceed Effective Date which fuel meets the requirements of the MHI fuel specification as set out in the MHI contract. - Owner causes the MHI turbines to be delivered in accordance with the delivery schedule in the MHI contract, to operate reliability and to meet the Specific Performance Guarantees as set out in the MHI Contract. - Owner causes backfeed power to be available at the Site by not later than 11months after the Notice to Proceed Effective Date. - The grid is capable of accepting full electrical output produced by the Facility on a reliable and uninterrupted basis no later than NTP plus 14 months. The criteria for achieving Substantial Completion shall be: - Mechanical Completion; - Passage of Minimum Performance Guarantees set forth in Paragraph 18 (Minimum Performance Guarantees); and - Punch list agreed or submitted to Dispute Resolution. Contractor may declare “Final Completion” of the Facility when all of the following have been met: - Substantial Completion has occurred; - All punchlist items have been completed; - Site cleanup has been completed; - Final waiver and release of Contractor liens provided; and - All manuals and drawings (including as-builts) have been delivered. |
| - Performance Guarantees: Net Output Guarantee: Net Heat Rate Guarantee: Basis Conditions: |  | Contractor guarantees the following Facility performance net of the Facility’s auxiliary loads: 500,025 kW (on Gas fuel) corrected to output Basis Conditions (In addition to proving that the Facility will meet the Guaranteed Electrical Output of 500,025 kw, Contractor shall demonstrate a capability to produce 517,311 kW in a new and clean condition (on gas fuel) corrected to Output Basis Conditions. The purpose of such demonstrate is to assure Owner that the Facility will be able to overcome expected lifecycle degradation). 7303 kj/kWh (6,923 BTU/kWh) HHV (on gas fuel) corrected to Heat Rate Basis Conditions - Output will be measured at the high voltage side of the step up transformer with the Facility boundary. - Performance Guarantees are based on: - 23.5 degrees C ambient temperature and 78 % relative humidity for heat rate; - 29.3 degrees C ambient temperature and 58% relative humidity for Output - 1.012 bar (14.68 psia) atmospheric pressure; and - Fuel used during testing meets the fuel specification, - New and clean, - Performance values to be corrected from test fuel to guarantee basis fuel - Frequency is 60 hz - Power factor is .85 lagging. - The Fuel Heating Value is 20872 BTU/lb (LHV). - Supplemental firing permitted |
| - Minimum Performance Guarantees: Minimum Performance Output Guarantee: Minimum Performance Heat Rate Guarantee: Minimum Performance Noise Level Guarantees: Minimum Performance Emissions Guarantees: Basis for Guarantees: |  | 475,575 kW (of gas Fuel) 7709 kj/kWh(HHV) (7307 BTU/kWh) HHV (of gas Fuel) Near source sound power levels less or equal to 85 dB(A), 1 meter up and 1 meter away. Far Field sound power levels 55 dB(A) at Site boundary. (Preliminary studies indicate Owner must obtain land up to Dutra Hwy and possibly install silencer on HRSG). Emissions on Gas to meet World Bank emissions standards (1998) provided that Owner obtains a lower emissions guarantee from MHI to offset the effects of supplemental firing, such reduced emissions to be pursuant to Section 10.6 of the MHI contract. Emission and noise guarantees are at 100% base load only. Contractor guarantees are based on the premise that MHI meets its Guaranteed Levels and Specific Performance Guarantees as set out in the contract between Owner and MHI. To the extent that it demonstrated that MHI has not met one or more of such a guarantee, Contractor will be granted relief under its corresponding Performance Guarantee and Minimum Performance Guarantee. Electrical Output of the Facility shall be measured at the high side of the step up transformers within the Facility boundary. The guarantees and warranties are based on gas meeting the MHI gas specification requirements. The output and heat guarantees are based on the premise that stack silencing will not be required to achieve the Far Field Noise Level Guarantee. In the event that stack silencing is required, the output and heat guarantees will be adjusted for impacts of the additional back pressure induced by the stack silencing. |
| - Operational Tests Reliability Guarantee: |  | Ten (10) day test pursuant to the same terms as set out in the MHI contract to be conducted after Substantial Completion. |
| - Degradation and Grid Impacts |  | Treatment of degradation shall be the same as in the MHI contract for fuel oil and any operating hours and equivalent operating hours induced by grid instability or trips shall be grounds for adjustments for degradation. |
| - Performance Test Procedures |  | The Facility Test procedures to measure Facility Output and Heat Rate will be developed based on PTC 46-1996 (Performance Test Code on Overall Plant Performance) for the Facility. The Performance Tests on the MHI combustion units shall be based on PTC 22 and the general guidelines set out in the MHI Contract. PTC 19.1 in conjunction with PTC 46 and PTC 22 shall be used for calculating Testing Uncertainty. Contractor shall be allowed to account for test uncertainty when comparing test results to the Performance Guarantees and Minimum Performance Guarantees. Performance Test procedures to measure Facility emissions will be developed in accordance with the MHI contract based on EPA method 20 for Nox , EPA Method 6 for SO2 and EPA method 5 (front and back half) for particulates and as modified as necessary by the HRSG Agreement. Performance Test procedures to measure Facility sound levels shall be consistent with the procedures set out in Exhibit F-2 of the MHI contract. |
| - Test Tolerance |  | Consistent with the MHI Contract: Contractor will be allowed to account for instrument uncertainty when comparing the Electrical Output to the Electrical Output Guarantee and the Specific Performance Electrical Output Guarantee, and the Heat Rate to the Heat Rate Guarantee. The definition of and calculation of instrument uncertainty shall be in accordance with ASME PTC 46 (1997) and PTC 19.1 and the Performance Test guidelines to be set out in the Contracts. The parties agree to use ninety five percent (95%) coverage as set forth in Section 2.6.1 of PTC 19.1 for the basis of uncertainty calculations. |
| - Delay in Completion Liquidated Damages: |  | Beginning upon the Guaranteed Completion Date, Owner may assess $70,000 U.S. dollars per day for each day thereafter that Substantial Completion is not achieved. |
| - Performance Liquidated Damages: Output Liquidated Damages Rate: Heat Rate Liquidated Damages Rate: |  | $908 U.S. dollars per kW shortfall below500,025 kW(gas only). (Same rate as MHI). $75,000 U.S. dollars per BTU/kWh (HHV) shortfall (gas) only. |
| - Bonus |  | Early completion and performance guarantee bonus to be discussed during detailed contract negotiations. |
| - Maximum Liquidated Damages: Maximum Aggregate Liquidated Damages: |  | Shall not exceed 30 % of the Contract Price. Liquidated damages are the exclusive remedy for performance shortfalls. |
| - Retest Period |  | Contractor reserves the right to attempt to improve Facility performance for a period of 240 days after Substantial Completion in order to mitigate performance shortfalls, retest of the Facility. Owner shall provide access to the Facility during any scheduled and unscheduled outages during the 240 day period. In the event Contractor elects at Substantial Completion to attempt to improve performance Contractor shall not be liable for paying the applicable Performance Liquidated Damages within 10 days after Substantial Completion, provided however Contractor shall be liable for paying Interim Liquidate Damages (approximately $0.35 / kW/day and $25/BTU/kWh/day) on a monthly basis until the later of (i) 240 days after Substantial Completion and (ii) when Contractor declares no further improvements to be made (the “Retest Expiry Date”). At such time the Interim LD’s paid shall be netted from the Performance Liquidated Damages due ( the Performance Liquidated Damages due shall be based on the shortfall at the Retest Expiry Date). |
| - Warranty |  | Contractor will provide 12 months warranty (the “Primary Warranty Period”) to design, materials and workmanship and further warrants repairs, replacements and corrections performed during the Primary Warranty Period for an additional 12 months not to exceed 24 months after Substantial Completion in any event (the “Extended Warranty Period”). This warranty excludes warranty claims associated with the MHI turbine. |
| - Insurance |  | (a) Contractor Obtains with the Base Contract Price: Workers Comp; General Liability; Business Auto; Vessel PI and Aircraft; and Excess Liability. (b) Project Insurance: Marine Cargo with a maximum deductible of $25,000; and Builders All Risk with maximum deductibles of: $100,000 for major perils; $100,000 commissioning and Testing; and $ 20,000 for all other events. Delay in Start-up Insurance (c) Each party will be a named insured and provided a waiver of subrogation under the project insurance policies. Contractor will be responsible for the deductibles under the builders all risks and cargo insurance policies not to exceed the above levels. (d) Contractor shall place the project insurance. The cost of project insurance premiums is not included in the Base Contract Price and shall be paid by Owner. (e) Any Delay Liquidated Damages due will be offset by proceeds from the DSU policy. (f) Owner shall be responsible for insurance surveyor costs. |
| - Risk of Loss |  | Contractor is responsible for risk of loss and damage to the Work until Substantial Completion. Contractor shall assume the risk of loss and damage for the MHI turbines upon delivery to the Site; provided however, in the event that one or more turbine incurs damage not as a result of Contractor negligence Contractor shall not be responsible for such damage or the time delay associated with effecting the repair. Owner retains risk of loss with respect to existing facilities and ensures Contractor is not subject to consequential damages. |
| - Title |  | Title to all imported Equipment incorporated into the Facility shall pass to Owner prior to arrival at the Port of Import. Title to all Equipment procured in the country in which the Facility is constructed shall pass upon delivery to the Site. In the event that the use of an equipment holding company or other similar structure is advantageous to either party the transfer and holding of title will be appropriately modified. |
| - Force Majeure |  | The performance obligations of each Party will be suspended during a Force Majeure event. A Force Majeure event shall mean events beyond the reasonable control of the effected Party, excluding the obligation to pay amounts due under the Contract, and strikes directed specifically against Contractor. Contractor shall be entitled to financial and schedule relief. |
| - Limits of Liability |  | Total Limitation of Liability = 40% of Contact Price. Third Party indemnities = Not limited by Contract. Proceeds of Insurance do not count towards Limits of Liability. The Contract will contain mutual waivers of consequential damages. |
| - Indemnification |  | Contractor and Owner shall provide reciprocal indemnities pertaining to damage to 3rd party property, injury or death to persons and neither indemnity shall be subject to either party’s insurance program; provided however such provisions shall be back to back with the terms of the indemnification as it relates to consequential damages pertaining to 3rd parties. |
| - Permits, Leases ,Rights of Way and Permissions |  | Owner shall obtain the permits, land leases, rights of way and governmental permissions necessary to construct and operate the Facility. Contractor required to develop the information needed by Owner to obtain its Facility construction permits and Contractor shall obtain such permits to conduct its own business and perform construction activities as are by law to be issued in Contractor’s name. Contractor’s support of Owner’s permitting program shall be paid outside the Contract Price under an AFE. |
| - Liens |  | Contractor shall provide a lien waiver certificate as a condition precedent for the final payment. Form of waiver to be agreed. |
| - Operator Training |  | Training is included in the Contract Price. Training shall be conducted in English. Contractor shall be responsible for: - On the job training during start-up and commissioning; and - Familiarization of Owner’s operators with the Facility. Owner is responsible for: - Orientation of its operators to power plants; and - Salaries, travel, board, lodging and expenses of its operators; and - Supply of experienced and qualified operators in the power industry - Translators - Training program for the MHI turbine as set out in the MHI contract Training responsibilities remaining to be allocated are: - Vendor training: and - On Site classroom and audio/ visual equipment. Note: the OJT and familiarization training is impromptu training that does not include the formal preparation of training manuals. |
| - Spare Parts |  | Spare parts will be negotiated, selected and paid for by Owner. Contractor agrees to use reasonable efforts to obtain spare parts pricing from the equipment suppliers and reasonable time for Owner to conclude negotiations on spare parts prior to any commitment to major equipment suppliers. Owner will ensure that the Spare Parts (including the Spare Parts provided by the MHI spare parts agreement) are available at the Site by not later than the first fire of the first turbine. Contractor shall be permitted to draw spare parts from the Owner stock (Contractor shall be obligated to replace such spare parts at its cost). |
| - Offsites/Interface |  | Owner is responsible for dispatch interface. Plant design is based on telephone dispatch with confirmation by fax. |
| - Hazardous Material Risk |  | Owner shall be responsible for all Hazardous Materials existing on Site prior to the commencement of work and re mediation thereof. Contractor shall be responsible for Hazardous Materials introduced to the Site by Contractor after the commencement of work and re mediation thereof. Contractor will notify Owner upon discovery of Hazardous materials on Site in any case and observe Owner instructions. |
| - Manmade Obstructions |  | The Contract Price is based upon no man made underground obstructions existing at the Site. Owner will provide to Contractor all applicable documents outlining existing conditions existing at the Site. Contractor will accept the risk of manmade underground obstructions identified by Owner and Contractor prior to Contract signing subject to an equitable adjustment to the guaranteed completion dates and Contract Price. All other undiscovered manmade underground obstructions remain Owner’s risk. |
| - Site Risk |  | The Contract Price is based upon the following premises: - No piling is required; - No hard pan excavation; - Natural soil provides 3000 psi bearing; and - Site noise baseline survey has been performed and available to the Contractor prior to NTP and demonstrates that the Facility will meet the guarantee within the Site boundary |
| - Governing Law |  | New York. |
| - Dispute Resolution |  | The parties shall attempt to resolve disputes in the following order of preference: - Senior corporate officers shall meet to resolve the dispute: - The dispute shall be referred to binding Arbitration under the rules of an arbitration authority to be determined; and - (iii) Enforcement of the arbitration award shall be brought in any court having competent jurisdiction - . |
| - Governing Language |  | English. |
| - Owner’s Responsibilities |  | Owner will: - Keep Contractor fully informed of the status of the development of the Project, the anticipated dates by which the final project contracts will be executed, and the anticipated Preliminary Notice to Proceed and Notice to Proceed Effective Dates. - Pay for Project insurance as detailed elsewhere in this term sheet. - Provide Contractor copies of the PPA and the lease, site services, or other agreements with the utility relating to site access, services and existing conditions, if any, and the fuel supply agreement promptly following execution of the same and prior to execution of the Contracts. - P - rovide Contractor access to Owner’s Site (including the laydown area) with easements and rights of way as are detailed elsewhere in this term sheet. - Coordinate delivery of required fuel, and/or fuel delivery system to the Site no later than 14 months after Notice to Proceed Effective Date (the gas must be at a minimum of 40 barg, 100,000 cm3/hr flow and 19.5 degrees C. - Pay for fuel utilized during start-up and testing of the Facility. - Order spare parts to Major Equipment (STG, HRSG, and DCS) in time to ensure delivery prior to first fire of the combustion turbine. (Contractor shall provide Owner with a suggested listing of spare parts with pricing upon completion of it selection process of the successful of such item of Major Equipment.) - Interface with utility including dispatch and arrange for timely dispatch of the Facility and off take energy to support testing of the Plant. - Coordinate with local utilities and provide construction utilities, including construction water (of a quality appropriate for concrete), construction electricity, telephone service (10 POT lines and one line with direct link to the Enron WAN - T1 quality) and start-up and testing fuel. - Staging and laydown areas as designated on drawing Laydown-M3-01-A as set out in the proposal. - Free issue MHI turbine generator packages, to be provided to the Contractor at the Site. - Act as importer of record for all imported equipment and materials (unless the parties agree to use a holding company). - Pay Contractor all amounts due and payable in accordance with the terms of the Contract. - Obtain the Water use permit, provide operating water in quantity, quality and in time to support Contractor’s start up, commissioning, and performance testing of the Facility. - Provide back feed power for start up, commissioning and testing by not later than 11 months after the Notice to Proceed Effective Date. - Obtain a waiver from the grid to operate the Facility within the frequency range limitations of the MHI turbine. |
| - Ownership of Drawings |  | Title to drawings specifically prepared for the Facility shall belong to Contractor, and Owner shall be granted the right of use. Title to Contractor and subcontractor proprietary drawings or other documents utilized in the design and construction of the Facility but which were not specifically prepared for this Facility, shall be retained by the developing party, but such party shall provide Owner a royalty free, non-revocable, transferable license for their use. |
| - Country of Origin for Equipment |  | Contractor agrees to make reasonable efforts to coordinate procurement within the Owner’s financing plan, provided however Contractor shall be kept whole arising out any increased cost or time arising changes in equipment selection necessitated by such compliance. |
| 49. Applicable Laws |  | Contract shall be entitled to schedule and cost relief for any change in law (including taxes) effective after the Effective Date of Contractor’s offer. |
| 50. Financing Support |  | Contractor shall provide support as necessary to assist Owner with its financing program however the costs of providing information that would not be produced at the time required in the normal course of design or is actions not normally performed during the engineering, procurement and construction of a comparable Facility shall be reimbursed via an AFE process. |
| 51. MHI Contract Management |  | The Contract Price does not include compensation for the costs of managing and administering the MHI contract (both during execution and warranty period). Contractor shall perform such services for Owner on an AFE basis outside the Contract Price. |