- Risk Management System Project

- Discretionary

- Statement of Work

- Prepared By:  Lisa Sawyer

Preparation Date:  08/17/00 10:00 AM

- Contents

Current Business Environment	3

Proposed Business Environment	3

Business Justification	3

Alternatives Considered	4

Recommendations	4

Project Scope	4

Delivery Commitment	4

Responsibilities	4

Business Unit	4

IT	5

Risk Identification and Mitigation	5

Estimated Cost	6

Customer Approval Sign-off	7

# Current Business Environment

ETS currently manages its market risks on a short term and/or deal by deal basis.  In addition, mitigating those risks must be done through a third party further reducing its ability to extract maximum margins.  Structured products are not readily broken down into their component parts and monitored to take advantage of favorable shifts in volatility or other market moves.  Current deal making for transport determines value by what the market bids and does not readily have models to calculate the option value.   Since each individual transport and storage marketing group within ETS is responsible for a revenue budget, risk profile positions are not viewed consistently or globally.  It is possible that a potential hedge for one group may increase risk for the group as a whole.

## Proposed Business Environment

We are proposing the purchase of a Risk Management system that would allow ETS to capture and manage any and all risks ETS is currently subject to and/or may become subject to in the future.  This system would account for both natural and transacted positions and would have the ability to view positions based on a forward "first of the month" mark-to-market view and an options mark-to-market view.  This system would be flexible enough to allow us to add new books, new companies, new transaction types, and sub-transaction types without additional programming.  This system will have the capability of running different sensitivity analysis including but not limited to VaR and Monte Carlo.  This system will support a variety of reports that can be customized for Management, Traders, Control, and Finance showing positions, Profit & Loss, accrual revenue, Mark-to-Market revenue (unrealized), and anticipated cash flows.  This system would have settlement capabilities (Invoicing and Payments) for any financial transactions entered into and the ability to account for margin accounts and settle broker fees.  This system would also have the ability to produce ad-hoc reports quickly and easily.

## Business Justification

ETS believes a Risk Management System will enable it to better protect and extract value from its assets.  This system will allow ETS to benefit from separating the financial aspects of a deal from the physical aspects of a deal and allow us to manage each independently.  This will allow ETS to take advantage of better timing of transacting a deal either financially or physically and in any order.  ETS will be able to manage the various risks it is subject to as well as trade from known positions on a global basis.  Other benefits would be: 1) better price discovery (since volatility will be taken into account), 2) more responsive to deal offers, 3) extract value from both physical and financial positions, 4) ability to hedge naturally occurring risks, 5) ability to better structure deals, 6) ability to monetize options that are built into deals, 7) ability to manage earnings and cash flows, 8) better management information and 9) adherence to new Accounting pronouncements on Risk Management activity..

## Alternatives Considered

An investigation was done to use an the internal Risk Management System that Enron North American uses; however, due to the size and complexity and large interfaces to other applications, this approach would be too costly and take too long.  Developing a system was considered, but due to timing and costs, that option was also eliminated.  Several packaged products were contemplated (Derivatives.com, Ensyte, ESI, Altra, Allegro, SAS, TriplePoint, Power Trade, Intermark and Focus) and two were evaluated in depth: (Caminus and SunGard).

## Recommendations

The recommendation is for ETS buy the Caminus Zai*Net Manager Risk Management System.

## Project Scope

Implement Caminus’ Risk Management System with minimal interfaces to existing applications.  Data conversion will be handled by the marketing group manually so no automated data conversion effort is necessary.  Caminus Consulting will provide technical support to conduct user testing and training, develop a price curve upload interface from EXCEL and develop an options pricing model interface.

## Delivery Commitment

| Activity/Milestone Description | Deliverable Name/Description | Target Date |
| --- | --- | --- |
| Complete Vendor Selection |  | October 20 |
| Establish Detail Project Plan |  | November 10 |
| Begin User Acceptance Testing |  | December 1 |
| Implement System |  | January 1, 2001 |

## Responsibilities

### Business Unit

- Vernon Mercaldo - Project Manager/Generalist

- Lee Ferrell - Project Sponsor/Risk Management Consultant

- Kent Miller - Executive Sponsor/Oversight

- Kim Watson - Revenue Management Consultant

- Jo Williams - NNG Transport Consultant

- Jeff Fawcett - TW Transport Consultant

- Morgan Gottsponer - Storage/Operational Storage Consultant

- TBD - Accounting Consultant

### IT

- Lisa Sawyer - IT Oversight

- Mark Ferguson - IT Manager

- Caminus Consulting – User training, Price Curve Upload Interface, Options Model Interface

## Risk Identification and Mitigation

The following criteria were used to provide a high-level risk assessment.

| Risk Assessment Criteria |  |  |  |
| --- | --- | --- | --- |
| Project Attribute | Low | Medium | High |
| Size | Less than 10,000 lines of code | 10,000 to 100,000 lines of code | More than 100,000 lines of code |
| Effort | Less than 1 man-year | 1 man-year to 10 man-years | More than 10 man-years |
| Cost | Less than $100,000 | $100,000 to $1,000,000 | More than$1,000,000 |
| Structure | Business process well defined and documented | Business process vague, or incomplete documentation | Business process not defined; no documentation available |
| Technology | Existing hardware/software systems; require minor or no modifications | Major modifications required to hardware or software systems, or both | State-of-the-art hardware or software systems required |
| Impact | Few impacts to the enterprise outside of the immediate project or the customer’s information protection | Impact affects several organizations across the enterprise or the customer’s information protection | Project essential to the strategic direction of the enterprise or high impact to the customer’s information protection |

This yields the following assessment:

| Assessed Risk for Project |  |  |  |
| --- | --- | --- | --- |
| Project Attribute | Low | Medium | High |
| Size |  | X |  |
| Effort |  | X |  |
| Cost |  | X |  |
| Structure |  |  | X |
| Technology | X |  |  |
| Impact |  |  | X |

## Estimated Cost

- Budgeted Funds $650,000 – Budgeted as part of Revenue Management Project

The project will be conducted on a time and materials basis. The cost estimates for completion of deliverables are calculated based on best estimates of costs for projects of similar scope, complexity and schedule constraints.  Any changes to the scope of the project as outlined in this proposal will be handled through existing project modification procedures.

| Cost Impact |  |  |  |  |
| --- | --- | --- | --- | --- |
| Resource Expenses | Number | Rate | Estimated Months | Total |
| ITby Job Category |  |  |  |  |
| Project Manager | 1 | $10,200 | 3 | $30,600 |
| Technical Support | 1 | $9,200 | 2 | $18,400 |
| Business Unitby Job Category |  |  |  |  |
| Caminus Consulting – Implementation Support |  |  |  | $91,000 |
| Total Estimated Resource Expenses |  |  |  | $140,000 |
| Hardware/Software Expenses |  |  |  |  |
| Caminus Base Software Lilcense (includes 2 users) |  |  |  | $300,000 |
| Add 8 Add’l User Licenses | 8 | $12,000 |  | $96,000 |
| 2001 License Maintenance Fee |  |  |  | $79,000 |
| Total Hardware/Software Expenses – Assumes no additional hardware will be nneded |  |  |  | $475,000 |
| Miscellaneous Expenses |  |  |  |  |
| Travel |  |  |  | $10,000 |
| Training |  |  |  |  |
| Other - AFUDC |  |  |  | $25,000 |
| Total Miscellaneous Expenses |  |  |  | $35,000 |
| Total Project Expenses |  |  |  | $650,000 |

## Customer Approval Sign-off

I have read the above Statement of Work and agree that the scope identified is accurate and complete.  I authorize the process to obtain a work order and understand that no work can begin until an approved work order has been obtained.

| GPG IT Project Manager |  |  |  |
| --- | --- | --- | --- |
|  | Mark Ferguson |  | Date |
| GPG IT Manager |  |  |  |
|  | Lisa Sawyer |  | Date |
| Business Unit Project Manager |  |  |  |
|  | Lee Ferrell |  | Date |
| Business Unit Executive Sponsor |  |  |  |
|  | Dave Neubauer |  | Date |
| Architecture Office |  |  |  |
|  | Bob Martinez |  | Date |
| Program Office |  |  |  |
|  | Tony Mayer |  | Date |
| GPG VP & CIO |  |  |  |
|  | Steve Hotte |  | Date |