E T & S							Interoffice  Memorandum

Northern Natural Gas Co./Transwestern Pipeline Co.

TO:	Keith Petersen

FROM:	Josie Call			DEPARTMENT:	Certificates & Reporting

SUBJECT:	Certificate Status Report			 DATE:	September 8, 2000

Northern currently has four (4) project(s) and Transwestern has no project(s) to be filed.  Certain of these projects require action by other groups before the Certificates & Reporting department can proceed with the FERC filings.  Updates on existing projects, which have occurred since the last report on  August 8, 2000, are in bold print.  Projects are more fully described in the following attachment.

To the extent you are aware of a project that is not referenced, please feel free to call me at extension 7258 in Omaha.

Distribution:

B. Cordes			Omaha				D. Neubauer		Omaha

M.K. Miller		Omaha				K. Miller			Omaha

M. McGowan		Omaha				J. Dushinske		Omaha

M. Nelson		Omaha				R. Storie			Houston

D. Fossum		Omaha				J. White			Houston

P. Lowry			Houston				S. Harris			Houston

All Marketing Account Managers:

Omaha, Houston & Minneapolis				Certificate Department Staff

G. Hass			Omaha				J. Centilli			Houston

D. Dornan		Omaha 				L. Stanton		Minneapolis

J. Talcott			Omaha 				M. Darveaux		Omaha

S. Scott			Houston 				D. Werkmeister		Minneapolis

G. Zahn			Houston 				M. VanNorden		Washington, DC

M. Pavlou		Omaha 				L. Soldano		Houston

L. Huber			Houston				K. Wilkie			Houston

T. Ritchey		Omaha				D. Waymire		Omaha

M. Bonnstetter		Omaha				R. Elizondo		Houston

S. January		Houston 				P. Prigmore		Omaha

G. Spevak		Omaha				T. Kissner		Omaha

L. Trevino		Houston 				T. Halpin			Omaha

R. Jolly			Albuquerque			R. Wilson			Omaha

K. Earl	 		Amarillo				T. Mertz			Beatrice Region

T. Galassini		Houston				T. Gilbert		Des Moines Region

R. Smith			Omaha				M. Adelmann		Minneapolis

D. Odneal		Hugoton Region			R. Cates			Omaha

D. Trayer			Omaha				R. Matthews		Houston

G. Bruner		Mullinville Region			D. Trayer			Omaha

M. Underwood		Minneapolis			G. Cade			Omaha

C. Graham		Omaha				D. Sinclair		Houston

#### S. Thomas		Omaha

Attachment

STATUS.DOC

STATUS  OF  CURRENT  PROJECTS

TABLE OF CONTENTS

PAGE NO.

FERC AUTHORIZATION RECEIVED

NEW APPLICATIONS FILED

OTHER DISPOSITIONS OF PROJECTS

CERTIFICATES PENDING REHEARING

CERTIFICATES APPROVED WITH CONDITIONS

CERTIFICATES PENDING FERC APPROVAL

PROJECTS TO BE FILED

# FERC AUTHORIZATION RECEIVED

TRANSWESTERN PIPELINE COMPANY

NONE

NORTHERN NATURAL GAS COMPANY

# NEW APPLICATIONS FILED

TRANSWESTERN PIPELINE COMPANY

NONE

NORTHERN NATURAL GAS COMPANY

CP98-132-001	C&D-LINE EXTENSIONS - Section 7(c) application to amend the certificate of public convenience and necessity granted by order issued June 30, 1998 in Docket No. CP98-132-000.  The amended application requests authorization to construct and operate approximately 5.6 miles of pipe, with appurtenances, rather than construct the originally authorized facilities.  The proposed facilities are necessary to provide the incremental firm transportation service to Koch Energy Services (Koch) for use at the Rosemount Refinery.  On September 5, 2000, Northern filed a supplement to its environmental report to update information regarding landowners, river permits, and minor corrections to the report.  Minnegasco filed a protest regarding Northern's request for rolled-in rate treatment of the incremental facilities.  Minnegasco argues that unless Northern provides contracts for the incremental capacity for a minimum of ten (10) years, the Commission should decline Northern's request for rolled-in rate treatment and leave in place the earlier certificate condition putting Northern at-risk for the incremental facilities.  Legal is drafting a response to the protest.  The NDG, UtiliCorp, and Viking filed vanilla interventions.

Filed:		08/02/00

Notice:		08/11/00

Order Issuing Certificate:		Pending

Regulatory Contact:  Michele

CP00-		T-44 RATE SCHEDULE ABANDONMENT- Section 7(b) application for permission and approval to abandon service to MidAm (formerly IPS) under the T-44 Rate Schedule contained in Northern's Original Volume No. 2 FERC Gas Tariff.

Filed:	08/9/00

Noticed:

Order Approving Abandonment:	Pending

Regulatory Analyst:  Bret

CP00-406	X-12 RATE SCHEDULE ABANDONMENT- Section 7(b) application for permission and approval to abandon service to Southern Union under the X-12 Rate Schedule contained in Northern's Original Volume No. 2 FERC Gas Tariff.

Filed:	07/17/00

Noticed:

Order Approving Abandonment:	Pending

Regulatory Analyst:  Bret

# OTHER DISPOSITIONS OF PROJECTS

Projects in this section will be deleted from the next Status Report

TRANSWESTERN PIPELINE COMPANY

NONE

NORTHERN NATURAL GAS COMPANY

CP00-103	X-25 RATE SCHEDULE ABANDONMENT- Section 7(b) application for permission and approval to abandon service to Southern Union under the X-25 Rate Schedule contained in Northern's Original Volume No. 2 FERC Gas Tariff.

Filed:	02/28/00

Order Approving Abandonment:	04/18/00 91 FERC ¶62,041 (2000)

Regulatory Analyst:  Bret

# CERTIFICATES PENDING REHEARING

TRANSWESTERN PIPELINE COMPANY

NONE

NORTHERN NATURAL GAS COMPANY

CP95-519	MOPS ABANDONMENT -  Section 7(b) application for the abandonment, by sale to Enron Gulf Coast Gathering, Limited Partnership (EGCG), of Northern's interest in its Matagorda Offshore Pipeline System (MOPS) facilities and the abandonment of any services impacted by the sale.  EGCG filed a Petition for Declaratory Order on May 25, 1995 in Docket No. CP95-516.  By Order issued April 17, 1997 (April 17 Order), the Commission denied EGCG's request and dismissed Northern's abandonment application.  Northern, EGCG, and the Williams Company filed Requests for Rehearing of the April 17 Order.  Tolling Order issued June 18, 1997. Acquisition of the MI 787 lateral closed effective December 8, 1998.  Letter notifying the Commission of the acquisition was filed on March 1, 1999.  Assignment and ROFR agreements have been drafted.

Filed:		05/25/95

Order Dismissing Request:		04/17/97 72 FERC ¶ 61,039

CP95-519-001	  	Request for Rehearing Filed:		05/19/97

Tolling Order Issued:		06/18/97

Order on Rehearing:		Pending

Regulatory Contact:  Michele

# CERTIFICATES APPROVED WITH CONDITIONS

TRANSWESTERN PIPELINE COMPANY

CP99-522	GALLUP EXPANSION/SAN JUAN COOLERS – Section 7(c) application to install and operate additional cooling at the Bloomfield and LaPlata “A” compressor stations and a new compression (Gallup) all on the San Juan lateral. On January 14, 2000, filed to accept the order without prejudice to reserving our right to seek rehearing and/or clarification to the order.  On January 21, filed notice of a bona fide beginning of construction date of January 17, 2000.  On February 14, 2000 filed a report explaining how Transwestern will retain operational control of the electric motor and a request for rehearing on the discounted rates.  On February 24, 2000 filed Notice of Construction for the Bloomfield cooler effective February 22, 2000.   A February 28, 2000 Notice of Construction at LaPlata was filed on February 29, 2000.  On 4/10/2000 and 4/24/2000 respectively, filed notices of in-service effective 4/6/2000 for the Bloomfield cooler and 4/20/2000 for the LaPlata coolers.  On 5/5/2000 filed notice of a 5/1/2000 in-service date for the Gallup Compressor Station.  On May 10, 2000 notified FERC that construction activities associated with the installation of the coolers at LaPlata were completed as of May 8, 2000.  On June 30, 2000 filed request for extension of time to file noise surveys.  Preliminary data indicates all sites fall within the 55 Ldn range.  Expect reports to be available by mid-July.   FERC granted the request for an extension until August 1, 2000.      FERC denied SoCal’s request for rehearing stating the project would not be subsidized by existing customers and SoCal would not be harmed by the project.  Transwestern’s request for rehearing was deemed moot because the discount rates were filed in the normal course of business.  Filed the noise survey for Gallup Compressor Station on July 21, 2000 indicating noise levels well below 55 Ldn (50.5 and 45.9) at the nearest noise sensitive areas.

REMAINING CONDITIONS:

- Final costs due 6 months after in-service date.

Filed:	05/13/99

Order Issued:	01/13/00 90 FERC ¶ 61,032 (2000)

Tolling Order:	03/08/00

Order on Rehearing	07/14/00 92 FERC ¶61,035 (2000)

Regulatory Contact:  Donna

CP98-795	UPH/BURTON FLATS SALE AND CRAWFORD COMPRESSOR RELOCATION - Section 7(b) application for permission and approval to abandon by sale to Union Pacific Highlands Gathering and Processing Company (UPH) approximately 58 miles of pipeline and the Crawford Compressor Station site.  Also filed a Section 7(c) application requesting permission to abandon and relocate two 1100 horsepower compressors at the Crawford Compressor Station to the tailgate of a proposed new processing plant to be built by UPH. Meetings held on April 15 and May 4 to discuss conditions, timetable and compliance status. The original purchaser, UPH, was acquired by Duke Energy prior to receiving an Order from the Commission.  On July 8, notified FERC that the first, of a two-part closing, became effective July 1, 1999. Negotiations/discussions on the remaining facilities are ongoing.  Subsequent negotiations with Duke have resulted in the cancellation of the second closing.  Once operations have been reviewed and finalized to accommodate this latest operational configuration, we intend to file a letter with FERC explaining the situation.

REMAINING CONDITIONS:

- Notice of abandonment must be filed within ten (10) days.

- Noise survey must be filed 60 days after placing new Crawford Compressor Station in service.

Filed:	09/23/98

Order approving abandonment: 	04/01/99 87 FERC ¶ 61,004 (1999)

Certificate Accepted:  	04/26/99

Regulatory Contact:  Vig

CP98-233	KN INTERSTATE/LIPSCOMB MOCANE & LEEDY LATERAL SALE - Section 7(b) application for permission and approval to abandon, by sale to K N Interstate Transmission Company, Transwestern’s Lipscomb Mocane and Leedy laterals. Mewbourne withdrew its protest October 1, 1998. Aurora did not withdraw its protest.  On December 22, 1998, the Commission issued an Order Denying Protest and Approving Abandonment.  A Second Amendment to the Asset Purchase Agreement was executed January 31, 2000 extending the terms of the agreement until March 31, 2000.  An agreement to assign the original Asset Purchase Agreement, as amended, to OneOk, Inc. was executed April 5, 2000.  OneOk has until July 5, 2000 to notify Transwestern of its intent to purchase the subject facilities.  By letter dated June 26, 2000, ONEOK officially exercised its right to terminate the Asset Purchase Agreement for this transaction.  However, ONEOK also indicated that it planned to make an unsolicited arms length offer to purchase these facilities.  If an offer is not made for these assets, Transwestern will file to vacate this order.  Waiting for Marketing to determine timing of any filing.

REMAINING CONDITION:

- Notice of abandonment must be filed within ten (10) days.

Filed:		02/13/98

Order Issued:		12/22/98 85 FERC ¶61,416 (1998)

Regulatory Contact:  Michele

CP94-751-000	ABANDONMENT OF FACILITIES - Section 7(b) filing for permission and approval to abandon and remove certain transmission and gathering facilities.  Removal of assets is ongoing.

REMAINING CONDITION:

- Status reports being filed by Legal.

Filed:		08/30/94

Filed Amendment to Application:		10/03/94

Filed Amendment to Application:		05/01/95

Order Approving Abandonment:		07/27/95  71 FERC ¶61,085 (1995)

CP94-751-003		Request for Rehearing:		08/28/95

Order Denying Rehearing:		10/17/95

CP94-751-004	751 AMENDMENT (2ND) - Amendment to application requests permission to abandon certain of the facilities in the original application by sale to third parties rather than removal.  There are five (5) separate closings. Closed are sale to Conoco, Agave Energy Company, and Enron Oil & Gas.  Bills of Sale for remaining facilities drafted by Legal. Pending sales are Mobil Producing Texas and New Mexico, Inc. and Highlands Gathering & Processing Company.  Negotiations continue with Duke (successor in interest) to execute the closing of the Mobil and Highlands sales.

REMAINING CONDITION:

- Notice of abandonment.

Filed Amendment to Application:		11/13/95

Order Approving Abandonment:		07/02/96 76 FERC ¶62,006 (1996)

Regulatory Contact:  Vig

CP94-751-005	751 AMENDMENT (3RD) - Amendment to application requests permission to abandon certain of the facilities in the original application by sale to Continental Natural Gas, Inc. and GPM Gas Corporation rather than remove the equipment as originally proposed.  Finals closing documents mailed to CMS and GPM.  Follow-up with the entities continues.

REMAINING CONDITION:

- Notice of abandonment.

Filed Amendment to Application:		12/24/96

Order issued:					11/03/97  81 FERC ¶ 61,151 (1997)

Regulatory Contact:  Vig

“751” Facilities – Internal meeting held to discuss status of closings and removals.  Possible third party interest in some of the remaining facilities originally scheduled for removal may result in an additional amendment to the application seeking authority to abandon the selected facilities by sale instead of removal.  Awaiting executed documents from Duke, CMS and GPM  to prepare final compliance notification to FERC .  Negotiations to sell some or all of the remaining 19 facilities, presently authorized for abandonment, continues.  We filed a letter with the Secretary’s office in June apprising them of the status of these 19 facilities.

NORTHERN NATURAL GAS COMPANY

CP00-371	OLIVE STREET REPLACEMENT – Section 7(b)/(c) application for permission and approval for the replacement and operation of approximately 199 feet of the 24-inch A-line with 6-inch pipe to repair a leak at Olive Street in Cass County, Iowa.  The replacement was completed and reported in Northern’s 1999 automatic blanket report as a like for like replacement.   The project was discussed with FERC and it was agreed that the 7(b)/(c) application would be filed.   On June 28, 2000 received FERC data request for:  (1) additional information on the replacement projects Northern filed under 2.55(b) Regulations for the last 5 years in which the pipe was replaced with a different diameter pipe;  (2) internal procedures insuring that Northern will not conduct replacement projects without the proper regulatory authority in the future;  (3) and whether the 6-inch line was designed to permit pigging operations as required by DOT regulations.  Northern’s responses  were filed  on July 10.	 On 8/18/2000, filed beginning construction date effective 4/20/1999, end of construction and in-service date effective 4/25/1999, and actual costs of $84,237.

Filed:					05/30/2000

Order Issuing Certificate:		07/28/2000  92 FERC ¶ 62,070 (2000)

Certificate Accepted:			08/02/2000

Regulatory Contact:	Donna

CP00-278	OAKLAND A-LINE REPLACEMENT – Section 7(b)/(c) application requesting permission and approval to replace approximately 179 feet of 24-inch A-Line with 6-inch pipe in order to repair a leak at Highway 6 located immediately adjacent to the Oakland Compressor Station in Potawattamie County, Iowa.  Northern requested an expedited notice period of 5 days and that an order be issued within 2 weeks of the end of the notice period.  On May 23, 2000, filed Notice of Construction effective May 22, 2000.  On June 1, 2000 filed Notice of In-Service effective May 29, 2000.  On August 2 filed notification that remediation activities were completed as of July 24, 2000.

Remaining conditions:

- Actual costs due no later that 11/29/2000.

Filed:	05/03/2000

Order Issuing Certificate:	05/17/2000  91 FERC ¶ 62,114 (2000)

Certificate Accepted:	05/19/2000

Regulatory Contact:	Donna

CP99-191	ELK RIVER LOOP/PD2K YR 3 - Prior notice filing for authorization to install and operate approximately 15 miles of 16 inch loop to meet firm entitlement for Peak Day 2000 shippers Year 3 off the Elk River Branchline.  The prior notice filing was protested and therefore pursuant to the regulations the application was treated as a case-specific filing.  The Order issued September 30, 1999 approved the entire project along Northern’s proposed route pursuant to its blanket certificate.  On November 1, 1999, Winslow Holasek filed a timely request for rehearing of the Commission‘s Order approving this project Order Denying Rehearing and Reconsideration and Dismissing Motion to Stay was issued March 24, 2000.  The Phase I facilities were placed in-service on November 29, 1999. A request for a waiver of the blanket cost limits was filed on June 13, 2000.   FERC responded on July 7 that the request for a waiver was premature unless Northern had information that showed the estimated costs would exceed the blanket cost limits.  On July 17, 2000, Northern filed a supplement to its request for a DL along 160th Lane.  Northern agreed to the City's conditions.  A DL was issued on July 21 approving the change is construction method.  Construction along 160th Lane was completed on August 11, 2000.  Installation of the pipe along 160th Lane resulted in only minor damage the curbs of 160th Lane.  The City engineer will conduct an inspection of repairs the week of September 11, 2000.  On August 15, 2000, Northern filed a request to commence service through the Phase II facilities.  The DL has not been issued.  FERC's environmental staff will conduct an inspection on September 13 and 14th.  Hopefully, a DL to place the facilities in-service will be issued following this inspection.  Restoration is proceeding satisfactorily therefore we do not expect any issues to arise during the inspection.

Filed:	02/02/99

Order Issued:	09/30/99 88 FERC ¶ 61,327 (1999)

Certificate Accepted:	10/01/99

Order Denying Rehearing:	03/24/00  90 FERC ¶ 61,296 (2000)

Regulatory Contact:  Michele

CP99-75	A-LINE ABANDONMENT - Section 7 application for permission and approval to abandon: (1) four (4) segments totaling 52 miles of the A-Line in Kansas, Iowa, Nebraska, and Texas; (2) abandon, and relocate in some instances, small volume meter stations; and (3) certain services rendered thereby.  On December 7, 1999 held a meeting with several groups, including Communications and Legal, to discuss/ the Historic Context and assure that no one had a problem with the document.  There are some discrepancies, which will be discussed with the third party historian and resolved prior to issuance of a final document.  On December 22, filed Notice of Abandonment stating that as of December 2, 1999 the final piping was removed from the Texas, Nebraska and Iowa portions of the project.  On March 1, 2000 filed revised Historic Context.  Copies to be sent to the various SHPOs for their comments in order to receive director’s letter.  Also notified FERC pre- and –post construction testing of water wells was completed and showed no problems or inconsistencies.    On May 16, 2000 filed SHPO’s responses to the revised Historical Context and requested a director’s letter.  Notified FERC that minimal activities would occur at the Iowa River this year.  On June 9, 2000 received director’s letter to abandon the Kansas segment and conduct minimal activities at Iowa River.  The historian at the Iowa SHPO has requested additional information to be included in the Historic Context showing the effect pipelines had in Iowa before they will recommend clearance for the abandonment of the Iowa River segment which is currently scheduled to be completed in 2001.   On 7/26/2000 received director’s letter authorizing a 7/13/2000 request: (1)  to abandon 1500 feet of Kansas A-Line in-place per landowner request to preserve shelter belt near his residence and (2) to use fill dirt from offsite sources where the subsoil contains high clay content.  Work stopped on July 31, 2000 while FWL investigated possible siting of whooping crane (endangered species).  The determination was made that it was not a whooping crane.  The FWL was very appreciative and impressed that we called and stopped work.  On 8/18/2000 filed notice that the 2.46 mile pipeline segment at the Iowa River was cut and capped as of 8/16/2000.  Any further activity on this segment is prohibited until clearance is received from the Iowa SHPO regarding their request for an additional 36 page historical context pamphlet.  On 9/11/2000 reported notice that the Kansas segment has been removed as of 9/6/2000.

REMAINING CONDITIONS:

- Notice of abandonment.

Filed:	11/13/98

Order Approving Abandonment: 	06/17/99 87 FERC ¶ 62,307 (1999)

Regulatory Contact:  Donna

CP98-229	KN GATHERING/LIBERAL FACILITIES SALE - Section 7(b) application for permission and approval to abandon, by sale to KN Gas Gathering, approximately 33 miles of pipeline with appurtenant facilities located in the Liberal area (Liberal Facilities). An amendment to the December 30, 1997 Asset Purchase Agreement (APA) was executed on January 29, 1999 that extended the term of the agreement. A Second Amendment to the Asset Purchase Agreement was executed January 31, 2000 extending the terms of the agreement until March 31, 2000.  An agreement to assign the original Asset Purchase Agreement, as amended, to OneOk, Inc. was executed April 5, 2000.  OneOk has until July 5, 2000 to notify Northern of its intent to purchase the subject facilities. By letter dated June 26, 2000, ONEOK officially exercised its right to terminate the Asset Purchase Agreement for this transaction.  However, ONEOK also indicated that it planned to make an unsolicited arms length offer to purchase these facilities.  If an offer is not made for these assets, Northern will file to vacate this order.  Waiting for Marketing regarding the timing of a filing.

REMAINING CONDITION:

- Notice of abandonment must be filed within ten (10) days.

Filed:		02/13/98

Order Approving Abandonment:		12/22/98  85 FERC ¶ 61,418 (1998)

Regulatory Contact:  Michele

CP98-234	WESTAR/AG/SKELLYTOWN FACILITIES SALE - Section 7(b) application for permission and approval to abandon by sale to Westar certain facilities downstream of Cargary Plant and by sale to American Gathering all facilities upstream of Cargary Plant.  Facilities include approximately 72 miles of pipeline, fifteen (15) units at four (4) compressor stations, all receipt and delivery points on the facilities, and appurtenant facilities (Skellytown Facilities).  An Asset Purchase Agreement (APA) was executed December 30, 1997.  Southern Union filed to withdraw its protest on January 27, 1999.  An amendment to the APA was executed on January 29, 1999 extending the terms of the agreement.  An Order Granting in Part, and Denying in Part Abandonment Authorization was issued on December 22, 1999.  The Commission approved the abandonment by sale (as non-jurisdictional gathering) to American Gathering the facilities located upstream of the Cargary Plant and the abandonment of the X-22 rate schedule.  The Commission denied Northern’s request to abandon facilities to be sold to Westar.  Such facilities are located downstream of the Cargary Plant.  The subject facilities would not be integrated into Westar’s Hinshaw system and therefore, can not be declared non-jurisdictional.  The tariff filing to cancel the X-22 rate schedule was filed on January 21, 2000.  A Second Amendment to the Asset Purchase Agreement was executed January 31, 2000 extending the terms of the agreement until March 31, 2000 for the American Gathering Assets.  This Amendment terminated the agreement with respect to the Westar Assets.  An agreement to assign that portion of the agreement for the facilities upstream of the Cargray Plant under the original Asset Purchase Agreement, as amended, to OneOk, Inc. was executed April 5, 2000.  OneOk has until July 5, 2000 to notify Northern of its intent to purchase the subject facilities.  By letter dated June 26, 2000, ONEOK officially exercised its right to terminate the Asset Purchase Agreement for this transaction.  On August 31, 2000, Northern filing a Motion to Partially Vacate this order.

REMAINING CONDITIONS:

- Notice of abandonment must be filed within ten (10) days.

Filed:		02/13/98

Order Granting in Part and

Denying in Part Issued:		12/22/99 89 FERC ¶ 61,317 (1999)

Regulatory Contact:  Michele

CP98-132	D-LINE EXTENSION - Section 7(c) application for permission and approval to construct and operate approximately 9.6 miles of 30-inch to complete the D-line between the Owatonna and Faribault compressor stations. Preliminary Determination granting non-environmental approval of the project issued April 23, 1998.  Northern is placed at-risk for the project costs. A transportation contract for the 40,000 must be executed prior to commencement of construction. Northern did not construct the proposed facilities by the June 30, 1999 deadline.  An Extension of Time was granted on May 12, 1999 to November 1, 2000..  See above for amended application.

Filed:		12/15/97

Preliminary Determination issued:		04/23/98 83 FERC ¶61,074 (1998)

Final order:		06/30/98 83 FERC ¶61,354 (1998)

Certificate Accepted:		07/16/98

CP98-132-001		Amendment filed:		08/02/00

Amendment noticed:		08/11/00

Regulatory Contact:  Michele

# CERTIFICATES PENDING FERC APPROVAL

TRANSWESTERN PIPELINE COMPANY

NONE

NORTHERN NATURAL GAS COMPANY

CP98-744	EL PASO/SSL FACILITIES - Section 7(b) application for permission and approval to abandon by sale to El Paso Offshore Gathering and Transmission Company certain of Northern’s Seagull Shoreline laterals (T0S-83421, TOS-83431, TOS-84071, TOS-84961, TOS-85411).  Protests were filed by Amoco and Anadarko regarding El Paso’s need to provide interruptible service for the life of the reserves comparable to Northern’s service.  Response to Protests filed October 19, 1998.  El Paso filed a Petition for Declaratory Order on February 1, 1999 in Docket No. CP99-188.  Northern and El Paso entered into an Amendatory Agreement regarding certain changes to the purchase price adjustment and modifications to the termination provision of the original agreement.  The Amendatory Agreement was filed May 8, 2000.

Filed:					08/25/98

Noticed:				08/28/98

Intervention Period Ends:		09/18/98

Regulatory Contact:	Michele

# PROJECTS TO BE FILED

TRANSWESTERN PIPELINE COMPANY

Project cancelled.

NORTHERN NATURAL GAS COMPANY

JOSIE		OLSEN FARM TAP ABANDONMENT – Prior notice filing to abandon by sale to Peoples farm taps located in Minnesota.  Draft in progress.

VIG		OMAHA MUD BRANCHLINE AND TBS #1E SALE – Section 7(b) filing to abandon by sale to MUD approximately 5 miles of the 16” Omaha BL #2 and the Omaha #1E TBS on the BL.  Draft routing completed and changes incorporated. The filing is currently on hold pending finalization of the Sale Agreement and the analysis of alternative business/operation strategies involving an enlarged piece of the branchline and related facilities.

DONNA	GALLUP HORSEPOWER MODIFICATION – Section 7(c) to program computer software at the Gallup Compressor Station to establish the existing unit as an 11,000 horsepower unit with a 1.1 service factor increasing capacity by 30,000 MMBtu on the mainline.   Waiting on further analysis.

VIG		A-LINE ABANDONMENT - PLATTE RIVER – Section 7(b) filing to abandon the A-Line and appurtenant equipment (i.e., the bridge) over the Platte River in Saunders County, Nebraska.  Construction bid accepted.  Draft in progress.

VIG		SUNRAY UNIT #9 – Section 7(b) filing to abandon, in place, the unit #9 compressor at Sunray.   Draft currently being reviewed for comments and revisions.  Anticipate filing during the second week of September.