| EES/WHS Integration-Business Planning Team Two-Week Schedule (10/23 – 11/6) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Date | Subject | # Objective | Room | Time | Attendees |
| Tuesday 10/23 | EES, WHS – Trading & Scheduling Mtg. 1 | Trading and Scheduling process and interfaces | 8C1 – Houston Mt. Adams Portland | 4-6:30 CST | Narsima Misra Corry Bentley Murray O’Neil Vladimir Gorny Jeff Richter Greg Woulfe |
| Wednesday 10/24 | ROC Review | High level overview of ROC and interfaces to the ROC | 2559 | 4:30 – 5:30 CST | Fred Kelly Lloyd Will Jeff Richter |
| Wednesday 10/24 | EES – Risk Management (valuation, flash) | Document processes and systems overlay | 2559 | 2 – 3:30 | Kristin Albrecht Todd Busby Stacey White |
| Thursday, 10/25 | EES, WHS – Trading, Scheduling and Settlements Mtg. 2 | Document Settlements interfaces to Trading and Scheduling, Review results from Tuesday’s meeting | 30C2 Houston Mt. Adams Portland | 11-1:30 CST | Jeff Richter Murray O’Neil Thresa Allen Rogers Herndon Smith Day Greg Woulfe |
| Friday, 10/26 | EES – Energy Asset Mngt | Document processes and interfaces | TBD | 10-12:30 (May move to 2pm CST) | Greg Woulfe Malik Avs Beth Jenkins Vladimir Gorny Mike Frazier |
| Monday, 10/29 | WHS/EES – Settlements and Vol. Mngt Detail | Document detailed processes in Settlements and Vol. Mngt. | 2559 | 3-5 CST | Murray O’Neil Thresa Allen Kristin Albrecht |
| Tuesday, 10/30 | EES – Trading, Settlements, Asset Management Systems Overlay | Review results from previous meetings. Apply systems overlay to processes | 2556 | 3:30-5:30 CST | Rogers Herndon Jeff Richter Murray O’Neil Narsima Misra Corry Bentley Greg Woulfe Malik Avs Beth Jenkins Vladimir Gorny Michael Frazier |
| Wednesday, 10/31 | EES, WHS – Review Systems Overlay with IT | Review business results with IT. Apply systems overlay. Discuss implementation plan | TBD | 8:30-1:00 CST | Anthony Dayao Steve Nat Pablo Pissanetzky Kenny Ha Neal Symms David Poston Duong Luu Norman Lee Michael Fink Ramesh Rao |
| Friday, 11/2 | Deliverables due |  |  | COB |  |
| Tuesday, 11/6 | Final Presentation |  |  | 9 – 12 |  |

**This schedule is preliminary and will be updated daily

**All meetings:  Debra Bailey, Todd Busby, Fred Kelly, Lloyd Will