##### SCHEDULE 1

#### Station Mechanical, Electrical and Civil  Construction

Enron Midstream Services, L.L.C. will install coal bed methane gathering systems in Northeast Wyoming during the second quarter of 2000 in accordance with the following "Scope of Work".

# Job Scope

The Scope of Work for this section is the mechanical, civil, electrical and instrumentation portions of the Haracz, Mustang and Palomino Compressor Stations. Contractor is to provide all supervision, labor, equipment and materials (except materials provided by Company) to construct the mechanical, civil, electrical and instrumentation portions of the Haracz, Mustang and Palomino Compressor Stations. At this time, the scopes of facilities to be constructed are as follows:

## Haracz Compressor Station

From Gillette, WY go South & Southeast on Hwy 50 approximately 7 1/2 miles to Bell Rd. (CR8).  Then turn south (left) 7 miles to Red & White mail box on top of hill turn left about 1/2 mile to Booster Station site (in Sec. 36, T48N/R73W), this compressor station is located on a new site and consists of:

- Gas Inlet Facilities, including pig receiver and slug catcher

- (2) Caterpillar 3516/Arial Compressor (1000 HP nominal) skids – (Hanover packages)

- (1) Gas Measurement Skid – (Scott Equipment Package)

- (1) Gas Dehydration skid – (J.W. Williams package)

- Electrical service provided by the local utility

- Discharge Interconnect with gas transmission line

All suction and discharge piping, tubing, electrical and instrumentation is included in this scope of work.  (Pre-fabrication of piping spools performed off-site is not included in this scope of work).

Sandblasting, priming and top coat painting of piping and equipment.  Installation of fiberglass insulation as required.

Building erection.

## Mustang Compressor Station

From Gillette go South on Hwy 59 12 miles, turn right, there will be 5 tanks as you turn. Go on 2 3/4 miles staying to the right to Booster Site (in Sec. 16, T48N/R72W), this compressor station is located on a new site and consists of:

- Gas Inlet Facilities, including pig receiver and slug catcher

- (2) Caterpillar 3516/Arial Compressor (1000 HP nominal) skids – (Hanover packages)

- (1) Gas Measurement Skid – (Scott Equipment Package)

- (1) Gas Dehydration skid – (J.W. Williams package)

- Electrical service provided by the local utility

- Discharge Interconnect with gas transmission line

All suction and discharge piping, tubing, electrical and instrumentation.  (Pre-fabrication of piping spools performed off-site is not included in this scope of work).

Sandblasting, priming and top coat painting of piping and equipment.  Installation of fiberglass insulation as required.

Building erection.

## Palomino Compressor Station

From Gillette go South on Hwy 59 approximately 16 miles, turn right at top of hill on Hoe Creek Rd. (CR54). Then go 4 1/2 miles to road on top of hill, turn right to Palomino Booster site about 1 1/4 miles (in Sec. 5, T47N/R72W), this compressor station is located on a new site and consists of:

- Gas Inlet Facilities, including pig receiver and slug catcher

- (2) Caterpillar 3516/Arial Compressor (1000 HP nominal) skids – (Hanover packages)

- (1) Gas Measurement Skid – (Scott Equipment Package)

- (1) Gas Dehydration skid – (J.W. Williams package)

- Electrical service provided by the local utility

- Discharge Interconnect with gas transmission line

All suction and discharge piping, tubing, electrical and instrumentation.  (Pre-fabrication of piping spools performed off-site is not included in this scope of work).

Sandblasting, priming and top coat painting of piping and equipment.  Installation of fiberglass insulation as required.

## Building erection.

### Job Schedule

The Scope of Work above will be conducted in the following circumstances:

- The current construction schedule for the compressor stations is as follows:

- Haracz Compressor Station

- Site work will begin on March 15, 2000.

- Compressor Delivery; Available April 5, 2000.

- Dehydrator Skids; Available April 5, 2000.

- Mechanical completion required on May 5, 2000.

- Mustang Compressor Station

- Site work will begin on March 15, 2000.

- Compressor Delivery; Available April 5, 2000.

- Dehydrator Skids; Available April 5, 2000.

- Mechanical completion required on May 5, 2000.

- Palomino Compressor Station

- Site work will begin on March 15, 2000.

- Compressor Delivery; Available April 5, 2000.

- Dehydrator Skids; Available April 5, 2000.

- Mechanical completion required on May 5, 2000.

### Materials

- All materials, except those specifically stated herein as being supplied by the Contractor, will be provided by Company.

- Company supplied materials will be delivered to the site, with the Contractor responsible for off loading and assuming responsibility for the equipment upon delivery.

- A skidded material consignment warehouses will be put on the compressor job sites. These material warehouses will provide all miscellaneous materials such as small fittings, small valves, gaskets, bolts, etc.

- Materials to be supplied by the Contractor are:

- All concrete, rebar and forming materials. Consumables, such as weld rod.

- All necessary tools.

- Instrument tubing and fittings.

- All conduit, wire and fittings.

- All necessary tools.

- Contractor is responsible for installation, including tubing, of all instruments.

### Representative

Company will supply an on site Company Representative who will be the Contractor’s  contact for work at that site. Other technical or inspection support will be provided as required. The Contractor will be responsible for on site supervision and work direction of their labor force.

### Miscellaneous

- Included in this package is a set of drawings for a compressor station titled “Hannum Compressor Station”. This station is similar to the stations that will be constructed for Company. Assume that the Contractor will have a set of drawings to build from of similar quality.

- The Scope of Work provided by the Contractor will include the following:

- The electrical work.

- Site Grading and drainage work as shown in the drawing package.

- Piered foundations provide estimates for foundations w/o piers. Piers required for pipe supports, etc. shall be included in the estimate.

- Contractor or their sub-contractor shall erect the compressor building.

### Specifications

- Included in this package is a set of construction standards to be used on the scope of work. The individual standards that apply to the scope of work are as follows:

- Earthwork Specification

- Concrete Specification

- Mechanical Specification

- Instrument Specification

- Electrical Specification

Also included in this package is a compact disk with Company’s Engineering Standards.  Where discrepancies are found to exist between the two sets of specifications, Contractor agrees to notify Company and both parties will decide which specification shall govern on a case by case basis.

### Pricing

Contractor agrees to perform all the work in accordance with the terms and conditions of this Scope of Work and the Agreement for the following lump sum prices:

Haracz Compressor Station				$513,757.00

Mustang Compressor Station 			$508,501.00

Palomino Compressor Station			$523,172.00

Plus $19.20/Yrd. for rock installation.