Power Trading Systems – Executive Summary & Scorecard

Fundamentals / Deal Administration / Position Management / Scheduling / Volume Management / Risk / Asset & Control Area Operations

## Week Ending 8/31/01

### Projects

Initiative							Target Date	Status							FTE’s

-------------------------------------------------------------------------	---------------	----------------------------------------------------------------	-------

ERCOT Market	 Operating System (MOS)			12/15/01	Development						2

Frontera Revenue Meter Readings

ERCOT Resource Imbalance Settlement

Distributed Event Notification Application

ERCOT Communications

Bid / Schedule / Settlement Transactions

RTU/DNP RT Operational Data

Modem Bank / RTU / DNP Relocation

Plant Monitoring & Control Systems (EMS / PI)			10/15/01	Development						1

Network / Firewall / ESCA Frame Relay Setup

Parallel EMS Systems Configuration and Installation

Control Room Migration from EBN to EBS

TVA (Allegheny) RTU Data Points via ICCP

Databeacon Cubes – Phase II					9/15/01		Development						1

MW Daily Index Prices for All Regions

DA / Real Time LMP’s for PJM/NYISO

16 Hour Avg / Peak Load for All Regions

24 Hour Avg Load for All Regions

Real-Time Traders WorkBench – Services Desk – Phase II	9/17/01		Development						1.5

Database Migration / Share with Extranet

Services Desk Extranet						TBD		Inception						.5

Expose PMI/Fundamental Data to Services Customers

MetaStock Analytics – Phase II					10/01/01	Development						2

Off-Peak Power Prices

Additional Power Curves

Strip Averaging

User Profile Improvements

Additional Heat Rate Calcs

NorthEast Gas Curves Model

NEPOOL Analysis Model

Convert DLL’s to C#

Risk Curve Mgr & Curve Shift Position Mgr – East Desk	10/01/01	Complete – Must Be Deployed with CPM		1

Risk Curve Mgr &  Curve Shift Position Mgr - Phase II 		11/01/01	Development						1

Real Time Gas Prices - Heat Rates  & Gas Curveshift

Security Revisions – Isolate Desk Positions

Swaption Volatility Matrix Implementation

Position Reporting – 30 Day History

Curve History – Tabular and Graphical Form

Correlation Curves for Asian Options

Volatility Curve Dependency

Options What-If Analysis Based on Curve Changes

Real-Time P&L Based on New / Changed Deals			TBD		Not Started – Pending Sponsorship			0

Portcalc & Monetary Position Manager Changes

West Desk FSP							N/A		In Production – CAPS Retirement Pending VMS		3

West Desk VMS – Production Milestone 5			9/15/01		In Production Parallel					10

Consolidated Position Manager – Phase I			9/17/01		In User Test / QA Test					2

Real-Time Enhancements

Architecture Improvements – Reliability & Failover

Consolidated GUI and Drill-Down Capability

Pos Mgr, Real-Time Pos Mgr, DA Pos Mgr, Fwd Obs

Consolidated Position Manager – Phase II			TBD		Not Started						0

Architecture Improvements – Performance

Load Balancing & Caching

Risk Position Mgrs & FSP Position Mgr

Customer Services Portal – Phase I – 2 Customers		9/30/01		Development						1

Web Pages – Manual and Electronic

Schedule Submission, Verification, Communication

EC Outlook Translation Engine

Deal Pathing, Routing, and Bookout Rewrite			9/07/01		In User Test / Iterating Through Revisions		1

Options Management Improvements – Phase II			N/A		In Prod							0

Portcalc Option Predictives Reporting

Option Blending & Volatility Smile

Ontario Market Solutions					12/30/01	Development						4

NUG Cost/Charge Model Engine

IMO Connectivity

Global Meter Data

VMS / FSP Integration

EnPower Legal Entity Revisions					9/6/01		In User Test						.5

Portcalc / EnPower Deal Type Expansion – Phase I		N/A		In Prod							0

Asian Options

Averaging Index Forwards

Portcalc / EnPower Deal Type Expansion – Phase II		9/28/01		In User Test						1

Renewable Energy Credits

SRA Deal for Australia

Portcalc / EnPower Deal Type Expansion – Phase III		TBD		Not Started – Pending Resource Availability		0

Ancillary Services

Index Options

Averaging Basis Options

EnPower Near-Term Performance Improvements		11/01/01	Underway						.5

DB Server Upgrades

Process Offloading

DB and Application Tuning

DB Partitioning

Delphi 6 Upgrade / DOA

Long-Term Architecture Design					TBD		Not Started – Pending Sponsorship			0

Data Model Re-Design

Object Model Design

Functional Migration Plan

Development Tool Decisions

West Desk Fundamentals High-Availability Solution		TBD		Discovery						.25

Projected Heat-Rate Curve App

EnPower Online						TBD		On Hold – Pending Resource Availability		0

Release Notes

Outage Notification / System Information

Option Sensitivities – Multi-Variable Manipulation		9/30/01		In User Test						1

Data Harvesting							12/15/01	Development						2

PJM FTR’s

TVA Preschedule Information

ERCOT Market Data (Prices, Load Fcsts, Weather)

SPP &  SERC Market Data

NYISO & PJM DA / RT LMP’s

#### Enhancements

Rank	Initiative					Sponsor	Target Date /		Status						FTE

Workday Est

-----	------------------------------------------------------	---------------	-----------------		-------------------------------------------------------	-------

1	Add Transmission Volumes to PCS or		White		TBD			Waiting for User Specs				0

Volume Validation Report

2	Perform Credit Check on Deal Entry		White		TBD			Waiting for User Specs				0

3	Add Broker to Auto-Confirm Rules in		Theriot		15 WD’s		Not Started – Pending Resource Availability	0

Table Edit

4	Calculate Swaption Volatility from a Curve	White		TBD			Not Started					0

(Portcalc Changes)

5	Create Link Between Excel Valued Deals	White		TBD			Not Started					0

and Oracle Adhoc Tables

6	Change the Curve Files to Read From the	White		TBD			Not Started					0

New Oracle Curve Tables

7	Content Additions to the East Desk Portal	Imai		9/7/01			Development					1

for the ERCOT ISO

8	Content Additions to the East Desk Portal	Imai		N/A			In Prod						1

Related to Nuclear Plant Status

9	Content Additions to the East Desk Portal	Imai		11/15/01		Development					2

Related to Hydro Plant Status

10	Content Additions to the East Desk Portal	Imai		N/A			In Prod						1

Related to the Reuters Feed

11	Upgrade EMS to EMP 2.1.1			Will		11/30/01		Development					2

12	Modify All Risk Spreadsheets to Utilize		White		TBD			Not Started					0

the New Oracle Curve Tables

13	Provide Mechanism to Perform Adhoc		White		TBD			Not Started					0

Table Queries

14	Add Cross-Portfolio Flag to Deals for Portcalc	White		TBD			On Hold – Pending Resource Availability	0

15	Apply a Technical Release Upgrade to the 	Imai		9/14/01			Development					1

East Desk Portal (.Net Beta 2)

16	Portcalc Expansion – Canadian Heat Rate	White		9/15/01			In User Test					.25

Swaps

17	Add Counterparty Financial Contract to		Theriot		5 WD’s			Not Started					0

Deal Entry Selection Criteria

18	Provide Verification and Audit History		Dupuy		5 WD’s			Not Started					0

Tools for Calgary EnPower Upload

19	Provide Pub Codes Archiving Capability	White / Allen	15 WD’s		Not Started					0

20	Build MKM Adaptor for Power Curves		Nat		9/15/01			In Unit Test					1

21	Convert PERL scripts to Knowmadic		Nat		TBD			Not Started					0

# Production Support

Category				Hours		FTE 		Prod Migrations		Success Rate		Same Day Delivery

----------------------------			-------		------		--------------------	----------------		-----------------------

Break-Fix				96		3		2			100%			1

Small Enhancements			*		*		1			100%			0

Projects					*		*		0			N/A			N/A

Consultation & Maintenance		78		2		N/A			N/A			N/A

* Captured In Projects and Enhancements Sections as FTE Equivalents