Power Trading Systems – Executive Summary & Scorecard

Fundamentals / Deal Administration / Position Management / Scheduling / Volume Management / Risk / Asset & Control Area Operations

## Week Ending 9/28/01

### Projects

Initiative							Target Date	Status							FTE’s

-------------------------------------------------------------------------	---------------	----------------------------------------------------------------	-------

ERCOT Market	 Operating System (MOS)			12/15/01	Development						2

Frontera Revenue Meter Readings

ERCOT Resource Imbalance Settlement

Distributed Event Notification Application

ERCOT Communications

Bid / Schedule / Settlement Transactions

RTU/DNP RT Operational Data

Modem Bank / RTU / DNP Relocation

ISO Analytics – Phase I						N/A		In Prod							1

ERCOT Price and Load Report

NYISO Price and Load Report

ISO Analytics – Phase I	I					10/30/01	Development						1

ERCOT Morning Report

PJM Price and Load Report

ERCOT Load Consolidation

Plant Monitoring & Control Systems (EMS / PI)			10/15/01	Development						1

Network / Firewall / ESCA Frame Relay Setup

Parallel EMS Systems Configuration and Installation

Control Room Migration from EBN to EBS

TVA (Allegheny) RTU Data Points via ICCP

Databeacon Cubes – Phase II					10/15/01	Development						1

MW Daily Index Prices for All Regions

DA / Real Time LMP’s for PJM/NYISO

16 Hour Avg / Peak Load for All Regions

24 Hour Avg Load for All Regions

Real-Time Traders WorkBench – Services Desk – Phase II	10/30/01	Development						1.5

Database Migration / Share with Extranet

Services Desk Extranet						TBD		Inception						.5

Expose PMI/Fundamental Data to Services Customers

MetaStock Analytics – Phase II					N/A		In Prod						2

Off-Peak Power Prices

Additional Power Curves

Additional Heat Rate Calcs

NorthEast Gas Curves Model

NEPOOL Analysis Model

MetaStock Analytics – Phase III					10/30/01	Development						2

Strip Averaging

User Profile Improvements

Convert DLL’s to C#

Add Fuel Oil

Add Emissions

Risk Curve Mgr & Curve Shift Position Mgr – East Desk	10/01/01	Complete – Users Requesting Deployment with CPM	1

Risk Curve Mgr &  Curve Shift Position Mgr - Phase II 		11/01/01	Development						2

Real Time Gas Prices - Heat Rates  & Gas Curveshift

Security Revisions – Isolate Desk Positions

Swaption Volatility Matrix Implementation

Position Reporting – 30 Day History

Curve History – Tabular and Graphical Form

Correlation Curves for Asian Options

Volatility Curve Dependency

Options What-If Analysis Based on Curve Changes

Real-Time P&L Based on New / Changed Deals			TBD		Not Started – Pending Sponsorship			0

Portcalc & Monetary Position Manager Changes

West Desk FSP							N/A		In Production – CAPS Retirement Pending VMS		3

West Desk VMS – Production Milestone 5			10/15/01	In Production Parallel					10

Consolidated Position Manager – Phase I			10/01/01	In User Test / QA Test - Iterating			2

Real-Time Enhancements

Architecture Improvements – Reliability & Failover

Consolidated GUI and Drill-Down Capability

Pos Mgr, Real-Time Pos Mgr, DA Pos Mgr, Fwd Obs

Consolidated Position Manager – Phase II			TBD		Not Started						0

Architecture Improvements – Performance

Load Balancing & Caching

Risk Position Mgrs & FSP Position Mgr

Add Other Desk Traded Commodities

Customer Services Portal – Phase I – 3 Customers		10/15/01	Development						1

Web Pages – Manual and Electronic

Schedule Submission, Verification, Communication

Deal Pathing, Routing, and Bookout Rewrite			10/01/01	In User Test						1

Ontario Market Solutions					12/30/01	Development						4

NUG Cost/Charge Model Engine

IMO Connectivity

Global Meter Data

VMS / FSP Integration

Portcalc / EnPower Deal Type Expansion – Phase II		9/28/01		In User Test						.5

Renewable Energy Credits

SRA Deal for Australia

Index Options

Asian Options

Portcalc / EnPower Deal Type Expansion – Phase III		TBD		Not Started – Pending Resource Availability		0

Ancillary Services

Averaging Basis Options

EnPower Near-Term Performance Improvements		11/01/01	Underway						4

DB Server Upgrades

Process Offloading

DB and Application Tuning

DB Partitioning

Delphi 6 Upgrade / DOA

Long-Term Architecture Design					TBD		Not Started – Pending Sponsorship			0

Data Model Re-Design

Object Model Design

Functional Migration Plan

Development Tool Decisions

West Desk Fundamentals High-Availability Solution		10/01/01	Options Identified / Developing Time & Cost		.25

Projected Heat-Rate Curve App

EnPower Online						TBD		On Hold – Pending Resource Availability		0

Release Notes

Outage Notification / System Information

Option Sensitivities – Multi-Variable Manipulation		9/30/01		In User Test						.25

Data Harvesting							12/15/01	Development						2

PJM FTR’s

TVA Preschedule and Load

ERCOT Market Data (Prices, Load Fcsts, Weather)

Hydro Data

NYISO & PJM DA / RT LMP’s

#### Enhancements

Rank	Initiative					Sponsor	Target Date /		Status						FTE

Workday Est

-----	------------------------------------------------------	---------------	-----------------		-------------------------------------------------------	-------

1	Add Transmission Volumes to PCS or		White		TBD			Waiting for User Specs				0

Volume Validation Report

2	Perform Credit Check on Deal Entry		White		TBD			Waiting for User Specs				0

3	Create Link Between Excel Valued Deals 	White		TBD			Waiting for User Specs				0

and Adhoc Tables

4	TAGG ERMS to EnPower Interface		White		TBD			Waiting for User Specs				0

Improvements

5	Weather Data Migration (DA/HA/RT -		Imai		10/30/01		Development					1

Oracle and VB)

6	Content Additions to the East Desk Portal	Imai		11/15/01		Development					2

Related to Hydro Plant Status

7	Upgrade EMS to EMP 2.1.1			Will		11/30/01		Development					2

8	Apply a Technical Release Upgrade to the 	Imai		10/01/01		Development					1

East Desk Portal (.Net Beta 2)

9	Add Additional Queries to the Adhoc Tables	Imai		10/15/01		Development					1

10	Portcalc Expansion – Canadian Heat Rate	White		10/01/01		In User Test					0

Swaps

11	Add Broker to Auto-Confirm Rules in		Theriot		15 WD’s		Not Started – Pending Resource Availability	0

Table Edit

12	Enhance Deal Upload to Include			Allen		10/15/01		In User Test					.5

Transmission Deals

13	Add Job Scheduling and Ops Monitoring	Allen		12/01/01		Not Started					0

Capability to CARP Report

14	Calculate Swaption Volatility from a Curve	White		TBD			Not Started					0

(Portcalc Changes)

15	Create Link Between Excel Valued Deals	White		TBD			Not Started					0

and Oracle Adhoc Tables

16	Change the Curve Files to Read From the	White		TBD			Not Started					0

New Oracle Curve Tables

17	Cooper Notification Service			Imai		TBD			Inception					1

18	Provide Job Scheduling Capability for		Imai		TBD			Inception					1

Web Scraping Apps

19	Modify All Risk Spreadsheets to Utilize		White		TBD			Not Started					0

the New Oracle Curve Tables

20	Provide Mechanism to Perform Adhoc		White		TBD			Not Started					0

Table Queries

21	Add Cross-Portfolio Flag to Deals for Portcalc	White		TBD			On Hold – Pending Resource Availability	0

22	Add Counterparty Financial Contract to		Theriot		5 WD’s			Not Started					0

Deal Entry Selection Criteria

23	Provide Verification and Audit History		Dupuy		5 WD’s			Not Started					0

Tools for Calgary EnPower Upload

24	Provide Pub Codes Archiving Capability	White / Allen	15 WD’s		Not Started					0

25	Build MKM Adaptor for Power Curves		Nat		10/15/01		In System Test					0

26	Convert PERL scripts to Knowmadic		Nat		TBD			Not Started					0

27	Provide Ability to Review Deal Changes		Bentley		TBD			Waiting for User Specs				0

Over a User Defined Time Horizen

# Production Support

Category				Hours		FTE 		Prod Migrations		Success Rate		Same Day Delivery

----------------------------			-------		------		--------------------	----------------		-----------------------

Break-Fix				100		2.5		6			100%			0

Small Enhancements			*		*		2			100%			0

Projects					*		*		0			N/A			N/A

Consultation & Maintenance		160		4		N/A			N/A			N/A

* Captured In Projects and Enhancements Sections as FTE Equivalents