Memo

Enron North America

To:	Ray Hoppe

From:	Ben Rogers

CC:	Terra Industries

Date:	9/28/2025

Re:	Project Cost Analysis

Ray:

Per your memo regarding the description of the proposed facility in Tulsa, OK. Here are the total project costs associated with building a two LM 6000 (enhanced sprint package) facility.  The facility will be run in simple cycle mode with a total of 46.0 MW’s per unit.  Project has a heat rate of 10,300 (HHV).  The VOM will be approximately $2.05 $/MWh.  Then total project costs are as follows:

Cost Figures:		$(000)

Turbines:		$28,645

Engineered Equipment:	$5,577

Gas Interconnect:	$2,500

Power Interconnect:	$1,000

Indirect Costs:		$1,260

Project Management:	$865

Switchyard Extension:	$375

Construction:		$3,147

Engineering Labor:	$475

Bulk Material:		$1,681

Chillers:			$1,900

Nepco Margin:		$1,404

IDC:			$1,606

Land:			$500

Sales & Used Tax:	$939

Cintingency:		$468

Total:			$52,342

Cost/kW:		$568.95