Summary of Contract Terms

4 LM-6000 PC Combustion Gas Turbines

Las Vegas Cogeneration II, L.L.C. Project

Delivery Point:			16415 Jacinto Port Blvd., Houston Texas

Optional Delivery Point:		Site laydown area (at option of purchaser), by change order to contract.

Delivery Date(s):			Three units by July 30, 2001; one unit by August 15, 2001

Payment terms:	Payment of remaining balance due as of [November _____, 2000] according to the Payment Schedule attached hereto.

Retention Letter of Credit:	$2,814,400, to be held by purchaser until final acceptance of last unit.  GE may replace with letter of credit in like amount.

Correction of Equipment:	GE is responsible for replacing or correcting any defective work or conditions prior to acceptance of the Unit.  GE must also correct punchlist items to Purchaser’s satisfaction within 180 days after Takeover, or Purchaser may draw on Retention Letter of credit.

Document Liquidated

Damages	1-30 days late	$600.00/day

31-90 days late	$1,000.00/day

91+ days late	$2,000.00/day

Delivery of Final

O&M Instructions

Liquidated Damages	$500.00/day if not delivered within 45 days after site delivery date of the first Unit.

Unit Delay Liquidated Damages	1-15 days late	$10,000.00/day/Unit

16+ days late	$25,000.00/day/Unit

Takeover Liquidated Damages	$25,000 per day per Unit for each date that the Unit fails to meet Take Over Criteria by the end of Time for Completion.

Exhaust Gas

Temperature Guarantee

(Combined Cycle)	Adjusted Exhaust Gas Temperature not less than 811 degrees Fahrenheit.

Exhaust Gas Energy

Guaranty (Combined Cycle)	Adjusted Exhaust Gas Energy > 89,062 BTU/sec. at 0 degrees Reference.

Specific Peformance

Near Source Sound Level

Guaranty	Near field average A-weighted sound pressure levels for each Unit < 85dB(A) (referenced to 20 micropascals) when measured at 1.5 meters above any working elevation and 1 meter from the surface.

Specific Performance Far Field

Sound Level Guaranty	Far field average A-weighted sound pressure levels as installed with GE provided auxiliary equipment for each Unit (referenced to 20 micropascals) < 65dB(A) for gas fueled and water injected Unit at 400 feet while operating at steady state loads from 50 to 100 percent.

Specific Performance

Exhaust Emissions Guaranty	Category	Value		Units of Measure

NOx		30		ppmvd @ 15% O2

CO		38		ppmvd @ 15% O2

avg./Unit @ 4 Units;

with absolute CO emission

limit from any individual Unit

not to exceed 56 ppmvd @15%

O2 at loads of 60-100% of Base

Load at Basis Conditions

VOCs		10		ppmvd @ 15% O2

PM10		4.5		lb/hr (front and back half)

NOx and PM10 emission guarantees valid for load range of 30-100% of Base Load, a compressor temperature (CIT) range of –18F through 110F and a relative humidity range of 0-100% (except the CIT range does not include those coincident ambient temperature/humidity conditions in which the ambient air must be heated to prevent inlet frosting).  CO and VOC emissions are valid for a load range of 60-100% at Basis Conditions.

Electrical Output Guaranty	Adjusted Electrical Output per Unit > 43,994 kW (net of Unit auxiliary loads).

Specific Performance Electrical

Output Guaranty	Adjusted Electrical Output per Unit > 42,234 kW (net of Unit auxiliary loads)

Heat Rate Guaranty	Adjusted Heat Rate not to exceed 8,969 BTU/kWh (LHV).

Specific Performance Heat

Rate Guaranty	Adjusted Heat Rate not to exceed 9,742 BTU/kWh (LHV).

Output Liquidated Damages	If a Unit achieves the Specific Performance Electrical Output Guaranty during Performance Test, but fails to achieve the Electrical Output Guaranty, $500.00/kW that that Adjusted Electrical Output of the Unit is less than the Electrical Output Guaranty.

Heat Rate Liquidated Damages	$3,500 per BTU/kWh (LHV) that the Adjusted Heat Rate of the Unit exceeds the Heat Rate Guaranty.

Maximum Document

Liquidated Damages	$50,000

Max. Delivery Liquidated

Damages	$8,443,200

Max. Takeover Liquidated

Damages	$8,443,200

Max. Output Liquidated

Damages	$8,443,200

Max. Heat Rate Liquidated

Damages	$5,628,800

Max. Aggregate Liquidated

Damages	$16,886,400

Overall Liability Cap	$56,288,000

See Attached Schedules

For Additional Information