Brief Summary of Lender’s Presentation (April 23, 2001)

- Operations update stated that plant operations are generally going well

- Phase II construction is 90% complete, with the LNG facility being ahead of plan

- 100% of base equity is contributed, 79% of debt for Phase II has been disbursed

- Total funding needed for Phase II is $ 2.09 Billion, $1.56 Billion is already incurred, $526 Million remaining (Another estimate shows $700 MM reqd)

- $90 MM required for debt service between June and year-end 2001.

- Additional $118 MM required for ship and LNG payments by early 2002

- Commercial Issues Update:

- Misdeclaration Allegations by MSEB

- Naphtha Contract with Indian Oil Corp. having issues

- Customs Duty increase for LNG facility could cost additional  $112 MM

- General update on MSEB/GOM credit position

- Discussion of the Godbole Committee Report

- Valuation of MSEB finances to show that without reforms Phase II is not sustainable for MSEB

- Put in a request for giving DPC Management the right to submit a Preliminary Termination Notice

- Several grounds for serving PTN discussed; each PTN delivered to be accompanied by a Transfer Notice that has to have a valuation of the project

- Termination Notice to be given only at the end of 6 month cure period, and requires Lenders’ Consent