##### CALME

##### BUSINESS UNIT COMUNICATION PLAN

Prior to the Announcement (one day before) – Business Unit Actions

| CORPORATE FOCUS (SELLER) |  |  |  |
| --- | --- | --- | --- |
| Action | Description | Responsibility | Timing |
| CALME executives/country managers conference call | Conference call to discuss timing issues, sensitive issues, final plans | CALME PR | 12 – 24 hours prior to announcement |
| Stakeholder letter | Draft a letter for CALME executives to send to partners, customers, employees, lenders, government officials | CALME PR (Prepare draft immediately) | To be sent day of announcement |
| Distribute materials/guidelines to CALME execs and country managers by e-mail | Post conference call by DH 12 – 24 hours prior to announcement. - Press release - Q&As for media - Q&As for employees - Chairman’s memo for local employees (Ken Lay) - Standardized draft letters for partners, government officials, employees, etc. - Communication guidelines - Overview of key elements of domestic and international communication plan role out - Key messages for influentials - CALME execs and country managers need to identify Tier 1, 2, 3 influentials - Inform CALME execs that after the Enron v-mail/eSpeak has concluded, they can distribute their messages to their employees. - Send them the video(s) done by Lay (and Sutton?) | CALME PR/D. Haug |  |
| Record voice mail (Joe Sutton) | Sutton or BU executive voice mail to be recorded (only for EI employees). | BU PR (we need to find out which offices cannot receive this voice mail) M. Newhouse | Will be played POST Ken Lay’s message the day after the announcement |
| Joe Sutton webcast | Need to define time, parameters | BU PR | TBD |
| FAQ sheet for website | Prepare an internal FAQ sheet for intranet website with note from DH | CALME PR |  |

Day 1-2: The Announcement (external)

| CORPORATE FOCUS (SELLER) |  |  |  |
| --- | --- | --- | --- |
| Action | Description | Responsibility | Timing |
| # Issuing of Press Release | Distribution to identified list of media contacts in Houston and BU offices | Corp. PR / BU PR | Day of Announcement, between 3:00 and 4:00 p.m. (CST) |
| # Analyst & Media Call in Houston | Key players would discuss details of the transaction to the media (option: KL alone or KL, JS/JS) | Corp. PR (room and time required) | Day of Announcement, between 3:00 and 4:00 p.m. (CST) |
| Press Kit for in-country | Fact sheets of Enron and Buyer, bios, news release (translate into Spanish, Portuguese, etc.) (option: US alone or US/International. Considerations: logistics and timing) | Corp. PR/BU PR Hal to get Enron Fact sheet and handle translation | TBD |
| Newsroom (online tool) | Online distribution of press release and a few standard FAQs: BU and Corp. websites (define what languages). Define who updates FAQs on a daily basis. | Corp. PR / BU PR Advise Corp. of need to have in multiple languages. We should supply in Spanish. We need to define who updates with Corp, i.e. new questions, etc. | Day of Announcement, one hour after release |
| CALME BU FOCUS (BUYER) |  |  |  |
| Spokesperson | These individuals need: - Prep session - Message points - Q&As - Designation by country/region Guidelines: - In-country spokespersons handle local media inquiries re: specific CALME issues - Houston spokespersons international media inquires re: specific CALME issues - Media inquiries re: all other issues referred to Corp. spokespersons | Middle East – Rick Bergsieker David Haug/Dennis Vegas cover all wire service calls regardless of market Enron Corp. - Mark Palmer - Karen Denne | On-going |
| Stakeholders and key influentials: visits (compile a list of in-country Tier 1, 2, and 3 individuals, such as govt. officials, lenders, civic leaders, customers) | Personal visits and / telephone calls by BU CEO and management Personal visit and/or personal letter from Joe Sutton/DH/sub-regional director or country managers There are certain key influentials, i.e., government leaders, lenders, where personal relationships beyond the country managers are required, etc. In those cases the sub regional directors and Chairman should determine who should address. | CALME PR to coordinate David Haug, Shawn Cumberland, Mariella Mahan, Dan Castagnola, Rick Bergsieker | Request appointments with relevant stakeholders one or two days prior to date of announcement |

Week One:

| CALME BU FOCUS (BUYER) |  |  |  |
| --- | --- | --- | --- |
| Action | Description | Responsibility | Timing |
| Q&A update | Update internal Q&As for BUs | CALME PR | On-going |
| News room | If applicable update FAQs: CALME and Corp. websites | Corp. PR/CALME PR | On-going |
| Spokesperson (process continues) | These individuals need: - Repeated/updated messages - Q&As - CALME spokespersons handle local media inquiries re specific CALME issues - Houston spokespersons international media inquires re: specific CALME issues - Media inquiries re: all other issues referred to Corp. spokespersons | Venezuela – Ronald Pantin Puerto Rico – G. Curran Dom. Rep. – M. Mahan Panama – M. Mahan Nicaragua –R. Figueroa Guatemala – R. Figueroa Colombia – M. Mahan Jamaica – D. Vegas Middle East – Rick Bergsieker Shawn Cumberland – Caribbean Basin ## David Haug/Dennis Vegas cover all wire service calls regardless of market | On-going |
| Stakeholders – local visits to countries by CALME leadership team | Personal visit and / or contact secondary influentials (other lenders and Head of Business Associations, Chambers of Commerce) | DH and Top Management (Country managers/sub regional heads) | Second, third and fourth day after announcement |
| Media tracking | Track all news stories on wire services, TV, etc. Country managers to submit clips daily to Houston by noon Hire a team in Houston to gather clips, receive faxes from CALME offices worldwide (define process) Translation for Newco/CALME materials goes to HM for processing Country managers should not send directly to office of chairman for CALME or new EI. Create distribution list; CALME PR to distribute clips to CALME leadership team, copy to Enron Corp. | CALME PR, in-country PR team | Daily after announcement |
| Interviews in country, e.g. - Newspapers (WSJ Americas, Latin Business, Latin Trade) - Wire services | Local interviews conducted with BU CEOs and other spokespersons | BU PR team to coordinate with BU CEOs | Second day and during week of announcement |
| Stakeholder reaction | Evaluation from management team on their findings and reaction by stakeholders to new entity. Determine whether a visit by Corp. or Joe Sutton is needed to meet with key stakeholder such as partner or govt. official | In country leadership team to share findings with CALME management (David Haug, Shawn Cumberland, Mariella Mahan, Dan Castagnola, Rick Bergsieker) and BU PR either through mail or weekly calls. | Second day and during week of announcement |

Day 1-2: The Announcement (internal – target audience: EI employees)

| CORPORATE FOCUS (SELLER) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Action | Description | Responsibility | Timing |  |  |
| Voice mail – notification of all employee meeting (Houston employees) | Message from Enron Corp. CEO and / or Newco CEO | BU PR, Corp PR & HR, Ken Lay or Joe Sutton | Day of Announcement (Prior to release) |  |  |
| Email – employee notification (All Houston and international employees) | Message from Enron Corp. CEO and / or Newco CEO. Include employee Q&As | BU PR, Corp. PR & HR, Ken Lay and / or Joe Sutton | Day of Announcement (Coincide with release) |  |  |
| All employee meeting (possible, tele conferencing, webcasting, video) (All Houston employees and international employees) | Briefing to employees Enron Corp CEO and / or Newco CEO, defining benefits of the transaction | Corp PR, BU PR & HR, Ken Lay and/or Joe Sutton | Day of Announcement (One hour before or after release) |  |  |
| Intranet message | Message on BU website from chairman modified. | BU PR | Day of Announcement |  |  |
| Videotape message | Message to employees from BU chairman, defining benefits of the [Newco] | BU PR | Day of Announcement- sent to BU offices |  |  |
| Rally cry | Employee letter and promo item (T-shirt) sent to all new employees (letter translated into other languages) | BU PR | Day of announcement |  |  |
| Videolink session | Q&A session with BU Chairman | BU PR, BU Chairman |  |  |  |

| CALME BU FOCUS (BUYER) |  |  |  |
| --- | --- | --- | --- |
| Business Unit Management Team briefing | Management Team briefed in confidence by BU CEO about deal and upcoming internal and external communication roll-out | BU CEO, HR, PR | Day of Announcement |
| In-country employee meetings with teleconferencing or video link to BU headquarters | BU CEO/country managers to meet with employees, defining benefits of the transaction. Answer general questions re: deal and HR issues | # Top Management and HR | # Day after announcement |
| All employee meeting (EI) – Joe Sutton | - Reserve space at hotel ASAP - Prepare for video recording or webcast of the meeting - Prepare for conference call phone line for outside callers to listen | BU PR | # Day after announcement |
| Feedback forum including eSpeak by Joe Sutton, BU CEOs, and HR | Collect suggestions, ideas, etc. from employees (could be a web-based tool). Enron and BU Intranets used for updates, Q&As, new leadership details and policies. Set up 800# for employees to call and leave messages/questions | Corp PR, BU PR team, HR, Joe Sutton | Rest of week (next five days) |