ETS Asset Development

PROJECT SUN DEVIL

EXECUTIVE SUMMARY

I.  Description / Scope

Project Sun Devil is a $911 million expansion of Transwestern Pipeline’s interstate natural gas system.  The project is designed to move incremental San Juan and Rocky mountain gas production through 490 miles of new pipe looping and compression to serve growing Phoenix, AZ and Southern California markets.

The project would begin in San Juan County, NM by looping TW’s existing San Juan lateral.  The 36-inch loop would start at the Blanco hub going south to the Gallup compressor station.   Modifications would need to be made at both the Bloomfield and Gallup, NM compressors plus modifications to the Blanco hub facilities.  A new compressor will also be required at the Standing Rock location in the Navajo territory.

The mainline looping going west from Gallup will consist of 188 miles of 36-inch pipe.  At Flagstaff, AZ, a new 175 mile 36” lateral will be built that runs south to Phoenix in Maricopa County, AZ.  To minimize cultural and environmental impacts, the Phoenix lateral will follow existing rights-of-way where possible.

At Phoenix, the lateral would loop to the west to access the growing gas-fired electric generation market and a newly proposed salt dome storage cavern.  Phoenix area gas demand is expected to grow by over 1.5 Bcf/day by 2003 with the start-up of these new generators.

The project would be sold according to the path and capacities shown below:

I. A.  Capacities

San Juan Lateral 			780,000 MMBtu/d

Thoreau west to Cal Border		310,000 “         “

Phoenix, AZ				500,000 “         “

I. B.  Timing:

Binding Open-season closed August 30, 2001

FERC application September 2002

Submit binding contracts and EIS to FERC by October 2002

Pipe in-service date Q3 2004

# II.  Commercial Summary

# II. A. Gas Market

The Project’s goal is to deliver incremental gas supplies from the transport-constrained San Juan basin to the growing Phoenix market.  The Phoenix area has been the 2nd fastest growing region in the continental U.S. for the last several years.  The area has also been electric supply constrained and local utilities import as much as 25% of their generation needs annually.

To address the area growth, local utilities and independent power producers have successfully petitioned the Arizona Corporation Commission to allow new large-scale gas-fired generation plants to be constructed.  Developers such as Sempra, PG&E, Duke, Reliant Energy, Panda International, and AZ Public Service have all broken ground on new generation projects (see attached plant listing).

The problem these new generators face is the lack of firm pipeline transport capacity.  Some generators hold firm capacity on El Paso Natural Gas (EPNG) due to their existing full-requirements contracts; others have had to rely on the secondary release market or marketers who hold firm transport.  Incremental transport demand from these new generators is projected to be as high as 1.5 Bcf/day.

# II. B.  Transport Market

To date, EPNG has been the sole pipeline serving the needs of Phoenix.  EPNG shippers source gas supply from both the Permian and San Juan basins.  Population growth in the Southwest over the last several years has put a severe strain on EPNG’s capacity, especially in peak summer cooling and winter heating demand periods.  This was evidenced most recently during the winter of 2000-01 when shippers holding firm contracts were cut upwards of 40% of their transport demands.  These figures do not include the anticipated demands created by the new electric generators when they begin plant start up in 2002-03.

As a result of 2000 – 2001 winter transport debacle, EPNG shippers have protested to FERC to revise the method in which EPNG allocates its system.  Shippers have also accused EPNG of over-subscribing its pipeline capacity.  Shippers estimate EPNG being short capacity ranging from 300,000 MMBtu/d to as much as 1 Bcf/d, again, exclusive of the new demands from local area generators.

Part of the constraint on EPNG is due to the Full Requirements (FR) contracts held by LDC’s, generators, and some industrial concerns.  Under the FR contracts, EPNG is obligated to serve 100% of the FR needs, sometimes at the expense of contract demand (CD) customers.  FERC is currently exploring ways to either abrogate or restructure these FR contracts.  Settlement is expected to occur sometime in the first half of 2002.

# II. C. Competition

EPNG

El Paso Natural Gas has two mainline transmission systems, north and south, that traverse Arizona flowing east to west.  El Paso has several options to compete with Sun Devil.  To compete on a heads-up basis, El Paso would need to construct a similar project of similar size from the San Juan basin.  Any further expansion of EPNG’s north system is unlikely due to current pipe diameter constraints.  Another critical factor is EPNG has only recently begun re-negotiating their ROW contract with the Native American Indian tribes on whose property a majority of the north system lies.  El Paso would be cautious to put any new assets at risk until this ROW is settled.  TW settled its Navajo ROW in 2001, so we have a basis for knowing how much ROW will cost for the Project.

In 2000, EPNG purchased the All American crude oil system and converted it to natural gas service (effective August 2001).  All American roughly parallels the existing EPNG south system.  By adding compressor stations to All American, EPNG could boost capacity by as much as 500,000 MMBtu/d to the California border.  Estimated cost of this expansion is $330 million.  However, the gas source would be the Permian basin and its capacity would not be enough to serve all the market needs.

## Sonoran

Kinder-Morgan – KMI, with their partner Calpine, have proposed a new high capacity gas transmission system (the Sonoran Project) that parallels the existing TW system in the San Juan basin all the way to the California border at Needles (phase I).  A large portion of Sonoran Phase I literally would reside in the same Navajo ROW as TW.  Sonoran Phase II proposes to run north from Needles up to Sacramento, CA.  KMI desires to compete with the PGT system in California to meet the needs of new California electric generators.

With the currently depressed western electric market and Calpine’s recently announced cutback in new project development, it may be that this project is no longer viable.  KMI informed us they were going out for a second open season in January 2002, but to date we have not seen anything.  In addition, Williams has re-floated their Ruby Pipeline project that will compete directly with Sonoran for the northern California market.  Williams has the advantage in that they will source cheaper gas to northern California via Opal, Wyoming than will Sonoran from San Juan.

## Desert Crossing

This new 10 Bcf storage project is sponsored by Salt River Project, Sempra Energy, and Allegheny Energy.  The sponsors hope to build, based on a successful open season, a high-capacity salt dome storage cavern near Kingman, AZ.  The project would source gas via a new lateral from Kern River, and re-deliver gas to existing lines owned by TW, El Paso, PG&E, So-Cal, and Questar.  They also propose to build a new 200-mile lateral south from Kingman and tie into El Paso’s south system.  The sponsors then hope to move gas both east (via displacement) and west to electric generation plants.  Storage rates are ______ plus another ______ for pipeline transport.  The project is expected to be built in 2.5 Bcf increments.

## Copper Eagle

This 10 Bcf storage project was announced in the fall of 2000 and is located on the west side of Phoenix on a salt dome near Luke Air Force Base.  The sponsors include Arizona Public Service, Crystal Gas, and the French utility, Gaz de France.  Designed to serve the high peaking needs of Phoenix area power generators, it is proposed to be built in 2.5 Bcf increments.  Projected rates are $0.40/MMBtu plus injection and withdrawal fees.  Their issue, in addition to the brine disposal during construction, is getting pipeline capacity to fill the storage without a Phoenix area expansion project such as Sun Devil.  The sponsors expect to file their FERC application in March 2002.

## Pataya / Red Lake

This 12 Bcf storage project is proposed by SouthWest Gas and Aquila Energy.  Pataya is located in the same salt formation as Desert Crossing near Kingman.  They propose to build the facility in increments of 6 Bcf and claim to have all the necessary water and disposal permits necessary.  Pataya proposes to source and redeliver gas to TW and El Paso.

# II. D.  Gas Supply

The Project will source gas from the prolific San Juan production basin plus use existing TW interconnects with pipelines connected to Rocky Mountain producers.  Historically, San Juan-sourced gas prices have been depressed relative to Permian gas due to the lack of San Juan transport capacity (see attached basin spread analysis). Both TW and EPNG systems in the San Juan basin have been completely sold out for several years and maintain 95+% utilization rates.

San Juan and Rocky Mountain supply projections completed by a 3rd party consultant indicate enough supply reserves exist to fill the demands of the Project.  However, there is not enough supply to fill both Sun Devil and KMI’s Sonoran project.  TW would also be able to source a small amount of incremental supply from the Panhandle or Permian basins.

# II. E.  Prospective Shippers

The table below outlines the prospective shippers for the Sun Devil project and the electric generation plants proposed or under construction.

| Sun Devil Power Generators |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | In-Service |  | MMBtu/d | Sun Devil |
| Developer | Plant | Cap. Mw | Date | Status | Gas Demand | Est. Demand |
| AZ Public Service | W Phoenix | 366 | Old | Operating | 97,262 |  |
| AZ Public Service | W Phoenix | 120 | 6/1/01 | Operating | 20,736 |  |
| SRP | Agua Fria | 600 | Old | Operating | 97,600 | 30,000 |
| Duke | Arlington Valley | 550 | 6/1/02 | Under Construction | 125,000 | 50,000 |
| Pinnacle West | Redhawk | 1,160 | 6/1/02 | Under Construction | 210,000 | 100,000 |
| Sempra Energy | Mesquite | 1,300 | 1/1/03 | Under Construction | 220,490 | ?? |
| Panda Energy | Gila Bend | 2,300 | 3/1/03 | Under Construction | 390,098 | 100,000 |
| PG&E | Harquahala Valley | 1,083 | 6/1/03 | Under Construction | 178,825 | ?? |
| Dynegy, Xcel, SRP | Kyrene | 265 | 6/1/03 | Advanced Devlpmt | 45,315 | 20,000 |
| Pinnacle West | West Phoenix | 500 | 6/1/03 | Under Construction | 86,352 | 50,000 |
| Energy Dev Group | Gallup | 1,200 | 7/1/04 | Early Development | 216,000 | 216,000 |
|  |  | 9,444 |  |  | 1,687,678 | 566,000 |

III. Project Economics

III. A. Assumptions

The project assumes a 14% return on equity using an 80/20 debt/equity structure on a $911million capital cost.  Debt interest rate is estimated at 7.5% with an economic project life of 30 years and 100% load factor.  Fuel is estimated at the current TW fuel rate of 4.75% for the first few years of the project life then converting to a fuel tracker with the next TW rate case in 2006.  O&M expense escalates at 3% per annum.  Near worst-case scenarios for ROW acquisition have been used considering the 220 miles of construction through Native American tribal lands.  This assumption is valid considering TW’s recent re-negotiation of Tribal ROW.  The rate schedule below is based on levelized assumptions for the various terms:

IV. Project Cost

IV. A. Engineering

The project cost estimate is based on 2001 dollars and is escalated for inflation to the time period when construction will begin.  The estimate is considered a “Level A+” estimate that barring unforeseen issues should not rise any higher.  For a more detailed and exacting Level B estimate, additional development monies would need to be spent.  Below is a description by pipe segment of the facilities required:

•San Juan lateral – 780,000 MMBtu/d

–97 miles of 36” loop

–Standing Rock compressor station

–Compressor mods at Bloomfield, Bisti, and Gallup

•Mainline  – 810,000 MMBtu/d

–224 miles of 36” loop

–New compressor at station 4, 1.5, and Kingman

–Compressor mods at stations 2 and 3

•New Phoenix lateral  - 500,000 MMBtu/d

–168.8 miles of 36” line, no compression

–Delivers to Copper Eagle storage, Panda lateral from El Paso south system

Sun Devil Project Costs:

# IV. B. Environmental

Third-party contractors were commissioned to perform an initial site survey along the proposed ROW path.  Inquiries were made to local state agencies and conservation groups; no material “deal-killer” issues were discovered.

# V. Regulatory

A budget has been established for costs necessary to get the Sun Devil project application filed with the Federal Energy Regulatory Commission.  The $8,750,000 budget includes costs for regulatory filing, right-of-way due diligence, field surveys, aerial photography, environmental due diligence, and project engineering.

# VI. Administration

Team Members (see attached page)

Project costs spent as of January 22, 2002 equal $100,976.70 of $200,000 budget.

File directory (see attached page)