TELEMARKETING TIME LINE

August 20, 2001

| Issue | State | Responsible Person(s) | Completion Date |
| --- | --- | --- | --- |
| Obtain Telemarketer Permit from NY Sec. of State | New York | Gloria Ogenyi | 10 to 15 business days after filing per SOS * |
| Finalize Scripts | New York New Jersey Texas | Sarah Dietrich (All) Marianne Castano, (All) Nicole Schwartz, (NY/NJ) JJ Saltsman (TX) | August 24 |
| File Script with NY PSC | New York | Gloria Ogenyi | August 27 |
| Set up document retention system | New York New Jersey Texas | Nicole Schwartz (NY, NJ) Suzanne Farrow (TX) | TBD after consultation with NS and SF |
| Set up system for maintaining Do Not Call list | New York New Jersey Texas | Nicole Schwartz (NY, NJ) Suzanne Farrow (TX) | TBD after consultation with NS and SF |
| Set up system for taping of conversations | New York New Jersey Texas | Nicole Schwartz (NY, NJ) Suzanne Farrow (TX) | TBD after consultation with NS and SF |
| Finalize NJ Mini Contract (revise billing & price terms) | New Jersey | Sarah Dietrich, Gillian Johnson, Nicole Schwartz | August 22 |
| Translate Texas Mini Contract and supporting documents | Texas | Sarah Dietrich, | August 24 |

*   We are researching expediting this process.