| George C. Robinson, P.E. | c/o: ENRON Operations Corp. Environmental Affairs Dept. | (713) 646-7327 ENRON office (713) 646-7867 ENRON fax |
| --- | --- | --- |

Memorandum

| To: | Larry Campbell | Date: | August 15, 2001 |
| --- | --- | --- | --- |

From:	George C. Robinson

Subject:	Summary of “Contract Installation” Costs for 2001

| Project | Budget Catagory | W.O. # | W.O. Auth. Amount | INST Auth. Amount | INST Coded to-Date | INST Committed Additional | INST Estimated Remaining | INST Estimated Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sta. 5 Rem. | TW Cap. |  | 105,000 | 64,000 | 19,000 | 9,000 | 37,000 | 65,000 |
| Sta. 6 Rem. | TW Cap. |  | 66,000 | 35,000 | 29,000 | 1,000 | 20,000 | 50,000 |
| N. Crawar Rem. | TW Cap. |  | 73,978 | 38,100 | 36,000 | 2,000 | 92,000 | 130,000 |
| Bell Lake Rem. | TW Cap. |  | 89,842 | 56,700 | 26,000 | 5,000 | 26,000 | 57,000 |
| Atoka-1 Rem. | TW Cap. |  | 65,000 | 35,000 | 8,000 | 0 | 7,000 | 15,000 |
| Lockridge Plant Rem. | NNG Cap. |  | 113,896 | 57,400 | 30,000 | 3,000 | 70,000 | 103,000 |
| Subtotals: Capital |  |  | 513,716 | 286,200 | 148,000 | 20,000 | 252,000 | 420,000 |
| Laguna Soil Rem. | TW Exp. |  | --- | 0 | 0 | 0 | 0 | 0 |
| Roswell Rem. | TW Exp. |  | --- | 80,000 | 29,000 | 1,000 | 40,000 | 70,000 |
| Roswell Pit Removal | TW Exp. |  | --- | 510,000 | 0 | 0 | 510,000 | 510,000 |
| WT-1 Dehy Area Rem. | TW Exp. |  | --- | 20,000 | 6,000 | 1,000 | 8,000 | 15,000 |
| WT-1 Pit Area Rem. | TW Exp. |  | --- | 45,000 | 11,000 | 1,000 | 13,000 | 25,000 |
| Eunice Ground Water Mon. | NNG Exp. |  | --- | 5,000 | 0 | 2,000 | 3,000 | 5,000 |
| NNG Gomez Rem. | NNG Exp. |  | --- | 150,000 | 53,000 | 2,000 | 95,000 | 150,000 |
| Subtotals: Expense |  |  | --- | 810,000 | 99,000 | 7,000 | 669,000 | 775,000 |
| Totals: Cap. + Exp. |  |  | --- | 1,096,200 | 247,000 | 27,000 | 921,000 | 1,195,000 |

(a)  Figures only include Contract Installation $s