| George C. Robinson, P.E. | c/o: ENRON Operations Corp. Environmental Affairs Dept. | (713) 646-7327 ENRON office (713) 646-7867 ENRON fax |
| --- | --- | --- |

Memorandum

| To: | Distribution | Date: | November 5, 2001 |
| --- | --- | --- | --- |

From:	George C. Robinson

Subject:	Summary of “Contract Installation” Costs for 2001

| Project | Budget Catagory | W.O. # | W.O. Auth. Amount | INST Auth. Amount | INST Coded to-Date | INST Committed Additional | INST Estimated Remaining | INST Estimated Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sta. 5 Rem. | TW Cap. | C.014507.02.05 | 105,000 | 64,000 | 29,000 | 2,000 | 14,000 | 45,000 |
| Sta. 6 Rem. | TW Cap. | C.014510.02.05 | 66,000 | 35,000 | 35,000 | 11,000 | 4,000 | 50,000 |
| N. Crawar Rem. | TW Cap. | C.014568.02.05 | 70,264 | 55,000 | 39,000 | 4,000 | 12,000 | 55,000 |
| N. Crawar Monitor Wells | TW Cap. | C.014907.01.05 | 93,000 | 75,000 | 0 | 1,000 | 74,000 | 75,000 |
| Bell Lake Rem. | TW Cap. | C.014569.02.05 | 89,842 | 56,700 | 32,000 | 1,000 | 24,000 | 57,000 |
| Atoka-1 Rem. | TW Cap. | C.014513.02.05 | 65,000 | 35,000 | 9,000 | 1,000 | 5,000 | 15,000 |
| Lockridge Plant Rem. | NNG Cap. | C.014577.02.05 | 57,600 | 40,000 | 34,000 | 2,000 | 4,000 | 40,000 |
| Lockridge Plant Mon. Wells | NNG Cap. | C.014908.01.05 | 86,864 | 63,000 | 0 | 24,000 | 39,000 | 63,000 |
| Subtotals: Capital |  |  | 633,570 | 423,700 | 178,000 | 46,000 | 176,000 | 400,000 |

| Project | Budget Catagory | WBS # | 3rd Qtr. Current Estimate | INST Coded to-Date | INST Committed Additional | INST Estimated Remaining | INST Estimated Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ivanhoe Rem. | TW Exp. | NA | 50,000 | 0 | 0 | 36,000 | 36,000 |
| Roswell Rem. | TW Exp. | X.000993.113785300040 | 70,000 | 44,000 | 7,000 | 10,000 | 61,000 |
| Roswell Pit Removal | TW Exp. | X.001140.113785300040 | 510,000 | 17,000 | 2,000 | 285,000 | 304,000 |
| WT-1 Dehy Area Rem. | TW Exp. | X.000994.113985300061 | 15,000 | 8,000 | 1,000 | 6,000 | 15,000 |
| WT-1 Pit Area Rem. | TW Exp. | X.000995.113985300061 | 25,000 | 14,000 | 1,000 | 5,000 | 20,000 |
| Eunice Ground Water Mon. | NNG Exp. | X.000172.143286400404 | 5,000 | 2,000 | 0 | 1,000 | 3,000 |
| Gomez Rem. | NNG Exp. | X.000145.162486400398 | 150,000 | 58,000 | 12,000 | 35,000 | 105,000 |
| Bushton UST | NNG Exp. | NA | 25,000 | 0 | 1,000 | 9,000 | 10,000 |
| Cunningham Brine Leak | NNG Exp. | NA | 25,000 | 0 | 0 | 10,000 | 10,000 |
| Subtotals: Expense |  |  | 875,000 | 143,000 | 24,000 | 397,000 | 564,000 |

| Totals: Cap. + Exp. |  |  |  | 1,298,700 | 321,000 | 70,000 | 573,000 | 964,000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

(a)  Figures only include Contract Installation $s