#### LONG TERM  (12-24 MONTHS)

| OPTIONS | #### FACILITY DESCRIPTIONS | FLOW (*) mmcfd | COSTS $MM | TIMING months | #### ADVANTAGES | #### DISADVANTAGES | #### REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Install 152,000 HP (ISO): Scope consists of installation of one 38,000 HP (ISO) unit installed at Stations 1-4. | 150 (177) | 99.6 | 15-17 | - Air Permit will take 6-9 months - Additional 4000 HP/unit - No downtime required for modifications to existing units | - Tie-in downtime is 3-5 days/station - $30.8M more than Option 2 - Limited by pipeline capacity | Modification to existing units not required. Existing units to be abandoned. Total O&M cost is $2.8M/yr Throughput Loss: 200 mmcf/d (construction) 220 mmcf/d (operations) |
| 2 | Install 62,800 HP (ISO): Scope consists of installation of one 15,700 HP (ISO) unit installed in parallel to the existing units, and compressor modifications to all twelve existing units at Stations 1-4. | 140 (168) | 68.8 | 12-19 | - $30.8M less than Option 1 - Can handle variation of flow | - Downtime is 4 weeks per unit for unit modifications plus 3-5 days/ station for tie-ins - Air permit will take 12-18 months - Acoustic study required | Modifications to existing units required. This is estimated at $8M and is included in cost. Total O&M cost is $5.4M/yr. Throughput Loss: 150 mmcf/d (construction) 140 mmcf/d (operations) |

(*)  Incremental flow above current certificated capacity of 1090 mmcf/d with 825 psig delivery pressure at SOCAL Needles.

The additional flow number indicated in parenthesis is the incremental capacity with 800 psig delivery pressure at SOCAL Needles.

SHORT TERM   (0-6 MONTHS)

| OPTIONS | #### FACILITY DESCRIPTION | FLOW (*) mmcfd | COSTS $MM | TIMING | #### REMARKS |
| --- | --- | --- | --- | --- | --- |
| 1 | Application of Nalco/Exxon’s Enerflow to reduce friction on pipeline downstream of Station 5. | 60 | 3.0/year | 12-18 hr reduced flow | From Station 5 to Needles. Solvents other than diesel will be employed (e.g. methanol, condensates). Throughput Loss: 400 mmcf/d (mainline) |
| 2 | Install a launcher and receiver at the Bisti Compressor Station on the San Juan Lateral. | 10 | 1.7 | 48-hr shutdown | Efficiency increase of 4% is assumed. This will eliminate the need for Gallup modifications. Assumes contract fuel physical flow on San Juan Lateral to be 20 mmcf/d. Throughput Loss: 850 mmcf/d (San Juan Lateral) |
| 3 | Add inlet air cooling for ambient rating HP - consider ground water loop system or evaporative cooler. | 7 | 2.4 | 1 week per unit | Install turbocharger inlet air cooling to reduce inlet air temperatures from 80 to 55 degrees F to generate approximately 3% incremental HP at each station. (per unit cost $200,000 x 3 = $600,000 per station) Throughput Loss: LEVEL “A” ESTIMATE 75-225 mmcf/d |
| 4 | Add small pocket loading and poppet valves at Stations 1, 2, and 4. | 11 | 1.38 | 8 hrs/unit downtime | To be scheduled with other operations outages. Install small pocket loader on each unit (per unit cost $20,000 x 3 = $60,000 per station). Efficiency increase of 3% is assumed. Throughput Loss: LEVEL “A” ESTIMATE 75-225 mmcf/d |
| 5 | Decrease the SOCAL Needles delivery pressure to 800 psig. | 8-28 | - | - | Marketing to discuss options with SOCAL to reduce delivery pressure to 800 psig. Incremental flow is dependent upon available HP and the long-term or short-term option that is applied. |

(*)  Incremental flow above current certificated capacity of 1090 mmcf/d with 825 psig delivery pressure at SOCAL Needles.