RED ROCK PROJECT WEEKLY REPORT (ENRON INTERNAL)

# WEEK ENDING – JANUARY 24, 2002

- ACTIVITIES:

- The first two NP units are at the Port of Houston and ship will dock sometime on the 24th.  Station 1 and 2 need date on site is 2/6 (pending building permit receipt this week at Station 2).  Compressors and Turbine skids will be shipped together and the Gas Generators will be shipped separate.

- Testing slippage in Italy on the third unit has delayed shipment until the second week of Feb ’02.  Testing is being conducted this week and Fire Test is scheduled sometime during January 25th – 31st.  ETA to site is mid March.

- NP reps should arrive at Stations 1 & 2 around mid February.

- Arnold will expedite telephone & communications issues at sites, especially Station 2.

- As a result of expediting and most of the current payment issues being resolved with vendors, a majority of the needed pipe, valves, and fittings should start arriving on site early next week.

- Station 1 and 2 will pour main block foundation on 1/26.

- Station 2 needs to get building permit before any concrete is poured.  Ron Roller will visit County Authority today to resolve issue.

- Station 1 – Complete Compressor Building rebar and anchor bolts.  Continue foundation excavation and formwork.  Fabricate available piping until large bore materials arrive next week.

- Station 2 – Compressor Building rebar mat and anchor bolt supports are complete. Set forms for cooler foundations.  Fabricate 8” blow down piping.  Install Compressor Building grounding.

- Station 3 – Complete compaction of sub grade and seal slab for compressor foundation.  Start excavation of PCR Building and Scrubber foundations.

- OBJECTIVES FOR NEXT WEEK:

- Leonard Meeks to confirm that archeological area at Station 1 has been fenced off as required.  Contractor has erected most of the fence.  Material for last 100’ section is on back order and the area has been flagged off.

- Negotiate and issue payments to vendors as required to maintain project schedule.

- Confirm receipt of County Building Permit for Station 2.

- Larry Campbell to set up an Environmental training kick off meeting at each site.

- Environmental Training videos have been located and videos will be forwarded to each site.

- Complete testing of Unit 3 in Italy.

- AREAS OF CONCERN:

- In service Dates remain as previously published:

  - Stations 1 & 2: June 15, 2002

  - Station 3: July 01, 2002

- Current Schedule Issues

  - GEA Rainey Gas Coolers – (CRITICAL ITEM) Waiting on response from GEA Rainey to advise of new delivery dates, they are not returning phone calls.

  - Markham 36” Check Valves – Bodies are currently being machined in Germany and will complete on Jan 31st.  Nozzle diffusers started machining this week and will also complete Jan. 31st.  All material and parts have been received and final assembly should start the first week of February.  All three valves should ship by February 15th.  Need to resolve any pre-payment issues that may potentially delay shipping.

  - Taylor Forge – Enron Engineering submitted a fabrication priority list and Taylor has responded with shipping dates.  Currently working two shifts, 60 hours/week and Taylor does not see any way to further expedite these ship dates at this time.  Priority is above ground sections first for Station 1, 2 and then 3.

  - Shaffer Actuators – Station 1 arrived on site, Station 2 on site, Station 3 will ship by 1/30/02.

  - Perry Equipment – Waiting on call back from Kim Long with PECO to confirm that they intend to ship the Station 1 scrubber and auxiliaries on 1/25/02 and Station 3 will ship on 2/14/02.

  - Daniel – Gas Chromatograph was put on hold three weeks ago without notification from vendor.  Resolving payment concerns / issues.  Need date on site is May 1, 2002 and Operations will install.

  - GULFEX – Second payment, in the form of an ACH, was scheduled to be made on 1/15/02 and they just received their money on 1/24/02.  As a result, the start of Station 3 piping fabrication was delayed a week.

- Cash flow and spending caps for 2002, and the resulting further impacts to scheduled in service dates.

- Material and Equipment delays due to Vendors requesting advanced or pre payments before shipping.  Also the associated additional delay for Enron to issue checks/payments and vendor to receive payment.

- Delayed Construction start date and winter construction.

- Maintaining Nuovo Pignone testing and delivery schedule.

- FINANCIAL STATUS:

- Project costs through December are approximately $23.5M and commitments total $45.4M.

- December expenditures were $9.5K and commitments were $6.2M.