RED ROCK PROJECT WEEKLY REPORT (ENRON INTERNAL)

# WEEK ENDING – February 14, 2002

- ACTIVITIES:

- Third unit should load this week in Italy and arrive at Port of Houston 21 days after vessel leaves Italy.

- NP rep continues to support activities at Stations 1 & 2.

- Continue to expedite telephone & communications issues at sites.

- Monitoring Station 4 Overhaul schedule with Optimization & Planning.

- Station 1 – Station 1 Turbine is on site and will be set 2/14/02.  Compressor is already set on foundation.  Continue excavating and concrete foundation activities.  Reviewing tie-in schedule with Operations.  The loop line tie-in point is out of square with the main line, and Leonard will work with Earl to come up with a work around plan for the loop line tie-in.

- Station 2 – Station 2 Turbine and Compressor were set on 2/12.  Continue civil excavation, foundation and backfill activities on the Compressor, Cooler and miscellaneous foundations.  Received all Building Permits from Coconino County.  Fabricating 36” unit suction and discharge piping.  Continue U/G conduit placement and backfill in the Cooler and Scrubber Areas.

- Station 3 – Continue rebar installation and formwork activities for Compressor, Cooler, Scrubber, and Generator Building foundations.  Placement of Compressor foundation concrete is now scheduled for Feb 16th, and not the 12th, due to concrete availability.  Continue to weld available spools on pipe systems 12” or larger.

- OBJECTIVES FOR NEXT WEEK:

- Procurement needs to follow up and status Airdyne Purchase Order.

- Need to make arrangements to get the Meter Run material to PECO that was accidentally shipped to Station 2.

- Negotiate and issue payments to vendors as required to maintain project schedule.

- Larry Campbell to set up an Environmental training kick off meeting at each site.

- Environmental Training videos have been located and videos will be forwarded to each site.

- AREAS OF CONCERN:

- In service Dates :

  - Stations 1 & 2: June 15, 2002

  - Station 3: July 15, 2002.  Slipped two weeks based on firm Cooler delivery date of May 31, 2002 not supporting Construction need date of 3/1/02.  Working with Vendor to try and improve Station 3 to 4/1/02, which is current ship date for Stations 1 & 2.

- Current Schedule Issues

  - GEA Rainey Gas Coolers – (CRITICAL ITEM) Working to improve Station 3 delivery date.  Need date at all three Stations is 3/1/02.  P.O has been revised and received today for Enron signature.  Station 1 & 2 delivery is currently 3/31/02 and Station 3 is 5/31/02.

  - Markham 36” Check Valves –  All three valves should ship on February 15th with a mid-March delivery to site.

  - Taylor Forge – Enron Engineering has submitted a fabrication priority list.  Currently working two shifts, 60 hours per week, and Taylor does not see any way to further expedite ship dates at this time.  Procurement has received a payment schedule and approximate due dates.  Ex-Works dates are as follows: Station 1 - 3/8 & 3/29, Station 2 - 3/1 & 3/22, and Station 3 – 3/15 & 4/5.

  - Perry Equipment – Station 1 & 2 scrubbers and auxiliaries are on site and Station 3 should ship on 2/14/02.  All issues have been resolved on the Domestic and Fuel Gas skids, and scheduled to ship all three stations on 2/20/02.

  - Daniel – Gas Chromatograph was put on hold without notification from vendor.  Resolving pre-payment issues.  Need date on site is April 1, 2002 and current ship date is 2/28/02, which is acceptable.  Operations will install.

  - Burgess Manning – Silencers and scrubbers for all three sites will be ready to ship 2/15/02.

  - Cleveland – PCR Building and associated equipment for all three Stations will be ready the week of February 12th and arrive on site February 22nd.

  - SISCORP – Building components are scheduled to arrive on site: Station 1 – 2/18/02, Station 2 – 2/15/02, and Station 3 – 3/04/02.  Generator Buildings will arrive on site as follows: Station 1 – 3/11/02, Station 2 – 2/25/02, and Station 3 – 3/5/02.

  - Altofer – Gen Sets are tested and ready for all three stations.  Switchgear is ready for Stations 1 & 2, and Station 3 should be ready by 2/22/02.  Expect 2% discount for pre-payment.  Vendor invoice for pre-payment was received, and Enron is processing wire for a 2/15 payment and subsequent 2/18 shipping release date.

  - GULFEX -  Welding of Station 3 spools will complete this week and spools will go to paint yard on 2/18 and ship to site on 2/25.  Remaining Station 2 spools shipped to site on 2/10.

- Cash flow and spending caps for 2002, and the possible further impacts to forecasted in service dates.

- Material and equipment delays as a result of Enron’s current financial situation.

- Late construction start date and mobilization during winter months.

- Construction progress is falling behind plan to support current in-service dates.  Reviewing schedules and developing plans to minimize impact.

- Monitoring Station 4 overhaul schedule with Optimization & Planning.

- FINANCIAL STATUS:

- Project costs through January are approximately $34.5M and commitments total $49.4M.

- January expenditures were $11.0M and commitments were $4.0M.

- Expenditures are running ahead of plan due to accelerated payments for goods & services.