RED ROCK PROJECT WEEKLY REPORT (ENRON INTERNAL)

# WEEK ENDING – February 21, 2002

- ACTIVITIES:

- Third unit did ship from Italy last week and should arrive at the Port of Houston in roughly three weeks.

- NP rep continues to support activities at Stations 1 & 2.

- Arnold & Lisa went to GEA Rainey in Tulsa to expedite and resolve issues surrounding the Gas Coolers.  Third unit delivery was improved one month.

- Continue to expedite telephone & communications issues at sites.

- Monitoring Station 4 Overhaul schedule with Optimization & Planning.

- Meter Run material was shipped to PECO from Station 2.

- Station 1 – Continue excavating and concrete foundation activities. Grouting of sole plates on compressor/turbine skids. The loop line tie-in point is out of square with the main line, and will be corrected by rolling and/or pushing the line; can also make adjustments at the tie-in locations with additional fittings. Excavation of the line continues as conditions allow.

- Station 2 – Continue civil excavation, foundation and backfill activities on the Compressor, Cooler and miscellaneous foundations.  Started rubbing down all foundations that have been poured.  Started pre-alignment of Compressor and Turbine.  Fabricating 36” unit suction & discharge, 16” recycle, and 6” blow down piping.  Continue U/G conduit placement and backfill around the PCR and Generator Buildings.  Start grounding at Compressor Building and continued PCR grounding.

- Station 3 – Continue civil activities on Compressor, Cooler, Tank Area, PCR, and Generator Building foundations.  Placed first lift (597CY) of compressor foundation.  Compressor foundation is scheduled to be complete on 2/21/02.  Completed both Scrubber foundations.  All fabrication has been completed at F&B Yard and received at site.  Continue fabrication of available pipe at site.

- OBJECTIVES FOR NEXT WEEK:

- Negotiate and issue payments to vendors as required to maintain project schedule.

- Larry Campbell to set up an Environmental training kick off meeting at each site.

- Environmental Training videos have been located and videos will be forwarded to each site.

- AREAS OF CONCERN:

- In service Dates :

  - Stations 1 & 2: June 15, 2002

  - Station 3: July 15, 2002.  Slipped two weeks based on firm Cooler delivery date of May 31, 2002 not supporting Construction need date of 3/1/02.  Working with Vendor to try and improve Station 3 to 4/1/02, which is current ship date for Stations 1 & 2.

- Current Schedule Issues

  - GEA Rainey Gas Coolers – (CRITICAL ITEM) Need date at all three Stations is 3/1/02.  Station 1 & 2 delivery is currently mid March and Station 3 is end of April. Rainey will try to improve Station 3 deliveries, and will look at partial shipments as individual coolers are completed.

  - Markham 36” Check Valves –  All three valves should have shipped on February 15th with a mid-March delivery to site.  Current ship date is now February 22nd, an additional one week slip. Wire transfer was sent on 2/14/02 to Germany, and we are waiting on a response to confirm receipt and an actual ship date.

  - Taylor Forge – TF has changed up the priority list, but engineering reviewed it and approved.  Ex-Works dates are as follows: Station 1 - 3/15 & 3/29, Station 2 - 3/1 & 3/22, and Station 3 – 3/8 & 4/5.

  - Perry Equipment – Station 1 & 2 scrubbers and auxiliaries are on site.  Station 3 will ship in two partial shipments, one on 2/22/02 and the other on 2/28/02.  Due to the meter runs arriving on 2/15/02, the ship dates on the Fuel Gas Skids slipped 8 days to 2/28/02.  The Domestic Gas skids are still scheduled to ship on 3/26/02.

  - Daniel – Gas Chromatograph was put on hold without notification from vendor.  Resolving pre-payment issues.  Need date on site is April 1, 2002 and current ship date is 2/28/02, which is acceptable.  Operations will install.

  - Airdyne – Vendor has cancelled all Enron Orders without notice.

  - Danmar – New supplier for the air compressor/dryer assemblies.  Quote was 10 weeks from 2/7/02.  Danmar talked to IR on 2/15/02 and will now commit to an 8 week delivery, but push for 6 weeks.  Ben Giusti, previous Airdyne salesman, has accepted a position with Danmar and will work our order.  Ben will get drawings to Byron by 2/21/02.

  - Burgess Manning – Silencers and scrubbers for all three sites are ready to ship and shipping address has been sent to NY.

  - Cleveland – All three PCR Buildings shipped on 2/18/02 and should arrive on site 2/22/02.

  - SISCORP – Building components for Station 1 arrived on site 2/18/02, Station 2 arrived 2/15/02, and Station 3 is scheduled to arrive on 3/04/02.  Generator Buildings will arrive on site as follows: Station 1 – 3/11/02, Station 2 – 2/25/02, and Station 3 – 3/5/02.

  - Altofer – Gen Sets are tested and ready for all three stations.  Switchgear is ready for Stations 1 & 2, and Station 3 should be ready by 2/22/02.  Expect 2% discount for pre-payment.  Altofer has received their money and released equipment to start shipping on 2/20/02.

  - GULFEX - Station 3 spools will all ship by 2/22/02.

- Cash flow and spending caps for 2002, and the possible further impacts to forecasted in service dates.

- Material and equipment delays as a result of Enron’s current financial situation.

- Late construction start date and mobilization during winter months.

- Construction progress is falling behind plan to support current in-service dates.  Reviewing schedules and developing plans to minimize impact.

- Monitoring Station 4 overhaul schedule with Optimization & Planning.

- FINANCIAL STATUS:

- Project costs through January are approximately $34.5M and commitments total $49.4M.

- January expenditures were $11.0M and commitments were $4.0M.

- Expenditures are running ahead of plan due to accelerated payments for goods & services.