RED ROCK PROJECT WEEKLY REPORT (ENRON INTERNAL)

# WEEK ENDING – February 28, 2002

- ACTIVITIES:

- Third unit should arrive at the Port of Houston on March 21, 2002 and site around March 28th.

- NP rep continues to support activities at Stations 1 & 2, and they are working on getting a second rep into the U.S..  A meeting with NP Management is scheduled for March 12, 2002 in Flagstaff to discuss Commissioning sequence and activities.

- NP will ship all three couplings from the factory to Station 2.  ETA at Station 2 is week of March 4th.

- Continue to expedite telephone & communications issues at sites.  Order has been place for satellite email service at Stations 1 & 3.

- Monitoring Station 4 Overhaul schedule with Optimization & Planning.  Outage planned for March 4th thru March 11th.

- Jerry Martin and Arnold Eisenstein made site visits this week.

- Steve Crabtree visited sites to review contractor issues and review pipe testing procedures.

- Station 1 – Continue excavating and concrete foundation activities. The loop line tie-in point is out of square with the main line, and will be corrected by rolling and/or pushing the line; can also make adjustments at the tie-in locations with additional fittings. Excavation of the line continues as conditions allow. Tie-in scheduled to start on March 4th.

- Station 2 – Continue civil excavation, foundation and backfill activities on the Compressor, Cooler and miscellaneous foundations.  Started erecting the Compressor Building.  Pre-alignment of Compressor and Turbine was stopped due to a missing hub.  Fabricating 36” unit suction & discharge, 16” recycle, and 6” blow down piping.  Install conduit at PCR Building, Generator, Scrubber and Cooler areas.  Install grounding and lighting grids around Compressor Building.

- Station 3 – Continue civil activities on Compressor, Cooler, Tank Area, PCR, and Generator Building foundations.  Placed second lift of compressor foundation and piers inside Compressor Building.  Set scrubbers on foundations.  Continue fabrication of available pipe at site. Install conduit at PCR Building, Generator, and Cooler areas.

- OBJECTIVES FOR NEXT WEEK:

- Negotiate and issue payments to vendors as required to maintain project schedule.

- Station 1 tie-in scheduled to start on March 4, 2002.

- Resolve issues with Donaldson at Station 2.  Gather back charge costs and forward report to Stations 1 & 3.

- Continue communications and work issues with power company at Station 1.

- Resolve Building Erector issues at Station 1.

- Verify Rosemount P.O. has correct quantities and is complete.

- AREAS OF CONCERN:

- In service Dates :

  - Stations 1 & 2: June 15, 2002

  - Station 3: July 15, 2002.

- Current Schedule Issues

  - GEA Rainey Gas Coolers – (CRITICAL ITEM) Committed to completing Station 3 by April 30 and Station 1 and 2 by March 31.  They will try to complete all the oil coolers at the same time in March and continue to do everything they can to improve these delivery dates. They have started working Fridays and Saturdays in an effort to improve.  Workaround Plan: Authorized shipping two sections of Station 1 Coolers to Station 3 in order to verify and begin spacing and tie-ins at Station 3.

  - Markham 36” Check Valves – Valves were picked up 2/26/02 by the forwarder, shipment is booked for a 3/7/02 departure and arriving in Houston on 3/20/02.

  - Taylor Forge – They have received two payments from Enron for their first two shipments.  As scheduled, 3A & B are in painting and will ship on 3/1/02 to Station 2.  Items 4A & B are in blasting then painting and scheduled to ship on 3/8/02 to Station 3.  They are on schedule with all remaining work. Ex-Work dates are Station 1 – 3/15/02 & 3/29/02, Station 2—3/1/02 & 3/22/02 and Station 3—3/8/02 and 4/5/02.

  - Perry Equipment – Scrubbers & Aux. For Station 3—1st half arrived on-site 2/26/02; the last half will ship 2/28/02.  The Fuel Gas Skids passed inspection on 2/27/02 and will ship to all 3 Stations by 3/1/02.  Due to “change orders” the Domestic Skids are set to ship on 3/26/02, however they are trying to improve that date.

  - Daniel – Gas Chromatograph was put on hold without notification from vendor.  Received/processed invoice for ACH to pay by 3/4/02. GC is on schedule to be complete by 2/28/02.  Will ship after receiving payment maybe 3/5/02.

  - Danmar – This is a replacement order for Airdyne.  IR has improved delivery of the Air Compressor from 10 weeks to 8 weeks (4/5/02).  They are still pushing to complete in 6 weeks (3/25/02). The drawings will be to Byron on Thursday 2/28/02 by 9am

  - Burgess Manning – Shipped out 2/21/02 should arrive at all 3 Stations by 2/28/02.

  - Cleveland – The PCR Buildings arrived at Station 1 and 2 on 2/22/02.  Station 3’s PCR Building is scheduled to be inspected on 3/1/02 and ship on 3/5/02.  The Gas Chromatograph (GC) Building for Station 2 is scheduled to ship on 3/20/02.

  - SISCORP – Station 2 received their Compressor Building (CB) on 2/15/02 and their Generator Building (GB) on 2/25/02.  Station 2 received their CB on 2/18/02 and their GB is scheduled to arrive on 3/11/02.  Station 3 is scheduled to receive their CB on 3/4/02 and their GB on 3/5/02, however some shipments are already arriving.

  - L F Manufacturing - The 24”dia x 8’3” tanks- 1 ready 3/12/02 and the remaining 2 on 3/20/02.  The 8’dia x 11’2” tanks-all 3 ready by 3/20/02.  Requested pre-payment prior to shipping.

AREAS OF CONCERN:

- Cash flow and spending caps for 2002, and the possible further impacts to forecasted in service dates.

- Material and equipment delays as a result of Enron’s financial situation.

- Late construction start date and mobilization during winter months.

- Construction progress is falling behind plan to support current in-service dates.  Reviewing schedules and developing plans to minimize impact.

- Monitoring Station 4 overhaul schedule with Optimization & Planning.

- FINANCIAL STATUS:

- Project costs through January are approximately $34.5M and commitments total $49.4M.

- January expenditures were $11.0M and commitments were $4.0M.

- Expenditures are running ahead of plan due to accelerated payments for goods & services.