RED ROCK PROJECT WEEKLY REPORT (ENRON INTERNAL)

# WEEK ENDING – OCTOBER 17, 2001

- ACTIVITIES:

- 30 day Public Notice started this week at all four stations.  Air Permits for all Stations are expected by the end of the year, and possibly by mid November.

- Station 2 tie-in work is currently re-scheduled for November 12th – 20th.  Gas Control has been notified and the outage posted.  Main line tie-in will be done first and then the loop line.

- Offsite fabrication of Station 2 tie-in assemblies and scrubber piping began at Foutz & Bursum’s yard in Bloomfield, NM on a T & M basis.

- Videoconference with Nuovo Pignone was held Thursday morning, and NP indicated that the fired unit testing in Italy on the third unit has been delayed until early Jan ’02.  ETS E&C Management Team is evaluating this impact and NP’s revised schedule.

- Resolved unit acceptance issues with NP during October 15th conference call.

- NP actively working to ship the first two units on December 15th.

- The load test on the first Gas Generator originally scheduled for October 10th in Cincinnati was moved to October 26th.  Engineering was informed today that the test has been moved up to October 21st, and Byron is confirming.  Engineering needs the names of anyone planning on attending the test at GE so they can get proper security clearances.

- Generators were re-finalized based on last weeks Air Permit issues.

- Generator engines for Station 3 were tested and they met emissions and horsepower requirements.

- Tree logging Contractor completed work at Station 2 on October 17th.

- Engineering and Contracts are working on construction bid clarifications.  Kickoff meeting notes and first set of clarifications will go out on October 19th.

- Issued a Purchase Order to GULFEX for pipe spooling.  Contractors will be notified of the 30% weld inch reduction in the bid clarifications going out next week.

- OBJECTIVES FOR NEXT WEEK:

- Complete NP Purchase Agreement.

- Award contract for PCR Building.  Low bidder is being queried on their bid qualifications.

- Negotiate Domestic Gas Skid contract with qualified low bidder.

- Complete County Building Permit Application for Station 2 and return to Roswell for processing.

- Expedite Air Permits.

- Gulfex start spooling of 10” Gas Cooler piping.  Material delivery scheduled for November 1st.

- Start Station 2 scrubber foundation activities and checking piping elevations at site.

- Issue second set of construction bid clarifications.

- OLD ISSUES:

- Construction bids are due November 7th, and contractor mobilization should be around December 1st.

- Current schedule, with minimal permit slippage from the original mid September date, still shows that an in-service date of June 1, 2002 for Stations 1, 2, & 3 is achievable, with favorable weather.  Project Schedule will be revised as new dates and information become available, and any changes to the target in-service date will be communicated to the team.

- AREAS OF CONCERN:

- Air permit and construction start.

- Nuovo Pignone testing and delivery schedule.

- Winter Construction.

- FINANCIAL STATUS:

- Project costs through September are approximately $12M.

- Treasury recovered the $7.8M they double payed NP on October 9th.